## Sheet2
Type | Task
Row Labels | Sum of Estimated Hours
Hardik | 110
Ronak | 111
Soumy Oza | 100
Parth Jani | 79
Grand Total | 400

## WBS
WBS ID | Task Name | Type | Estimated Hours | Developer
1 | HIMAPP 2.0 — Admin Module Implementation | Project | 400
1.1 | Epic 1: Dashboard & KPIs | Epic | 48
1.1.1 | US-01: Admin Views Real-Time Project Dashboard | User Story | 12 | Developer
1.1.1.1 | Database | Task | 2 | Parth Jani
1.1.1.2 | Backend API | Task | 3 | Parth Jani
1.1.1.3 | Web Front End | Task | 3 | Parth Jani
1.1.1.4 | Mobile | Task | 4 | Hardik
1.1.2 | US-02: Ready-to-Issue Banner Highlights Cleared Workers | User Story | 12 | Developer
1.1.1.1 | Database | Task | 2 | Parth Jani
1.1.2.1 | Backend API | Task | 3 | Parth Jani
1.1.2.2 | Web Front End | Task | 3 | Parth Jani
1.1.2.3 | Mobile | Task | 4 | Hardik
1.1.3 | US-03: Recently Registered Labour List with Quick Actions | User Story | 12 | Developer
1.1.1.1 | Database | Task | 2 | Parth Jani
1.1.3.1 | Backend API | Task | 3 | Parth Jani
1.1.3.2 | Web Front End | Task | 3 | Parth Jani
1.1.3.3 | Mobile | Task | 4 | Hardik
1.1.4 | US-04: Expiring Gatepasses Widget with Renew Shortcut | User Story | 12 | Developer
1.1.1.1 | Database | Task | 2 | Parth Jani
1.1.4.1 | Backend API | Task | 3 | Parth Jani
1.1.4.2 | Web Front End | Task | 3 | Parth Jani
1.1.4.3 | Mobile | Task | 4 | Hardik
1.2 | Epic 2: Labour Registration | Epic | 53
1.2.1 | US-05: Admin Registers New Labour via Four-Section Form | User Story | 14 | Developer
1.2.1.1 | Database | Task | 2 | Parth Jani
1.2.1.2 | Backend API | Task | 4 | Ronak
1.2.1.3 | Web Front End | Task | 4 | Soumy Oza
1.2.1.4 | Mobile | Task | 4 | Hardik
1.2.2 | US-06: Auto-Fill Contractor Contact Number on Selection | User Story | 4 | Developer
1.2.2.1 | Backend API | Task | 2 | Ronak
1.2.2.2 | Web Front End | Task | 1 | Soumy Oza
1.2.2.3 | Mobile | Task | 1 | Hardik
1.2.3 | US-07: System Validates Minimum Age of 18 Years at Registration | User Story | 4 | Developer
1.2.3.1 | Backend API | Task | 2 | Ronak
1.2.3.2 | Web Front End | Task | 1 | Soumy Oza
1.2.3.3 | Mobile | Task | 1 | Hardik
1.2.4 | US-08: System Enforces Aadhaar Mandatory Format and Masking | User Story | 4 | Developer
1.2.4.1 | Backend API | Task | 2 | Ronak
1.2.4.2 | Web Front End | Task | 1 | Soumy Oza
1.2.4.3 | Mobile | Task | 1 | Hardik
1.2.5 | US-09: System Validates PAN Format When Provided | User Story | 4 | Developer
1.2.5.1 | Backend API | Task | 2 | Ronak
1.2.5.2 | Web Front End | Task | 1 | Soumy Oza
1.2.5.3 | Mobile | Task | 1 | Hardik
1.2.6 | US-10: System Enforces Mandatory Labour Photo Before Save | User Story | 8 | Developer
1.2.6.1 | Backend API | Task | 2 | Ronak
1.2.6.2 | Web Front End | Task | 3 | Soumy Oza
1.2.6.3 | Mobile | Task | 3 | Hardik
1.2.7 | US-11: System Validates Vaccine Date Sequencing | User Story | 8 | Developer
1.2.7.1 | Backend API | Task | 2 | Ronak
1.2.7.2 | Web Front End | Task | 3 | Soumy Oza
1.2.7.3 | Mobile | Task | 3 | Hardik
1.2.8 | US-12: Admin Views Success Summary and Auto-Notifies Safety Officer | User Story | 7 | Developer
1.2.8.1 | Backend API | Task | 3 | Ronak
1.2.8.2 | Web Front End | Task | 2 | Soumy Oza
1.2.8.3 | Mobile | Task | 2 | Hardik
1.3 | Epic 3: Multi-Project Reuse & Duplicate Prevention | Epic | 22
1.3.1 | US-13: System Detects Cross-Project Aadhaar Match and Prompts Reuse | User Story | 6 | Developer
1.3.1.2 | Backend API | Task | 2 | Ronak
1.3.1.3 | Web Front End | Task | 2 | Soumy Oza
1.3.1.4 | Mobile | Task | 2 | Hardik
1.3.2 | US-14: Admin Reuses Existing Record with One Click | User Story | 4 | Developer
1.3.3.1 | Backend API | Task | 0 | Ronak
1.3.2.2 | Web Front End | Task | 2 | Soumy Oza
1.3.2.3 | Mobile | Task | 2 | Hardik
1.3.3 | US-15: Admin Creates a New Record Despite a Cross-Project Match | User Story | 6 | Developer
1.3.3.1 | Backend API | Task | 2 | Ronak
1.3.3.2 | Web Front End | Task | 2 | Soumy Oza
1.3.3.3 | Mobile | Task | 2 | Hardik
1.3.4 | US-16: System Hard-Blocks Duplicate Aadhaar on the Same Project | User Story | 6 | Developer
1.3.4.1 | Backend API | Task | 2 | Ronak
1.3.4.2 | Web Front End | Task | 2 | Soumy Oza
1.3.4.3 | Mobile | Task | 2 | Hardik
1.4 | Epic 4: Labour List, Search & Export | Epic | 26
1.4.1 | US-17: Admin Searches and Filters the Labour List | User Story | 10 | Developer
1.4.1.1 | Database | Task | 4 | Parth Jani
1.4.1.2 | Backend API | Task | 2 | Ronak
1.4.1.3 | Web Front End | Task | 2 | Soumy Oza
1.4.1.4 | Mobile | Task | 2 | Hardik
1.4.2 | US-18: Admin Exports Filtered Labour List to Excel | User Story | 6 | Developer
1.4.2.1 | Backend API | Task | 4 | Ronak
1.4.2.2 | Web Front End | Task | 1 | Soumy Oza
1.4.2.3 | Mobile | Task | 1 | Hardik
1.4.3 | US-19: Admin Issues Gatepass Directly from Labour List | User Story | 10 | Developer
1.4.3.1 | Backend API | Task | 3 | Ronak
1.4.3.2 | Web Front End | Task | 3 | Soumy Oza
1.4.3.3 | Mobile | Task | 4 | Hardik
1.4.4 | US-20: Admin Views Paginated Labour List with Total Count | User Story | 0 | Developer
1.4.4.1 | Backend API | Task | 0 | Ronak
1.4.4.2 | Web Front End | Task | 0 | Soumy Oza
1.4.4.3 | Mobile | Task | 0 | Hardik
1.5 | Epic 5: Gatepass Issuance | Epic | 54
1.5.1 | US-21: Admin Issues Gatepass Gated on Safety Clearance | User Story | 26 | Developer
1.5.1.1 | Database | Task | 6 | Parth Jani
1.5.1.2 | Backend API | Task | 8 | Ronak
1.5.1.3 | Web Front End | Task | 6 | Soumy Oza
1.5.1.4 | Mobile | Task | 6 | Hardik
1.5.2 | US-22: System Validates Gatepass Validity Dates on Issuance | User Story | 4 | Developer
1.5.2.1 | Backend API | Task | 2 | Ronak
1.5.2.2 | Web Front End | Task | 1 | Soumy Oza
1.5.2.3 | Mobile | Task | 1 | Hardik
1.5.3 | US-23: System Generates Unique Gatepass Number on Issuance | User Story | 2 | Developer
1.5.3.1 | Backend API | Task | 2 | Ronak
1.5.3.2 | Web Front End | Task | 0 | Soumy Oza
1.5.3.3 | Mobile | Task | 0 | Hardik
1.5.4 | US-24: Admin Views and Filters Gatepass Management List | User Story | 16 | Developer
1.5.4.1 | Backend API | Task | 6 | Ronak
1.5.4.2 | Web Front End | Task | 5 | Soumy Oza
1.5.4.3 | Mobile | Task | 5 | Hardik
1.5.5 | US-25: Admin Views Cleared Count Summary on Gatepass Screen | User Story | 6 | Developer
1.5.5.1 | Backend API | Task | 2 | Ronak
1.5.5.2 | Web Front End | Task | 2 | Soumy Oza
1.5.5.3 | Mobile | Task | 2 | Hardik
1.6 | Epic 6: Gatepass Renewal & Revocation | Epic | 33
1.6.1 | US-26: Admin Renews an Expired Gatepass | User Story | 16 | Developer
1.6.1.1 | Database | Task | 4 | Parth Jani
1.6.1.2 | Backend API | Task | 4 | Ronak
1.6.1.3 | Web Front End | Task | 4 | Soumy Oza
1.6.1.4 | Mobile | Task | 4 | Hardik
1.6.2 | US-27: System Requires Mandatory Reason for Gatepass Revocation | User Story | 6 | Developer
1.6.2.1 | Backend API | Task | 2 | Ronak
1.6.2.2 | Web Front End | Task | 2 | Soumy Oza
1.6.2.3 | Mobile | Task | 2 | Hardik
1.6.3 | US-28: System Displays Irreversibility Warning Before Confirming Revocation | User Story | 5 | Developer
1.6.3.1 | Backend API | Task | 2 | Ronak
1.6.3.2 | Web Front End | Task | 2 | Soumy Oza
1.6.3.3 | Mobile | Task | 1 | Hardik
1.6.4 | US-29: System Enforces Irreversible Status Change on Revocation | User Story | 6 | Developer
1.6.4.1 | Backend API | Task | 2 | Ronak
1.6.4.2 | Web Front End | Task | 2 | Soumy Oza
1.6.4.3 | Mobile | Task | 2 | Hardik
1.7 | Epic 7: Bulk Print & Printable Gatepass Slip | Epic | 37
1.7.1 | US-30: Admin Selects Multiple Active Gatepasses for Bulk Print | User Story | 10 | Developer
1.7.1.1 | Database | Task | 2 | Parth Jani
1.7.1.2 | Backend API | Task | 4 | Ronak
1.7.1.3 | Web Front End | Task | 4 | Soumy Oza
1.7.2 | US-31: Admin Confirms Bulk Print with Previous Print Count Visibility | User Story | 6 | Developer
1.7.2.1 | Backend API | Task | 3 | Ronak
1.7.2.2 | Web Front End | Task | 3 | Soumy Oza
1.7.3 | US-32: System Increments and Logs Print Count on Every Print Action | User Story | 6 | Developer
1.7.3.1 | Backend API | Task | 3 | Ronak
1.7.3.2 | Web Front End | Task | 3 | Soumy Oza
1.7.4 | US-33: Admin Generates A5 Printable Gatepass Slip | User Story | 9 | Developer
1.7.4.1 | Backend API | Task | 4 | Ronak
1.7.4.2 | Web Front End | Task | 5 | Soumy Oza
1.7.5 | US-34: Admin Generates ID-Card (CR80) Printable Gatepass | User Story | 6 | Developer
1.7.5.1 | Backend API | Task | 3 | Ronak
1.7.5.2 | Web Front End | Task | 3 | Soumy Oza
1.7.6 | US-35: System Renders Revoked Watermark and Warns Before Printing a Revoked Pass | User Story | 0 | Developer
1.7.6.1 | Backend API | Task | 0 | Ronak
1.7.6.2 | Web Front End | Task | 0 | Soumy Oza
1.8 | Epic 8: Colony Assignment | Epic | 64
1.8.1 | US-36: Admin Views Block-Wise Room Occupancy | User Story | 18 | Developer
1.8.1.1 | Database | Task | 4 | Parth Jani
1.8.1.2 | Backend API | Task | 4 | Ronak
1.8.1.3 | Web Front End | Task | 5 | Soumy Oza
1.8.1.4 | Mobile | Task | 5 | Hardik
1.8.2 | US-37: Admin Creates a New Colony Assignment with Capacity Visibility | User Story | 10 | Developer
1.8.2.1 | Backend API | Task | 4 | Ronak
1.8.2.2 | Web Front End | Task | 3 | Soumy Oza
1.8.2.3 | Mobile | Task | 3 | Hardik
1.8.3 | US-38: System Blocks Assignment Beyond Room Capacity | User Story | 14 | Developer
1.8.3.1 | Backend API | Task | 4 | Ronak
1.8.3.2 | Web Front End | Task | 5 | Soumy Oza
1.8.3.3 | Mobile | Task | 5 | Hardik
1.8.4 | US-39: Admin Reassigns a Worker to a Different Room | User Story | 11 | Developer
1.8.4.1 | Backend API | Task | 4 | Ronak
1.8.4.2 | Web Front End | Task | 4 | Soumy Oza
1.8.4.3 | Mobile | Task | 3 | Hardik
1.8.5 | US-40: Admin Vacates a Colony Assignment | User Story | 11 | Developer
1.8.5.1 | Backend API | Task | 4 | Ronak
1.8.5.2 | Web Front End | Task | 4 | Soumy Oza
1.8.5.3 | Mobile | Task | 3 | Hardik
1.9 | Epic 9: Notifications & Alerts | Epic | 24
1.9.1 | US-41: System Sends In-App Toast on Successful Labour Registration | User Story | 0 | Developer
1.9.1.1 | Database | Task | 0 | Parth Jani
1.9.1.2 | Backend API | Task | 0 | Ronak
1.9.1.3 | Web Front End | Task | 0 | Soumy Oza
1.9.1.4 | Mobile | Task | 0 | Hardik
1.9.2 | US-42: System Notifies Admin Team on Safety Clearance Confirmation | User Story | 10 | Developer
1.9.2.1 | Backend API | Task | 4 | Ronak
1.9.2.2 | Web Front End | Task | 3 | Soumy Oza
1.9.2.3 | Mobile | Task | 3 | Hardik
1.9.3 | US-43: System Sends Expiry Alerts via Push | User Story | 10 | Developer
1.9.3.1 | Backend API | Task | 4 | Ronak
1.9.3.2 | Web Front End | Task | 3 | Soumy Oza
1.9.3.3 | Mobile | Task | 3 | Hardik
1.9.4 | US-44: System Displays Inline Warning on Room Capacity Conflict | User Story | 4 | Developer
1.9.4.1 | Backend API | Task | 2 | Ronak
1.9.4.2 | Web Front End | Task | 1 | Soumy Oza
1.9.4.3 | Mobile | Task | 1 | Hardik
1.10 | Epic 10: Mobile Experience | Epic | 6
1.10.2 | US-46: Admin Captures Photo and Documents via Device Camera | User Story | 6 | Developer
1.10.2.3 | Mobile | Task | 6 | Hardik
1.11 | Epic 11: Integrations, Reporting & NFRs | Epic | 33
1.11.1 | US-49: System Consumes Safety Clearance Flag Read-Only from Safety Module | User Story | 14 | Developer
1.11.1.1 | Database | Task | 2 | Parth Jani
1.11.1.2 | Backend API | Task | 4 | Parth Jani
1.11.1.3 | Web Front End | Task | 4 | Parth Jani
1.11.1.4 | Mobile | Task | 4 | Hardik
1.11.2 | US-50: System Consumes ERP Master Data as Read-Only Dropdowns | User Story | 12 | Developer
1.11.2.1 | Backend API | Task | 4 | Parth Jani
1.11.2.2 | Web Front End | Task | 4 | Parth Jani
1.11.2.3 | Mobile | Task | 4 | Hardik
1.11.3 | US-51: System Maintains a Complete Audit Trail for All Transactions | User Story | 0 | Developer
1.11.3.1 | Backend API | Task | 0 | Parth Jani
1.11.3.2 | Web Front End | Task | 0 | Parth Jani
1.11.4 | US-52: Admin Generates Statutory Compliance Export | User Story | 7 | Developer
1.11.4.1 | Backend API | Task | 4 | Parth Jani
1.11.4.2 | Web Front End | Task | 3 | Parth Jani

## Epic Timeline
HIMAPP 2.0 ADMIN MODULE — EPIC-LEVEL TIMELINE
WBS ID | Epic | Estimated Hours | Days
1.1 | Epic 1: Dashboard & KPIs | 48 | 8 | Row Labels | Estimated Hours | Days
1.2 | Epic 2: Labour Registration | 53 | 8.8333 | Hardik | 110 | 18.3333
1.3 | Epic 3: Multi-Project Reuse & Duplicate Prevention | 22 | 3.6667 | Ronak | 111 | 18.5
1.4 | Epic 4: Labour List, Search & Export | 26 | 4.3333 | Soumy Oza | 100 | 16.6667
1.5 | Epic 5: Gatepass Issuance | 54 | 9 | Parth Jani | 79 | 13.1667
1.6 | Epic 6: Gatepass Renewal & Revocation | 33 | 5.5 | Grand Total | 400 | 18.5
1.7 | Epic 7: Bulk Print & Printable Gatepass Slip | 37 | 6.1667
1.8 | Epic 8: Colony Assignment | 64 | 10.6667
1.9 | Epic 9: Notifications & Alerts | 24 | 4
1.10 | Epic 10: Mobile Experience | 6 | 1
1.11 | Epic 11: Integrations, Reporting & NFRs | 33 | 5.5
| PROJECT TOTAL | 400 | 66.6667