## Settings
All Module Estimations — Schedule Settings
Project Start Date | 2026-07-16
Working Hours / Day | 7
Buffer Between Modules (working days) | 7
Module Order
# | Module | Module Start Date | Day Zero (helper)
1 | Execution | 2026-07-16 | 2026-07-15
2 | Admin | 2026-08-26 | 2026-08-25
3 | Safety | 2026-09-28 | 2026-09-25
4 | P&M | 2026-11-10 | 2026-11-09
5 | Store | 2027-01-14 | 2027-01-13
HOW THIS FILE WORKS:
1. Working hours per day = 7 (editable above). The schedule is calculated in WORKING HOURS, so several small tasks
can be completed on the same day. "Start Hr"/"End Hr" = cumulative working hours of that developer within the module.
2. All developers work IN PARALLEL: each developer completes his own tasks one after another (top to bottom),
so a module finishes when its busiest developer finishes.
3. Modules run sequentially: Execution -> Admin -> Safety -> P&M -> Store, with a 3-working-day buffer between modules.
4. Saturdays, Sundays and all dates on the "Holidays" sheet are excluded automatically.
5. Everything is live formulas — change Start Date, Hours/Day, Buffer, any Estimated Hours, or any Start Hr,
and every downstream task, Epic, Module and Developer date updates automatically (cascades across modules too).
6. 0-hour tasks are milestones (consume no time). Epic / User Story / Project rows roll up from their children.
Formulas:
Day Zero (helper) = WORKDAY([Module Start Date],-1,Holidays)

## Holidays
Holiday Date | Holiday Name
2026-08-15 | Independence Day (Saturday) | Add / edit company holidays in column A (rows 2-60); they are excluded from the schedule automatically.
2026-10-02 | Gandhi Jayanti
2026-12-25 | Christmas Day
2027-01-26 | Republic Day

## All Modules WBS
Module | WBS ID | Task Name | Type | Estimated Hours | Developer | Start Hr | End Hr | Start Date | End Date
Execution | 1 | HIMAPP 2.0 — SITE EXECUTION MODULE — Implementation | Project | 564 |  |  |  | 2026-07-16 | 2026-08-14
Execution | 1.1 | Epic 1: Manpower & Labour Deployment (AM Entry) | Epic | 40 |  |  |  | 2026-07-16 | 2026-07-20
Execution | 1.1.1 | US-01: Field Engineer Logs Morning Manpower Deployment | User Story | 20 |  |  |  | 2026-07-16 | 2026-07-17
Execution | 1.1.1.1 | Database | Task | 3 | Ronak | 0 | 3 | 2026-07-16 | 2026-07-16
Execution | 1.1.1.2 | Backend API | Task | 6 | Ronak | 3 | 9 | 2026-07-16 | 2026-07-17
Execution | 1.1.1.3 | Web Front End | Task | 5 | Soumy | 0 | 5 | 2026-07-16 | 2026-07-16
Execution | 1.1.1.4 | Mobile | Task | 6 | Hardik | 0 | 6 | 2026-07-16 | 2026-07-16
Execution | 1.1.2 | US-02: System Carries Saved Manpower Forward into Daily DPR | User Story | 10 |  |  |  | 2026-07-16 | 2026-07-17
Execution | 1.1.2.1 | Database | Task | 2 | Ronak | 9 | 11 | 2026-07-17 | 2026-07-17
Execution | 1.1.2.2 | Backend API | Task | 3 | Ronak | 11 | 14 | 2026-07-17 | 2026-07-17
Execution | 1.1.2.3 | Web Front End | Task | 3 | Soumy | 5 | 8 | 2026-07-16 | 2026-07-17
Execution | 1.1.2.4 | Mobile | Task | 2 | Hardik | 6 | 8 | 2026-07-16 | 2026-07-17
Execution | 1.1.3 | US-03: Add, Tag, and Remove Contractors with Work Category | User Story | 10 |  |  |  | 2026-07-17 | 2026-07-20
Execution | 1.1.3.1 | Database | Task | 2 | Ronak | 14 | 16 | 2026-07-20 | 2026-07-20
Execution | 1.1.3.2 | Backend API | Task | 3 | Ronak | 16 | 19 | 2026-07-20 | 2026-07-20
Execution | 1.1.3.3 | Web Front End | Task | 3 | Soumy | 8 | 11 | 2026-07-17 | 2026-07-17
Execution | 1.1.3.4 | Mobile | Task | 2 | Hardik | 8 | 10 | 2026-07-17 | 2026-07-17
Execution | 1.2 | Epic 2: Site DPR & Project DPR Consolidation | Epic | 124 |  |  |  | 2026-07-16 | 2026-07-27
Execution | 1.2.1 | US-04: Engineer Records Per-Section Activity Quantities Against Plan | User Story | 14 |  |  |  | 2026-07-16 | 2026-07-20
Execution | 1.2.1.1 | Database | Task | 2 | Parth Jani | 0 | 2 | 2026-07-16 | 2026-07-16
Execution | 1.2.1.2 | Backend API | Task | 3 | Parth Jani | 2 | 5 | 2026-07-16 | 2026-07-16
Execution | 1.2.1.3 | Web Front End | Task | 4 | Soumy | 11 | 15 | 2026-07-17 | 2026-07-20
Execution | 1.2.1.4 | Mobile | Task | 5 | Hardik | 10 | 15 | 2026-07-17 | 2026-07-20
Execution | 1.2.2 | US-05: QS Enters Quantities via Cross-Section Quantity Matrix | User Story | 13 |  |  |  | 2026-07-16 | 2026-07-20
Execution | 1.2.2.1 | Database | Task | 2 | Parth Jani | 5 | 7 | 2026-07-16 | 2026-07-16
Execution | 1.2.2.2 | Backend API | Task | 4 | Parth Jani | 7 | 11 | 2026-07-17 | 2026-07-17
Execution | 1.2.2.3 | Web Front End | Task | 4 | Soumy | 15 | 19 | 2026-07-20 | 2026-07-20
Execution | 1.2.2.4 | Mobile | Task | 3 | Hardik | 15 | 18 | 2026-07-20 | 2026-07-20
Execution | 1.2.3 | US-06: Bulk Quantity Entry via Excel Template Upload | User Story | 12 |  |  |  | 2026-07-17 | 2026-07-21
Execution | 1.2.3.1 | Database | Task | 1 | Parth Jani | 11 | 12 | 2026-07-17 | 2026-07-17
Execution | 1.2.3.2 | Backend API | Task | 6 | Parth Jani | 12 | 18 | 2026-07-17 | 2026-07-20
Execution | 1.2.3.3 | Web Front End | Task | 5 | Soumy | 19 | 24 | 2026-07-20 | 2026-07-21
Execution | 1.2.4 | US-07: Capture Hindrances with Auto-Classification | User Story | 12 |  |  |  | 2026-07-20 | 2026-07-21
Execution | 1.2.4.1 | Database | Task | 1 | Parth Jani | 18 | 19 | 2026-07-20 | 2026-07-20
Execution | 1.2.4.2 | Backend API | Task | 4 | Parth Jani | 19 | 23 | 2026-07-20 | 2026-07-21
Execution | 1.2.4.3 | Web Front End | Task | 4 | Soumy | 24 | 28 | 2026-07-21 | 2026-07-21
Execution | 1.2.4.4 | Mobile | Task | 3 | Hardik | 18 | 21 | 2026-07-20 | 2026-07-20
Execution | 1.2.5 | US-08: Capture GPS Tag and Site Photo for Daily Record | User Story | 12 |  |  |  | 2026-07-21 | 2026-07-22
Execution | 1.2.5.1 | Database | Task | 1 | Parth Jani | 23 | 24 | 2026-07-21 | 2026-07-21
Execution | 1.2.5.2 | Backend API | Task | 3 | Parth Jani | 24 | 27 | 2026-07-21 | 2026-07-21
Execution | 1.2.5.3 | Web Front End | Task | 2 | Soumy | 28 | 30 | 2026-07-22 | 2026-07-22
Execution | 1.2.5.4 | Mobile | Task | 6 | Hardik | 21 | 27 | 2026-07-21 | 2026-07-21
Execution | 1.2.6 | US-09: Capture Tomorrow's Plan Note | User Story | 6 |  |  |  | 2026-07-21 | 2026-07-22
Execution | 1.2.6.1 | Database | Task | 1 | Parth Jani | 27 | 28 | 2026-07-21 | 2026-07-21
Execution | 1.2.6.2 | Backend API | Task | 2 | Parth Jani | 28 | 30 | 2026-07-22 | 2026-07-22
Execution | 1.2.6.3 | Web Front End | Task | 2 | Soumy | 30 | 32 | 2026-07-22 | 2026-07-22
Execution | 1.2.6.4 | Mobile | Task | 1 | Hardik | 27 | 28 | 2026-07-21 | 2026-07-21
Execution | 1.2.7 | US-10: System Calculates DPR Completion % from Required Inputs | User Story | 7 |  |  |  | 2026-07-22 | 2026-07-22
Execution | 1.2.7.2 | Backend API | Task | 2 | Parth Jani | 30 | 32 | 2026-07-22 | 2026-07-22
Execution | 1.2.7.3 | Web Front End | Task | 2 | Soumy | 32 | 34 | 2026-07-22 | 2026-07-22
Execution | 1.2.7.4 | Mobile | Task | 3 | Hardik | 28 | 31 | 2026-07-22 | 2026-07-22
Execution | 1.2.8 | US-11: Engineer Submits DPR for Manager Approval | User Story | 11 |  |  |  | 2026-07-22 | 2026-07-23
Execution | 1.2.8.2 | Backend API | Task | 4 | Parth Jani | 32 | 36 | 2026-07-22 | 2026-07-23
Execution | 1.2.8.3 | Web Front End | Task | 4 | Soumy | 34 | 38 | 2026-07-22 | 2026-07-23
Execution | 1.2.8.4 | Mobile | Task | 3 | Hardik | 31 | 34 | 2026-07-22 | 2026-07-22
Execution | 1.2.9 | US-12: Manager Approves or Reopens Submitted DPR | User Story | 11 |  |  |  | 2026-07-22 | 2026-07-23
Execution | 1.2.9.2 | Backend API | Task | 3 | Parth Jani | 36 | 39 | 2026-07-23 | 2026-07-23
Execution | 1.2.9.3 | Mobile | Task | 4 | Hardik | 34 | 38 | 2026-07-22 | 2026-07-23
Execution | 1.2.9.3 | Web Front End | Task | 4 | Soumy | 38 | 42 | 2026-07-23 | 2026-07-23
Execution | 1.2.10 | US-13: Share DPR via WhatsApp and Export as PDF | User Story | 11 |  |  |  | 2026-07-23 | 2026-07-24
Execution | 1.2.10.1 | Database | Task | 1 | Parth Jani | 39 | 40 | 2026-07-23 | 2026-07-23
Execution | 1.2.10.2 | Backend API | Task | 3 | Parth Jani | 40 | 43 | 2026-07-23 | 2026-07-24
Execution | 1.2.10.3 | Web Front End | Task | 3 | Soumy | 42 | 45 | 2026-07-24 | 2026-07-24
Execution | 1.2.10.4 | Mobile | Task | 4 | Hardik | 38 | 42 | 2026-07-23 | 2026-07-23
Execution | 1.2.11 | US-14: QS Views Consolidated Project DPR Across All Areas | User Story | 15 |  |  |  | 2026-07-24 | 2026-07-27
Execution | 1.2.11.1 | Database | Task | 3 | Parth Jani | 43 | 46 | 2026-07-24 | 2026-07-24
Execution | 1.2.11.2 | Backend API | Task | 4 | Parth Jani | 46 | 50 | 2026-07-24 | 2026-07-27
Execution | 1.2.11.3 | Mobile | Task | 4 | Hardik | 42 | 46 | 2026-07-24 | 2026-07-24
Execution | 1.2.11.3 | Web Front End | Task | 4 | Soumy | 45 | 49 | 2026-07-24 | 2026-07-24
Execution | 1.3 | Epic 3: Daily Labour Slip (DDLS) | Epic | 76 |  |  |  | 2026-07-20 | 2026-07-30
Execution | 1.3.1 | US-15: User Creates a Daily Labour Slip with Auto-Priced Lines | User Story | 20 |  |  |  | 2026-07-20 | 2026-07-27
Execution | 1.3.1.1 | Database | Task | 2 | Ronak | 19 | 21 | 2026-07-20 | 2026-07-20
Execution | 1.3.1.2 | Backend API | Task | 4 | Ronak | 21 | 25 | 2026-07-21 | 2026-07-21
Execution | 1.3.1.3 | Web Front End | Task | 6 | Soumy | 49 | 55 | 2026-07-27 | 2026-07-27
Execution | 1.3.1.4 | Mobile | Task | 8 | Hardik | 46 | 54 | 2026-07-24 | 2026-07-27
Execution | 1.3.2 | US-16: System Derives Work Hours, Mandays and Flags Over-Limit Lines | User Story | 0 |  |  |  | 2026-07-21 | 2026-07-27
Execution | 1.3.2.2 | Backend API | Task | 0 | Ronak | 25 | 25 | 2026-07-21 | 2026-07-21
Execution | 1.3.2.3 | Web Front End | Task | 0 | Soumy | 55 | 55 | 2026-07-27 | 2026-07-27
Execution | 1.3.3 | US-17: Require Lumpsum or Exception Justification on Flagged Lines | User Story | 10 |  |  |  | 2026-07-21 | 2026-07-28
Execution | 1.3.3.2 | Backend API | Task | 3 | Ronak | 25 | 28 | 2026-07-21 | 2026-07-21
Execution | 1.3.3.3 | Web Front End | Task | 3 | Soumy | 55 | 58 | 2026-07-27 | 2026-07-28
Execution | 1.3.3.4 | Mobile | Task | 4 | Hardik | 54 | 58 | 2026-07-27 | 2026-07-28
Execution | 1.3.4 | US-18: Bulk Import Labour Slip Lines via Excel | User Story | 12 |  |  |  | 2026-07-22 | 2026-07-28
Execution | 1.3.4.2 | Backend API | Task | 8 | Ronak | 28 | 36 | 2026-07-22 | 2026-07-23
Execution | 1.3.4.3 | Web Front End | Task | 4 | Soumy | 58 | 62 | 2026-07-28 | 2026-07-28
Execution | 1.3.5 | US-19: Save Draft and Submit Slip for Approval | User Story | 12 |  |  |  | 2026-07-23 | 2026-07-29
Execution | 1.3.5.2 | Backend API | Task | 3 | Ronak | 36 | 39 | 2026-07-23 | 2026-07-23
Execution | 1.3.5.3 | Web Front End | Task | 3 | Soumy | 62 | 65 | 2026-07-28 | 2026-07-29
Execution | 1.3.5.4 | Mobile | Task | 6 | Hardik | 58 | 64 | 2026-07-28 | 2026-07-29
Execution | 1.3.6 | US-20: User Views, Edits, and Resubmits Slips from My Submissions | User Story | 10 |  |  |  | 2026-07-23 | 2026-07-29
Execution | 1.3.6.1 | Database | Task | 2 | Ronak | 39 | 41 | 2026-07-23 | 2026-07-23
Execution | 1.3.6.2 | Backend API | Task | 3 | Ronak | 41 | 44 | 2026-07-23 | 2026-07-24
Execution | 1.3.6.3 | Web Front End | Task | 3 | Soumy | 65 | 68 | 2026-07-29 | 2026-07-29
Execution | 1.3.6.4 | Mobile | Task | 2 | Hardik | 64 | 66 | 2026-07-29 | 2026-07-29
Execution | 1.3.7 | US-21: Maintain a Project-Wide Labour Slip Feed | User Story | 12 |  |  |  | 2026-07-24 | 2026-07-30
Execution | 1.3.7.1 | Mobile | Task | 4 | Ronak | 44 | 48 | 2026-07-24 | 2026-07-24
Execution | 1.3.7.2 | Backend API | Task | 4 | Ronak | 48 | 52 | 2026-07-24 | 2026-07-27
Execution | 1.3.7.3 | Web Front End | Task | 4 | Soumy | 68 | 72 | 2026-07-29 | 2026-07-30
Execution | 1.4 | Epic 4: Approvals & Cost Intelligence | Epic | 71 |  |  |  | 2026-07-27 | 2026-08-04
Execution | 1.4.1 | US-22: Approver Reviews Pending Slip Queue | User Story | 13 |  |  |  | 2026-07-27 | 2026-07-30
Execution | 1.4.1.1 | Database | Task | 2 | Parth Jani | 50 | 52 | 2026-07-27 | 2026-07-27
Execution | 1.4.1.2 | Backend API | Task | 6 | Parth Jani | 52 | 58 | 2026-07-27 | 2026-07-28
Execution | 1.4.1.3 | Web Front End | Task | 5 | Soumy | 72 | 77 | 2026-07-30 | 2026-07-30
Execution | 1.4.2 | US-23: System Surfaces Approval Intelligence: Mandays and Rate Variance vs History | User Story | 18 |  |  |  | 2026-07-28 | 2026-07-31
Execution | 1.4.2.1 | Database | Task | 6 | Parth Jani | 58 | 64 | 2026-07-28 | 2026-07-29
Execution | 1.4.2.2 | Backend API | Task | 6 | Parth Jani | 64 | 70 | 2026-07-29 | 2026-07-29
Execution | 1.4.2.3 | Web Front End | Task | 6 | Soumy | 77 | 83 | 2026-07-31 | 2026-07-31
Execution | 1.4.3 | US-24: System Flags Duplicate Slip Submission | User Story | 8 |  |  |  | 2026-07-29 | 2026-08-03
Execution | 1.4.3.2 | Backend API | Task | 2 | Parth Jani | 70 | 72 | 2026-07-30 | 2026-07-30
Execution | 1.4.3.3 | Mobile | Task | 4 | Hardik | 66 | 70 | 2026-07-29 | 2026-07-29
Execution | 1.4.3.3 | Web Front End | Task | 2 | Soumy | 83 | 85 | 2026-07-31 | 2026-08-03
Execution | 1.4.4 | US-25: System Flags Slips Exceeding the Cost Threshold | User Story | 12 |  |  |  | 2026-07-30 | 2026-08-03
Execution | 1.4.4.1 | Database | Task | 2 | Parth Jani | 72 | 74 | 2026-07-30 | 2026-07-30
Execution | 1.4.4.2 | Backend API | Task | 3 | Parth Jani | 74 | 77 | 2026-07-30 | 2026-07-30
Execution | 1.4.4.3 | Web Front End | Task | 3 | Soumy | 85 | 88 | 2026-08-03 | 2026-08-03
Execution | 1.4.4.4 | Mobile | Task | 4 | Hardik | 70 | 74 | 2026-07-30 | 2026-07-30
Execution | 1.4.5 | US-26: Approver Approves a Slip | User Story | 10 |  |  |  | 2026-07-31 | 2026-08-04
Execution | 1.4.5.1 | Database | Task | 2 | Parth Jani | 77 | 79 | 2026-07-31 | 2026-07-31
Execution | 1.4.5.2 | Backend API | Task | 4 | Parth Jani | 79 | 83 | 2026-07-31 | 2026-07-31
Execution | 1.4.5.3 | Web Front End | Task | 4 | Soumy | 88 | 92 | 2026-08-03 | 2026-08-04
Execution | 1.4.6 | US-27: Approver Rejects a Slip with Mandatory Reason and Remark | User Story | 10 |  |  |  | 2026-07-31 | 2026-08-04
Execution | 1.4.6.1 | Database | Task | 2 | Parth Jani | 83 | 85 | 2026-07-31 | 2026-08-03
Execution | 1.4.6.2 | Backend API | Task | 4 | Parth Jani | 85 | 89 | 2026-08-03 | 2026-08-03
Execution | 1.4.6.3 | Web Front End | Task | 4 | Soumy | 92 | 96 | 2026-08-04 | 2026-08-04
Execution | 1.5 | Epic 5: D365 Reconciliation & Billing | Epic | 25 |  |  |  | 2026-07-27 | 2026-08-05
Execution | 1.5.1 | US-28: Finance Books Approved Slips to D365 | User Story | 0 |  |  |  | 2026-07-27 | 2026-08-04
Execution | 1.5.1.1 | Database | Task | 0 | Ronak | 52 | 52 | 2026-07-27 | 2026-07-27
Execution | 1.5.1.2 | Backend API | Task | 0 | Ronak | 52 | 52 | 2026-07-27 | 2026-07-27
Execution | 1.5.1.3 | Web Front End | Task | 0 | Soumy | 96 | 96 | 2026-08-04 | 2026-08-04
Execution | 1.5.2 | US-29: System Tracks Approved vs Booked vs Pending Reconciliation Totals | User Story | 5 |  |  |  | 2026-07-27 | 2026-08-04
Execution | 1.5.2.1 | Database | Task | 1 | Ronak | 52 | 53 | 2026-07-27 | 2026-07-27
Execution | 1.5.2.2 | Backend API | Task | 2 | Ronak | 53 | 55 | 2026-07-27 | 2026-07-27
Execution | 1.5.2.3 | Web Front End | Task | 2 | Soumy | 96 | 98 | 2026-08-04 | 2026-08-04
Execution | 1.5.3 | US-30: Generate Billing Register of Approved Slips | User Story | 15 |  |  |  | 2026-07-27 | 2026-08-05
Execution | 1.5.3.1 | Database | Task | 4 | Ronak | 55 | 59 | 2026-07-27 | 2026-07-28
Execution | 1.5.3.2 | Backend API | Task | 6 | Ronak | 59 | 65 | 2026-07-28 | 2026-07-29
Execution | 1.5.3.3 | Web Front End | Task | 5 | Soumy | 98 | 103 | 2026-08-05 | 2026-08-05
Execution | 1.5.4 | US-31: Export Reconciliation and Billing Data to PDF | User Story | 5 |  |  |  | 2026-07-29 | 2026-08-05
Execution | 1.5.4.1 | Database | Task | 1 | Ronak | 65 | 66 | 2026-07-29 | 2026-07-29
Execution | 1.5.4.2 | Backend API | Task | 2 | Ronak | 66 | 68 | 2026-07-29 | 2026-07-29
Execution | 1.5.4.3 | Web Front End | Task | 2 | Soumy | 103 | 105 | 2026-08-05 | 2026-08-05
Execution | 1.6 | Epic 6: Planning & Targets | Epic | 40 |  |  |  | 2026-08-03 | 2026-08-10
Execution | 1.6.1 | US-32: QS Defines Planning Period and Daily Targets per Area | User Story | 15 |  |  |  | 2026-08-03 | 2026-08-06
Execution | 1.6.1.1 | Database | Task | 4 | Parth Jani | 89 | 93 | 2026-08-03 | 2026-08-04
Execution | 1.6.1.2 | Backend API | Task | 6 | Parth Jani | 93 | 99 | 2026-08-04 | 2026-08-05
Execution | 1.6.1.3 | Web Front End | Task | 5 | Soumy | 105 | 110 | 2026-08-06 | 2026-08-06
Execution | 1.6.2 | US-33: QS Marks Applicable Activities per Section | User Story | 10 |  |  |  | 2026-08-05 | 2026-08-07
Execution | 1.6.2.1 | Database | Task | 2 | Parth Jani | 99 | 101 | 2026-08-05 | 2026-08-05
Execution | 1.6.2.2 | Backend API | Task | 4 | Parth Jani | 101 | 105 | 2026-08-05 | 2026-08-05
Execution | 1.6.2.3 | Web Front End | Task | 4 | Soumy | 110 | 114 | 2026-08-06 | 2026-08-07
Execution | 1.6.3 | US-34: QS Attaches Drawings or BOQ to the Plan | User Story | 10 |  |  |  | 2026-08-06 | 2026-08-07
Execution | 1.6.3.1 | Database | Task | 2 | Parth Jani | 105 | 107 | 2026-08-06 | 2026-08-06
Execution | 1.6.3.2 | Backend API | Task | 4 | Parth Jani | 107 | 111 | 2026-08-06 | 2026-08-06
Execution | 1.6.3.3 | Web Front End | Task | 4 | Soumy | 114 | 118 | 2026-08-07 | 2026-08-07
Execution | 1.6.4 | US-35: Reset Plan to Defaults or Copy Default Targets | User Story | 5 |  |  |  | 2026-08-06 | 2026-08-10
Execution | 1.6.4.1 | Database | Task | 1 | Parth Jani | 111 | 112 | 2026-08-06 | 2026-08-06
Execution | 1.6.4.2 | Backend API | Task | 2 | Parth Jani | 112 | 114 | 2026-08-07 | 2026-08-07
Execution | 1.6.4.3 | Web Front End | Task | 2 | Soumy | 118 | 120 | 2026-08-07 | 2026-08-10
Execution | 1.7 | Epic 7: Rate Master & Validation Configuration | Epic | 32 |  |  |  | 2026-07-29 | 2026-08-11
Execution | 1.7.1 | US-36: ERP Support Configures Indicative Trade Rates per Project | User Story | 17 |  |  |  | 2026-07-29 | 2026-08-10
Execution | 1.7.1.1 | Database | Task | 6 | Ronak | 68 | 74 | 2026-07-29 | 2026-07-30
Execution | 1.7.1.2 | Backend API | Task | 6 | Ronak | 74 | 80 | 2026-07-30 | 2026-07-31
Execution | 1.7.1.3 | Web Front End | Task | 5 | Soumy | 120 | 125 | 2026-08-10 | 2026-08-10
Execution | 1.7.2 | US-37: ERP Support Configures Max Working Hours/Day Validation Cap | User Story | 10 |  |  |  | 2026-07-31 | 2026-08-11
Execution | 1.7.2.1 | Database | Task | 2 | Ronak | 80 | 82 | 2026-07-31 | 2026-07-31
Execution | 1.7.2.2 | Backend API | Task | 4 | Ronak | 82 | 86 | 2026-07-31 | 2026-08-03
Execution | 1.7.2.3 | Web Front End | Task | 4 | Soumy | 125 | 129 | 2026-08-10 | 2026-08-11
Execution | 1.7.3 | US-38: Reset Project Rates to Company Master Defaults | User Story | 5 |  |  |  | 2026-08-03 | 2026-08-11
Execution | 1.7.3.1 | Database | Task | 1 | Ronak | 86 | 87 | 2026-08-03 | 2026-08-03
Execution | 1.7.3.2 | Backend API | Task | 2 | Ronak | 87 | 89 | 2026-08-03 | 2026-08-03
Execution | 1.7.3.3 | Web Front End | Task | 2 | Soumy | 129 | 131 | 2026-08-11 | 2026-08-11
Execution | 1.8 | Epic 8: Central Control — Portfolio, Provisioning, Masters & Guardrails | Epic | 94 |  |  |  | 2026-07-30 | 2026-08-14
Execution | 1.8.1 | US-39: Central QS Views Portfolio Status Across All Projects | User Story | 19 |  |  |  | 2026-07-30 | 2026-08-10
Execution | 1.8.1.1 | Database | Task | 6 | Ronak | 89 | 95 | 2026-08-03 | 2026-08-04
Execution | 1.8.1.2 | Backend API | Task | 6 | Parth Jani | 114 | 120 | 2026-08-07 | 2026-08-10
Execution | 1.8.1.3 | Web Front End | Task | 7 | Hardik | 74 | 81 | 2026-07-30 | 2026-07-31
Execution | 1.8.2 | US-40: Central QS Launches a New Project and Assigns a QS | User Story | 15 |  |  |  | 2026-07-31 | 2026-08-10
Execution | 1.8.2.1 | Database | Task | 4 | Ronak | 95 | 99 | 2026-08-04 | 2026-08-05
Execution | 1.8.2.2 | Backend API | Task | 6 | Parth Jani | 120 | 126 | 2026-08-10 | 2026-08-10
Execution | 1.8.2.3 | Web Front End | Task | 5 | Hardik | 81 | 86 | 2026-07-31 | 2026-08-03
Execution | 1.8.3 | US-41: QS Completes On-Site Setup Steps for a Provisioned Project | User Story | 15 |  |  |  | 2026-08-03 | 2026-08-11
Execution | 1.8.3.1 | Database | Task | 4 | Ronak | 99 | 103 | 2026-08-05 | 2026-08-05
Execution | 1.8.3.2 | Backend API | Task | 6 | Parth Jani | 126 | 132 | 2026-08-11 | 2026-08-11
Execution | 1.8.3.3 | Web Front End | Task | 5 | Hardik | 86 | 91 | 2026-08-03 | 2026-08-03
Execution | 1.8.4 | US-42: Central QS Configures Company-Wide Rate and Activity Masters | User Story | 15 |  |  |  | 2026-08-04 | 2026-08-12
Execution | 1.8.4.1 | Database | Task | 4 | Ronak | 103 | 107 | 2026-08-05 | 2026-08-06
Execution | 1.8.4.2 | Backend API | Task | 6 | Parth Jani | 132 | 138 | 2026-08-11 | 2026-08-12
Execution | 1.8.4.3 | Web Front End | Task | 5 | Hardik | 91 | 96 | 2026-08-04 | 2026-08-04
Execution | 1.8.5 | US-43: Central QS Configures Per-Project QS Guardrails | User Story | 15 |  |  |  | 2026-08-04 | 2026-08-13
Execution | 1.8.5.1 | Database | Task | 4 | Ronak | 107 | 111 | 2026-08-06 | 2026-08-06
Execution | 1.8.5.2 | Backend API | Task | 6 | Parth Jani | 138 | 144 | 2026-08-12 | 2026-08-13
Execution | 1.8.5.3 | Web Front End | Task | 5 | Hardik | 96 | 101 | 2026-08-04 | 2026-08-05
Execution | 1.8.6 | US-44: View Company-Wide Billing Roll-up by Region and Project | User Story | 15 |  |  |  | 2026-08-05 | 2026-08-14
Execution | 1.8.6.1 | Database | Task | 4 | Ronak | 111 | 115 | 2026-08-06 | 2026-08-07
Execution | 1.8.6.2 | Backend API | Task | 6 | Parth Jani | 144 | 150 | 2026-08-13 | 2026-08-14
Execution | 1.8.6.3 | Web Front End | Task | 5 | Hardik | 101 | 106 | 2026-08-05 | 2026-08-06
Execution | 1.8.7 | US-45: Enforce Role-Based Navigation and Access Across Site Execution Roles | User Story | 0 |  |  |  | 2026-08-06 | 2026-08-14
Execution | 1.8.7.1 | Database | Task | 0 | Ronak | 115 | 115 | 2026-08-07 | 2026-08-07
Execution | 1.8.7.2 | Backend API | Task | 0 | Parth Jani | 150 | 150 | 2026-08-14 | 2026-08-14
Execution | 1.8.7.3 | Web Front End | Task | 0 | Hardik | 106 | 106 | 2026-08-06 | 2026-08-06
Execution | 1.9 | Epic 9: Dashboard & Reporting | Epic | 62 |  |  |  | 2026-08-06 | 2026-08-13
Execution | 1.9.1 | US-46: Site Manager Views Site Command Dashboard KPIs | User Story | 20 |  |  |  | 2026-08-06 | 2026-08-12
Execution | 1.9.1.1 | Database | Task | 4 | Ronak | 115 | 119 | 2026-08-07 | 2026-08-07
Execution | 1.9.1.2 | Backend API | Task | 6 | Ronak | 119 | 125 | 2026-08-10 | 2026-08-10
Execution | 1.9.1.3 | Mobile | Task | 5 | Hardik | 106 | 111 | 2026-08-06 | 2026-08-06
Execution | 1.9.1.3 | Web Front End | Task | 5 | Soumy | 131 | 136 | 2026-08-11 | 2026-08-12
Execution | 1.9.2 | US-47: Dashboard Shows 7-Day Labour Cost Trend and Area Progress | User Story | 15 |  |  |  | 2026-08-06 | 2026-08-12
Execution | 1.9.2.1 | Database | Task | 2 | Ronak | 125 | 127 | 2026-08-10 | 2026-08-11
Execution | 1.9.2.2 | Backend API | Task | 4 | Ronak | 127 | 131 | 2026-08-11 | 2026-08-11
Execution | 1.9.2.3 | Mobile | Task | 5 | Hardik | 111 | 116 | 2026-08-06 | 2026-08-07
Execution | 1.9.2.3 | Web Front End | Task | 4 | Soumy | 136 | 140 | 2026-08-12 | 2026-08-12
Execution | 1.9.3 | US-48: Dashboard Highlights Top Contractors by Approved Value | User Story | 7 |  |  |  | 2026-08-07 | 2026-08-13
Execution | 1.9.3.1 | Database | Task | 1 | Ronak | 131 | 132 | 2026-08-11 | 2026-08-11
Execution | 1.9.3.2 | Backend API | Task | 2 | Ronak | 132 | 134 | 2026-08-11 | 2026-08-12
Execution | 1.9.3.3 | Mobile | Task | 2 | Hardik | 116 | 118 | 2026-08-07 | 2026-08-07
Execution | 1.9.3.3 | Web Front End | Task | 2 | Soumy | 140 | 142 | 2026-08-13 | 2026-08-13
Execution | 1.9.4 | US-49: Maintain Offline-Safe Local Save with Synced Status Indicator | User Story | 20 |  |  |  | 2026-08-07 | 2026-08-13
Execution | 1.9.4.1 | Database | Task | 4 | Ronak | 134 | 138 | 2026-08-12 | 2026-08-12
Execution | 1.9.4.2 | Backend API | Task | 6 | Ronak | 138 | 144 | 2026-08-12 | 2026-08-13
Execution | 1.9.4.3 | Mobile | Task | 5 | Hardik | 118 | 123 | 2026-08-07 | 2026-08-10
Execution | 1.9.4.3 | Web Front End | Task | 5 | Soumy | 142 | 147 | 2026-08-13 | 2026-08-13
Admin | 1 | HIMAPP 2.0 — Admin Module Implementation | Project | 400 |  |  |  | 2026-08-26 | 2026-09-16
Admin | 1.1 | Epic 1: Dashboard & KPIs | Epic | 48 |  |  |  | 2026-08-26 | 2026-09-01
Admin | 1.1.1 | US-01: Admin Views Real-Time Project Dashboard | User Story | 12 |  |  |  | 2026-08-26 | 2026-08-27
Admin | 1.1.1.1 | Database | Task | 2 | Parth Jani | 0 | 2 | 2026-08-26 | 2026-08-26
Admin | 1.1.1.2 | Backend API | Task | 3 | Parth Jani | 2 | 5 | 2026-08-26 | 2026-08-26
Admin | 1.1.1.3 | Web Front End | Task | 3 | Parth Jani | 5 | 8 | 2026-08-26 | 2026-08-27
Admin | 1.1.1.4 | Mobile | Task | 4 | Hardik | 0 | 4 | 2026-08-26 | 2026-08-26
Admin | 1.1.2 | US-02: Ready-to-Issue Banner Highlights Cleared Workers | User Story | 12 |  |  |  | 2026-08-26 | 2026-08-28
Admin | 1.1.1.1 | Database | Task | 2 | Parth Jani | 8 | 10 | 2026-08-27 | 2026-08-27
Admin | 1.1.2.1 | Backend API | Task | 3 | Parth Jani | 10 | 13 | 2026-08-27 | 2026-08-27
Admin | 1.1.2.2 | Web Front End | Task | 3 | Parth Jani | 13 | 16 | 2026-08-27 | 2026-08-28
Admin | 1.1.2.3 | Mobile | Task | 4 | Hardik | 4 | 8 | 2026-08-26 | 2026-08-27
Admin | 1.1.3 | US-03: Recently Registered Labour List with Quick Actions | User Story | 12 |  |  |  | 2026-08-27 | 2026-08-31
Admin | 1.1.1.1 | Database | Task | 2 | Parth Jani | 16 | 18 | 2026-08-28 | 2026-08-28
Admin | 1.1.3.1 | Backend API | Task | 3 | Parth Jani | 18 | 21 | 2026-08-28 | 2026-08-28
Admin | 1.1.3.2 | Web Front End | Task | 3 | Parth Jani | 21 | 24 | 2026-08-31 | 2026-08-31
Admin | 1.1.3.3 | Mobile | Task | 4 | Hardik | 8 | 12 | 2026-08-27 | 2026-08-27
Admin | 1.1.4 | US-04: Expiring Gatepasses Widget with Renew Shortcut | User Story | 12 |  |  |  | 2026-08-27 | 2026-09-01
Admin | 1.1.1.1 | Database | Task | 2 | Parth Jani | 24 | 26 | 2026-08-31 | 2026-08-31
Admin | 1.1.4.1 | Backend API | Task | 3 | Parth Jani | 26 | 29 | 2026-08-31 | 2026-09-01
Admin | 1.1.4.2 | Web Front End | Task | 3 | Parth Jani | 29 | 32 | 2026-09-01 | 2026-09-01
Admin | 1.1.4.3 | Mobile | Task | 4 | Hardik | 12 | 16 | 2026-08-27 | 2026-08-28
Admin | 1.2 | Epic 2: Labour Registration | Epic | 53 |  |  |  | 2026-08-26 | 2026-09-01
Admin | 1.2.1 | US-05: Admin Registers New Labour via Four-Section Form | User Story | 14 |  |  |  | 2026-08-26 | 2026-09-01
Admin | 1.2.1.1 | Database | Task | 2 | Parth Jani | 32 | 34 | 2026-09-01 | 2026-09-01
Admin | 1.2.1.2 | Backend API | Task | 4 | Ronak | 0 | 4 | 2026-08-26 | 2026-08-26
Admin | 1.2.1.3 | Web Front End | Task | 4 | Soumy | 0 | 4 | 2026-08-26 | 2026-08-26
Admin | 1.2.1.4 | Mobile | Task | 4 | Hardik | 16 | 20 | 2026-08-28 | 2026-08-28
Admin | 1.2.2 | US-06: Auto-Fill Contractor Contact Number on Selection | User Story | 4 |  |  |  | 2026-08-26 | 2026-08-28
Admin | 1.2.2.1 | Backend API | Task | 2 | Ronak | 4 | 6 | 2026-08-26 | 2026-08-26
Admin | 1.2.2.2 | Web Front End | Task | 1 | Soumy | 4 | 5 | 2026-08-26 | 2026-08-26
Admin | 1.2.2.3 | Mobile | Task | 1 | Hardik | 20 | 21 | 2026-08-28 | 2026-08-28
Admin | 1.2.3 | US-07: System Validates Minimum Age of 18 Years at Registration | User Story | 4 |  |  |  | 2026-08-26 | 2026-08-31
Admin | 1.2.3.1 | Backend API | Task | 2 | Ronak | 6 | 8 | 2026-08-26 | 2026-08-27
Admin | 1.2.3.2 | Web Front End | Task | 1 | Soumy | 5 | 6 | 2026-08-26 | 2026-08-26
Admin | 1.2.3.3 | Mobile | Task | 1 | Hardik | 21 | 22 | 2026-08-31 | 2026-08-31
Admin | 1.2.4 | US-08: System Enforces Aadhaar Mandatory Format and Masking | User Story | 4 |  |  |  | 2026-08-26 | 2026-08-31
Admin | 1.2.4.1 | Backend API | Task | 2 | Ronak | 8 | 10 | 2026-08-27 | 2026-08-27
Admin | 1.2.4.2 | Web Front End | Task | 1 | Soumy | 6 | 7 | 2026-08-26 | 2026-08-26
Admin | 1.2.4.3 | Mobile | Task | 1 | Hardik | 22 | 23 | 2026-08-31 | 2026-08-31
Admin | 1.2.5 | US-09: System Validates PAN Format When Provided | User Story | 4 |  |  |  | 2026-08-27 | 2026-08-31
Admin | 1.2.5.1 | Backend API | Task | 2 | Ronak | 10 | 12 | 2026-08-27 | 2026-08-27
Admin | 1.2.5.2 | Web Front End | Task | 1 | Soumy | 7 | 8 | 2026-08-27 | 2026-08-27
Admin | 1.2.5.3 | Mobile | Task | 1 | Hardik | 23 | 24 | 2026-08-31 | 2026-08-31
Admin | 1.2.6 | US-10: System Enforces Mandatory Labour Photo Before Save | User Story | 8 |  |  |  | 2026-08-27 | 2026-08-31
Admin | 1.2.6.1 | Backend API | Task | 2 | Ronak | 12 | 14 | 2026-08-27 | 2026-08-27
Admin | 1.2.6.2 | Web Front End | Task | 3 | Soumy | 8 | 11 | 2026-08-27 | 2026-08-27
Admin | 1.2.6.3 | Mobile | Task | 3 | Hardik | 24 | 27 | 2026-08-31 | 2026-08-31
Admin | 1.2.7 | US-11: System Validates Vaccine Date Sequencing | User Story | 8 |  |  |  | 2026-08-27 | 2026-09-01
Admin | 1.2.7.1 | Backend API | Task | 2 | Ronak | 14 | 16 | 2026-08-28 | 2026-08-28
Admin | 1.2.7.2 | Web Front End | Task | 3 | Soumy | 11 | 14 | 2026-08-27 | 2026-08-27
Admin | 1.2.7.3 | Mobile | Task | 3 | Hardik | 27 | 30 | 2026-08-31 | 2026-09-01
Admin | 1.2.8 | US-12: Admin Views Success Summary and Auto-Notifies Safety Officer | User Story | 7 |  |  |  | 2026-08-28 | 2026-09-01
Admin | 1.2.8.1 | Backend API | Task | 3 | Ronak | 16 | 19 | 2026-08-28 | 2026-08-28
Admin | 1.2.8.2 | Web Front End | Task | 2 | Soumy | 14 | 16 | 2026-08-28 | 2026-08-28
Admin | 1.2.8.3 | Mobile | Task | 2 | Hardik | 30 | 32 | 2026-09-01 | 2026-09-01
Admin | 1.3 | Epic 3: Multi-Project Reuse & Duplicate Prevention | Epic | 22 |  |  |  | 2026-08-28 | 2026-09-02
Admin | 1.3.1 | US-13: System Detects Cross-Project Aadhaar Match and Prompts Reuse | User Story | 6 |  |  |  | 2026-08-28 | 2026-09-01
Admin | 1.3.1.2 | Backend API | Task | 2 | Ronak | 19 | 21 | 2026-08-28 | 2026-08-28
Admin | 1.3.1.3 | Web Front End | Task | 2 | Soumy | 16 | 18 | 2026-08-28 | 2026-08-28
Admin | 1.3.1.4 | Mobile | Task | 2 | Hardik | 32 | 34 | 2026-09-01 | 2026-09-01
Admin | 1.3.2 | US-14: Admin Reuses Existing Record with One Click | User Story | 4 |  |  |  | 2026-08-28 | 2026-09-02
Admin | 1.3.3.1 | Backend API | Task | 0 | Ronak | 21 | 21 | 2026-08-31 | 2026-08-31
Admin | 1.3.2.2 | Web Front End | Task | 2 | Soumy | 18 | 20 | 2026-08-28 | 2026-08-28
Admin | 1.3.2.3 | Mobile | Task | 2 | Hardik | 34 | 36 | 2026-09-01 | 2026-09-02
Admin | 1.3.3 | US-15: Admin Creates a New Record Despite a Cross-Project Match | User Story | 6 |  |  |  | 2026-08-28 | 2026-09-02
Admin | 1.3.3.1 | Backend API | Task | 2 | Ronak | 21 | 23 | 2026-08-31 | 2026-08-31
Admin | 1.3.3.2 | Web Front End | Task | 2 | Soumy | 20 | 22 | 2026-08-28 | 2026-08-31
Admin | 1.3.3.3 | Mobile | Task | 2 | Hardik | 36 | 38 | 2026-09-02 | 2026-09-02
Admin | 1.3.4 | US-16: System Hard-Blocks Duplicate Aadhaar on the Same Project | User Story | 6 |  |  |  | 2026-08-31 | 2026-09-02
Admin | 1.3.4.1 | Backend API | Task | 2 | Ronak | 23 | 25 | 2026-08-31 | 2026-08-31
Admin | 1.3.4.2 | Web Front End | Task | 2 | Soumy | 22 | 24 | 2026-08-31 | 2026-08-31
Admin | 1.3.4.3 | Mobile | Task | 2 | Hardik | 38 | 40 | 2026-09-02 | 2026-09-02
Admin | 1.4 | Epic 4: Labour List, Search & Export | Epic | 26 |  |  |  | 2026-08-31 | 2026-09-03
Admin | 1.4.1 | US-17: Admin Searches and Filters the Labour List | User Story | 10 |  |  |  | 2026-08-31 | 2026-09-02
Admin | 1.4.1.1 | Database | Task | 4 | Parth Jani | 34 | 38 | 2026-09-01 | 2026-09-02
Admin | 1.4.1.2 | Backend API | Task | 2 | Ronak | 25 | 27 | 2026-08-31 | 2026-08-31
Admin | 1.4.1.3 | Web Front End | Task | 2 | Soumy | 24 | 26 | 2026-08-31 | 2026-08-31
Admin | 1.4.1.4 | Mobile | Task | 2 | Hardik | 40 | 42 | 2026-09-02 | 2026-09-02
Admin | 1.4.2 | US-18: Admin Exports Filtered Labour List to Excel | User Story | 6 |  |  |  | 2026-08-31 | 2026-09-03
Admin | 1.4.2.1 | Backend API | Task | 4 | Ronak | 27 | 31 | 2026-08-31 | 2026-09-01
Admin | 1.4.2.2 | Web Front End | Task | 1 | Soumy | 26 | 27 | 2026-08-31 | 2026-08-31
Admin | 1.4.2.3 | Mobile | Task | 1 | Hardik | 42 | 43 | 2026-09-03 | 2026-09-03
Admin | 1.4.3 | US-19: Admin Issues Gatepass Directly from Labour List | User Story | 10 |  |  |  | 2026-08-31 | 2026-09-03
Admin | 1.4.3.1 | Backend API | Task | 3 | Ronak | 31 | 34 | 2026-09-01 | 2026-09-01
Admin | 1.4.3.2 | Web Front End | Task | 3 | Soumy | 27 | 30 | 2026-08-31 | 2026-09-01
Admin | 1.4.3.3 | Mobile | Task | 4 | Hardik | 43 | 47 | 2026-09-03 | 2026-09-03
Admin | 1.4.4 | US-20: Admin Views Paginated Labour List with Total Count | User Story | 0 |  |  |  | 2026-09-01 | 2026-09-03
Admin | 1.4.4.1 | Backend API | Task | 0 | Ronak | 34 | 34 | 2026-09-01 | 2026-09-01
Admin | 1.4.4.2 | Web Front End | Task | 0 | Soumy | 30 | 30 | 2026-09-01 | 2026-09-01
Admin | 1.4.4.3 | Mobile | Task | 0 | Hardik | 47 | 47 | 2026-09-03 | 2026-09-03
Admin | 1.5 | Epic 5: Gatepass Issuance | Epic | 54 |  |  |  | 2026-09-01 | 2026-09-07
Admin | 1.5.1 | US-21: Admin Issues Gatepass Gated on Safety Clearance | User Story | 26 |  |  |  | 2026-09-01 | 2026-09-04
Admin | 1.5.1.1 | Database | Task | 6 | Parth Jani | 38 | 44 | 2026-09-02 | 2026-09-03
Admin | 1.5.1.2 | Backend API | Task | 8 | Ronak | 34 | 42 | 2026-09-01 | 2026-09-02
Admin | 1.5.1.3 | Web Front End | Task | 6 | Soumy | 30 | 36 | 2026-09-01 | 2026-09-02
Admin | 1.5.1.4 | Mobile | Task | 6 | Hardik | 47 | 53 | 2026-09-03 | 2026-09-04
Admin | 1.5.2 | US-22: System Validates Gatepass Validity Dates on Issuance | User Story | 4 |  |  |  | 2026-09-02 | 2026-09-04
Admin | 1.5.2.1 | Backend API | Task | 2 | Ronak | 42 | 44 | 2026-09-03 | 2026-09-03
Admin | 1.5.2.2 | Web Front End | Task | 1 | Soumy | 36 | 37 | 2026-09-02 | 2026-09-02
Admin | 1.5.2.3 | Mobile | Task | 1 | Hardik | 53 | 54 | 2026-09-04 | 2026-09-04
Admin | 1.5.3 | US-23: System Generates Unique Gatepass Number on Issuance | User Story | 2 |  |  |  | 2026-09-02 | 2026-09-04
Admin | 1.5.3.1 | Backend API | Task | 2 | Ronak | 44 | 46 | 2026-09-03 | 2026-09-03
Admin | 1.5.3.2 | Web Front End | Task | 0 | Soumy | 37 | 37 | 2026-09-02 | 2026-09-02
Admin | 1.5.3.3 | Mobile | Task | 0 | Hardik | 54 | 54 | 2026-09-04 | 2026-09-04
Admin | 1.5.4 | US-24: Admin Views and Filters Gatepass Management List | User Story | 16 |  |  |  | 2026-09-02 | 2026-09-07
Admin | 1.5.4.1 | Backend API | Task | 6 | Ronak | 46 | 52 | 2026-09-03 | 2026-09-04
Admin | 1.5.4.2 | Web Front End | Task | 5 | Soumy | 37 | 42 | 2026-09-02 | 2026-09-02
Admin | 1.5.4.3 | Mobile | Task | 5 | Hardik | 54 | 59 | 2026-09-04 | 2026-09-07
Admin | 1.5.5 | US-25: Admin Views Cleared Count Summary on Gatepass Screen | User Story | 6 |  |  |  | 2026-09-03 | 2026-09-07
Admin | 1.5.5.1 | Backend API | Task | 2 | Ronak | 52 | 54 | 2026-09-04 | 2026-09-04
Admin | 1.5.5.2 | Web Front End | Task | 2 | Soumy | 42 | 44 | 2026-09-03 | 2026-09-03
Admin | 1.5.5.3 | Mobile | Task | 2 | Hardik | 59 | 61 | 2026-09-07 | 2026-09-07
Admin | 1.6 | Epic 6: Gatepass Renewal & Revocation | Epic | 33 |  |  |  | 2026-09-03 | 2026-09-08
Admin | 1.6.1 | US-26: Admin Renews an Expired Gatepass | User Story | 16 |  |  |  | 2026-09-03 | 2026-09-08
Admin | 1.6.1.1 | Database | Task | 4 | Parth Jani | 44 | 48 | 2026-09-03 | 2026-09-03
Admin | 1.6.1.2 | Backend API | Task | 4 | Ronak | 54 | 58 | 2026-09-04 | 2026-09-07
Admin | 1.6.1.3 | Web Front End | Task | 4 | Soumy | 44 | 48 | 2026-09-03 | 2026-09-03
Admin | 1.6.1.4 | Mobile | Task | 4 | Hardik | 61 | 65 | 2026-09-07 | 2026-09-08
Admin | 1.6.2 | US-27: System Requires Mandatory Reason for Gatepass Revocation | User Story | 6 |  |  |  | 2026-09-03 | 2026-09-08
Admin | 1.6.2.1 | Backend API | Task | 2 | Ronak | 58 | 60 | 2026-09-07 | 2026-09-07
Admin | 1.6.2.2 | Web Front End | Task | 2 | Soumy | 48 | 50 | 2026-09-03 | 2026-09-04
Admin | 1.6.2.3 | Mobile | Task | 2 | Hardik | 65 | 67 | 2026-09-08 | 2026-09-08
Admin | 1.6.3 | US-28: System Displays Irreversibility Warning Before Confirming Revocation | User Story | 5 |  |  |  | 2026-09-04 | 2026-09-08
Admin | 1.6.3.1 | Backend API | Task | 2 | Ronak | 60 | 62 | 2026-09-07 | 2026-09-07
Admin | 1.6.3.2 | Web Front End | Task | 2 | Soumy | 50 | 52 | 2026-09-04 | 2026-09-04
Admin | 1.6.3.3 | Mobile | Task | 1 | Hardik | 67 | 68 | 2026-09-08 | 2026-09-08
Admin | 1.6.4 | US-29: System Enforces Irreversible Status Change on Revocation | User Story | 6 |  |  |  | 2026-09-04 | 2026-09-08
Admin | 1.6.4.1 | Backend API | Task | 2 | Ronak | 62 | 64 | 2026-09-07 | 2026-09-08
Admin | 1.6.4.2 | Web Front End | Task | 2 | Soumy | 52 | 54 | 2026-09-04 | 2026-09-04
Admin | 1.6.4.3 | Mobile | Task | 2 | Hardik | 68 | 70 | 2026-09-08 | 2026-09-08
Admin | 1.7 | Epic 7: Bulk Print & Printable Gatepass Slip | Epic | 37 |  |  |  | 2026-09-03 | 2026-09-10
Admin | 1.7.1 | US-30: Admin Selects Multiple Active Gatepasses for Bulk Print | User Story | 10 |  |  |  | 2026-09-03 | 2026-09-08
Admin | 1.7.1.1 | Database | Task | 2 | Parth Jani | 48 | 50 | 2026-09-03 | 2026-09-04
Admin | 1.7.1.2 | Backend API | Task | 4 | Ronak | 64 | 68 | 2026-09-08 | 2026-09-08
Admin | 1.7.1.3 | Web Front End | Task | 4 | Soumy | 54 | 58 | 2026-09-04 | 2026-09-07
Admin | 1.7.2 | US-31: Admin Confirms Bulk Print with Previous Print Count Visibility | User Story | 6 |  |  |  | 2026-09-07 | 2026-09-09
Admin | 1.7.2.1 | Backend API | Task | 3 | Ronak | 68 | 71 | 2026-09-08 | 2026-09-09
Admin | 1.7.2.2 | Web Front End | Task | 3 | Soumy | 58 | 61 | 2026-09-07 | 2026-09-07
Admin | 1.7.3 | US-32: System Increments and Logs Print Count on Every Print Action | User Story | 6 |  |  |  | 2026-09-07 | 2026-09-09
Admin | 1.7.3.1 | Backend API | Task | 3 | Ronak | 71 | 74 | 2026-09-09 | 2026-09-09
Admin | 1.7.3.2 | Web Front End | Task | 3 | Soumy | 61 | 64 | 2026-09-07 | 2026-09-08
Admin | 1.7.4 | US-33: Admin Generates A5 Printable Gatepass Slip | User Story | 9 |  |  |  | 2026-09-08 | 2026-09-10
Admin | 1.7.4.1 | Backend API | Task | 4 | Ronak | 74 | 78 | 2026-09-09 | 2026-09-10
Admin | 1.7.4.2 | Web Front End | Task | 5 | Soumy | 64 | 69 | 2026-09-08 | 2026-09-08
Admin | 1.7.5 | US-34: Admin Generates ID-Card (CR80) Printable Gatepass | User Story | 6 |  |  |  | 2026-09-08 | 2026-09-10
Admin | 1.7.5.1 | Backend API | Task | 3 | Ronak | 78 | 81 | 2026-09-10 | 2026-09-10
Admin | 1.7.5.2 | Web Front End | Task | 3 | Soumy | 69 | 72 | 2026-09-08 | 2026-09-09
Admin | 1.7.6 | US-35: System Renders Revoked Watermark and Warns Before Printing a Revoked Pass | User Story | 0 |  |  |  | 2026-09-09 | 2026-09-10
Admin | 1.7.6.1 | Backend API | Task | 0 | Ronak | 81 | 81 | 2026-09-10 | 2026-09-10
Admin | 1.7.6.2 | Web Front End | Task | 0 | Soumy | 72 | 72 | 2026-09-09 | 2026-09-09
Admin | 1.8 | Epic 8: Colony Assignment | Epic | 64 |  |  |  | 2026-09-04 | 2026-09-15
Admin | 1.8.1 | US-36: Admin Views Block-Wise Room Occupancy | User Story | 18 |  |  |  | 2026-09-04 | 2026-09-11
Admin | 1.8.1.1 | Database | Task | 4 | Parth Jani | 50 | 54 | 2026-09-04 | 2026-09-04
Admin | 1.8.1.2 | Backend API | Task | 4 | Ronak | 81 | 85 | 2026-09-10 | 2026-09-11
Admin | 1.8.1.3 | Web Front End | Task | 5 | Soumy | 72 | 77 | 2026-09-09 | 2026-09-09
Admin | 1.8.1.4 | Mobile | Task | 5 | Hardik | 70 | 75 | 2026-09-09 | 2026-09-09
Admin | 1.8.2 | US-37: Admin Creates a New Colony Assignment with Capacity Visibility | User Story | 10 |  |  |  | 2026-09-09 | 2026-09-11
Admin | 1.8.2.1 | Backend API | Task | 4 | Ronak | 85 | 89 | 2026-09-11 | 2026-09-11
Admin | 1.8.2.2 | Web Front End | Task | 3 | Soumy | 77 | 80 | 2026-09-10 | 2026-09-10
Admin | 1.8.2.3 | Mobile | Task | 3 | Hardik | 75 | 78 | 2026-09-09 | 2026-09-10
Admin | 1.8.3 | US-38: System Blocks Assignment Beyond Room Capacity | User Story | 14 |  |  |  | 2026-09-10 | 2026-09-14
Admin | 1.8.3.1 | Backend API | Task | 4 | Ronak | 89 | 93 | 2026-09-11 | 2026-09-14
Admin | 1.8.3.2 | Web Front End | Task | 5 | Soumy | 80 | 85 | 2026-09-10 | 2026-09-11
Admin | 1.8.3.3 | Mobile | Task | 5 | Hardik | 78 | 83 | 2026-09-10 | 2026-09-10
Admin | 1.8.4 | US-39: Admin Reassigns a Worker to a Different Room | User Story | 11 |  |  |  | 2026-09-10 | 2026-09-14
Admin | 1.8.4.1 | Backend API | Task | 4 | Ronak | 93 | 97 | 2026-09-14 | 2026-09-14
Admin | 1.8.4.2 | Web Front End | Task | 4 | Soumy | 85 | 89 | 2026-09-11 | 2026-09-11
Admin | 1.8.4.3 | Mobile | Task | 3 | Hardik | 83 | 86 | 2026-09-10 | 2026-09-11
Admin | 1.8.5 | US-40: Admin Vacates a Colony Assignment | User Story | 11 |  |  |  | 2026-09-11 | 2026-09-15
Admin | 1.8.5.1 | Backend API | Task | 4 | Ronak | 97 | 101 | 2026-09-14 | 2026-09-15
Admin | 1.8.5.2 | Web Front End | Task | 4 | Soumy | 89 | 93 | 2026-09-11 | 2026-09-14
Admin | 1.8.5.3 | Mobile | Task | 3 | Hardik | 86 | 89 | 2026-09-11 | 2026-09-11
Admin | 1.9 | Epic 9: Notifications & Alerts | Epic | 24 |  |  |  | 2026-09-04 | 2026-09-16
Admin | 1.9.1 | US-41: System Sends In-App Toast on Successful Labour Registration | User Story | 0 |  |  |  | 2026-09-04 | 2026-09-15
Admin | 1.9.1.1 | Database | Task | 0 | Parth Jani | 54 | 54 | 2026-09-04 | 2026-09-04
Admin | 1.9.1.2 | Backend API | Task | 0 | Ronak | 101 | 101 | 2026-09-15 | 2026-09-15
Admin | 1.9.1.3 | Web Front End | Task | 0 | Soumy | 93 | 93 | 2026-09-14 | 2026-09-14
Admin | 1.9.1.4 | Mobile | Task | 0 | Hardik | 89 | 89 | 2026-09-11 | 2026-09-11
Admin | 1.9.2 | US-42: System Notifies Admin Team on Safety Clearance Confirmation | User Story | 10 |  |  |  | 2026-09-11 | 2026-09-15
Admin | 1.9.2.1 | Backend API | Task | 4 | Ronak | 101 | 105 | 2026-09-15 | 2026-09-15
Admin | 1.9.2.2 | Web Front End | Task | 3 | Soumy | 93 | 96 | 2026-09-14 | 2026-09-14
Admin | 1.9.2.3 | Mobile | Task | 3 | Hardik | 89 | 92 | 2026-09-11 | 2026-09-14
Admin | 1.9.3 | US-43: System Sends Expiry Alerts via Push | User Story | 10 |  |  |  | 2026-09-14 | 2026-09-16
Admin | 1.9.3.1 | Backend API | Task | 4 | Ronak | 105 | 109 | 2026-09-16 | 2026-09-16
Admin | 1.9.3.2 | Web Front End | Task | 3 | Soumy | 96 | 99 | 2026-09-14 | 2026-09-15
Admin | 1.9.3.3 | Mobile | Task | 3 | Hardik | 92 | 95 | 2026-09-14 | 2026-09-14
Admin | 1.9.4 | US-44: System Displays Inline Warning on Room Capacity Conflict | User Story | 4 |  |  |  | 2026-09-14 | 2026-09-16
Admin | 1.9.4.1 | Backend API | Task | 2 | Ronak | 109 | 111 | 2026-09-16 | 2026-09-16
Admin | 1.9.4.2 | Web Front End | Task | 1 | Soumy | 99 | 100 | 2026-09-15 | 2026-09-15
Admin | 1.9.4.3 | Mobile | Task | 1 | Hardik | 95 | 96 | 2026-09-14 | 2026-09-14
Admin | 1.10 | Epic 10: Mobile Experience | Epic | 6 |  |  |  | 2026-09-14 | 2026-09-15
Admin | 1.10.2 | US-46: Admin Captures Photo and Documents via Device Camera | User Story | 6 |  |  |  | 2026-09-14 | 2026-09-15
Admin | 1.10.2.3 | Mobile | Task | 6 | Hardik | 96 | 102 | 2026-09-14 | 2026-09-15
Admin | 1.11 | Epic 11: Integrations, Reporting & NFRs | Epic | 33 |  |  |  | 2026-09-04 | 2026-09-16
Admin | 1.11.1 | US-49: System Consumes Safety Clearance Flag Read-Only from Safety Module | User Story | 14 |  |  |  | 2026-09-04 | 2026-09-16
Admin | 1.11.1.1 | Database | Task | 2 | Parth Jani | 54 | 56 | 2026-09-04 | 2026-09-04
Admin | 1.11.1.2 | Backend API | Task | 4 | Parth Jani | 56 | 60 | 2026-09-07 | 2026-09-07
Admin | 1.11.1.3 | Web Front End | Task | 4 | Parth Jani | 60 | 64 | 2026-09-07 | 2026-09-08
Admin | 1.11.1.4 | Mobile | Task | 4 | Hardik | 102 | 106 | 2026-09-15 | 2026-09-16
Admin | 1.11.2 | US-50: System Consumes ERP Master Data as Read-Only Dropdowns | User Story | 12 |  |  |  | 2026-09-08 | 2026-09-16
Admin | 1.11.2.1 | Backend API | Task | 4 | Parth Jani | 64 | 68 | 2026-09-08 | 2026-09-08
Admin | 1.11.2.2 | Web Front End | Task | 4 | Parth Jani | 68 | 72 | 2026-09-08 | 2026-09-09
Admin | 1.11.2.3 | Mobile | Task | 4 | Hardik | 106 | 110 | 2026-09-16 | 2026-09-16
Admin | 1.11.3 | US-51: System Maintains a Complete Audit Trail for All Transactions | User Story | 0 |  |  |  | 2026-09-09 | 2026-09-09
Admin | 1.11.3.1 | Backend API | Task | 0 | Parth Jani | 72 | 72 | 2026-09-09 | 2026-09-09
Admin | 1.11.3.2 | Web Front End | Task | 0 | Parth Jani | 72 | 72 | 2026-09-09 | 2026-09-09
Admin | 1.11.4 | US-52: Admin Generates Statutory Compliance Export | User Story | 7 |  |  |  | 2026-09-09 | 2026-09-10
Admin | 1.11.4.1 | Backend API | Task | 4 | Parth Jani | 72 | 76 | 2026-09-09 | 2026-09-09
Admin | 1.11.4.2 | Web Front End | Task | 3 | Parth Jani | 76 | 79 | 2026-09-09 | 2026-09-10
Safety | 1 | HIMAPP 2.0 — Safety Module Implementation | Project | 558 |  |  |  | 2026-09-28 | 2026-10-29
Safety | 1.1 | Epic 1: Safety Induction | Epic | 84 |  |  |  | 2026-09-28 | 2026-10-01
Safety | 1.1.1 | US-01: Creates Group Induction Session | User Story | 18 |  |  |  | 2026-09-28 | 2026-09-29
Safety | 1.1.1.1 | Database | Task | 6 | Ronak | 0 | 6 | 2026-09-28 | 2026-09-28
Safety | 1.1.1.2 | Backend API | Task | 4 | Ronak | 6 | 10 | 2026-09-28 | 2026-09-29
Safety | 1.1.1.3 | Web Front End | Task | 4 | Parth Jani | 0 | 4 | 2026-09-28 | 2026-09-28
Safety | 1.1.1.4 | Mobile | Task | 4 | Hardik | 0 | 4 | 2026-09-28 | 2026-09-28
Safety | 1.1.3 | US-03: Labourer Provides Signature or Thumbprint Acknowledgement | User Story | 24 |  |  |  | 2026-09-28 | 2026-09-29
Safety | 1.1.3.2 | Backend API | Task | 4 | Ronak | 10 | 14 | 2026-09-29 | 2026-09-29
Safety | 1.1.3.3 | Web Front End | Task | 10 | Parth Jani | 4 | 14 | 2026-09-28 | 2026-09-29
Safety | 1.1.3.4 | Mobile | Task | 10 | Hardik | 4 | 14 | 2026-09-28 | 2026-09-29
Safety | 1.1.4 | US-04: Manage Induction Topic Library with Free-Text Add | User Story | 11 |  |  |  | 2026-09-30 | 2026-09-30
Safety | 1.1.4.2 | Backend API | Task | 4 | Ronak | 14 | 18 | 2026-09-30 | 2026-09-30
Safety | 1.1.4.3 | Web Front End | Task | 4 | Parth Jani | 14 | 18 | 2026-09-30 | 2026-09-30
Safety | 1.1.4.4 | Mobile | Task | 3 | Hardik | 14 | 17 | 2026-09-30 | 2026-09-30
Safety | 1.1.5 | US-05: System Calculates Per-Person Induction Validity with Override | User Story | 6 |  |  |  | 2026-09-30 | 2026-09-30
Safety | 1.1.5.2 | Backend API | Task | 2 | Ronak | 18 | 20 | 2026-09-30 | 2026-09-30
Safety | 1.1.5.3 | Web Front End | Task | 2 | Parth Jani | 18 | 20 | 2026-09-30 | 2026-09-30
Safety | 1.1.5.4 | Mobile | Task | 2 | Hardik | 17 | 19 | 2026-09-30 | 2026-09-30
Safety | 1.1.7 | US-07: Issue First-Time PPE Inline on Induction Screen | User Story | 18 |  |  |  | 2026-09-30 | 2026-10-01
Safety | 1.1.7.2 | Backend API | Task | 6 | Ronak | 20 | 26 | 2026-09-30 | 2026-10-01
Safety | 1.1.7.3 | Web Front End | Task | 6 | Parth Jani | 20 | 26 | 2026-09-30 | 2026-10-01
Safety | 1.1.7.4 | Mobile | Task | 6 | Hardik | 19 | 25 | 2026-09-30 | 2026-10-01
Safety | 1.1.8 | US-08: Pending Induction List Auto-Populated from Registrations | User Story | 7 |  |  |  | 2026-10-01 | 2026-10-01
Safety | 1.1.8.2 | Backend API | Task | 2 | Ronak | 26 | 28 | 2026-10-01 | 2026-10-01
Safety | 1.1.8.3 | Web Front End | Task | 2 | Parth Jani | 26 | 28 | 2026-10-01 | 2026-10-01
Safety | 1.1.8.4 | Mobile | Task | 3 | Hardik | 25 | 28 | 2026-10-01 | 2026-10-01
Safety | 1.2 | Epic 2: Labour Tests & Medical Records (BOCW) | Epic | 50 |  |  |  | 2026-09-28 | 2026-10-07
Safety | 1.2.1 | US-09: Configure Project-Level Labour Test Requirements | User Story | 16 |  |  |  | 2026-09-28 | 2026-10-06
Safety | 1.2.1.1 | Database | Task | 4 | Parth Jani | 28 | 32 | 2026-10-05 | 2026-10-05
Safety | 1.2.1.2 | Backend API | Task | 4 | Parth Jani | 32 | 36 | 2026-10-05 | 2026-10-06
Safety | 1.2.1.3 | Web Front End | Task | 4 | Soumy | 0 | 4 | 2026-09-28 | 2026-09-28
Safety | 1.2.1.4 | Mobile | Task | 4 | Hardik | 28 | 32 | 2026-10-05 | 2026-10-05
Safety | 1.2.2 | US-10: Hard Block PPE Issuance on Pending or Failed Mandatory Test Status Change to Fail | User Story | 6 |  |  |  | 2026-09-28 | 2026-10-06
Safety | 1.2.2.2 | Backend API | Task | 2 | Parth Jani | 36 | 38 | 2026-10-06 | 2026-10-06
Safety | 1.2.2.3 | Web Front End | Task | 2 | Soumy | 4 | 6 | 2026-09-28 | 2026-09-28
Safety | 1.2.2.4 | Mobile | Task | 2 | Hardik | 32 | 34 | 2026-10-05 | 2026-10-05
Safety | 1.2.3 | US-11: Doctor Creates Medical Test Record (Form XI / BOCW) | User Story | 16 |  |  |  | 2026-09-28 | 2026-10-06
Safety | 1.2.3.2 | Backend API | Task | 4 | Parth Jani | 38 | 42 | 2026-10-06 | 2026-10-06
Safety | 1.2.3.3 | Web Front End | Task | 6 | Soumy | 6 | 12 | 2026-09-28 | 2026-09-29
Safety | 1.2.3.4 | Mobile | Task | 6 | Hardik | 34 | 40 | 2026-10-05 | 2026-10-06
Safety | 1.2.5 | US-13: Track Pending Medical Examinations with Dashboard KPI | User Story | 6 |  |  |  | 2026-09-29 | 2026-10-07
Safety | 1.2.5.2 | Backend API | Task | 2 | Parth Jani | 42 | 44 | 2026-10-07 | 2026-10-07
Safety | 1.2.5.3 | Web Front End | Task | 2 | Soumy | 12 | 14 | 2026-09-29 | 2026-09-29
Safety | 1.2.5.4 | Mobile | Task | 2 | Hardik | 40 | 42 | 2026-10-06 | 2026-10-06
Safety | 1.2.6 | US-14: Maintain Multiple Permanent Medical Records per Labourer | User Story | 6 |  |  |  | 2026-09-30 | 2026-10-07
Safety | 1.2.6.2 | Backend API | Task | 2 | Parth Jani | 44 | 46 | 2026-10-07 | 2026-10-07
Safety | 1.2.6.3 | Web Front End | Task | 2 | Soumy | 14 | 16 | 2026-09-30 | 2026-09-30
Safety | 1.2.6.4 | Mobile | Task | 2 | Hardik | 42 | 44 | 2026-10-07 | 2026-10-07
Safety | 1.3 | Epic 3: PPE Issuance | Epic | 76 |  |  |  | 2026-09-30 | 2026-10-12
Safety | 1.3.1 | US-15: Configure PPE Master with Labour Type Baseline Mapping | User Story | 24 |  |  |  | 2026-09-30 | 2026-10-07
Safety | 1.3.1.1 | Database | Task | 4 | Ronak | 28 | 32 | 2026-10-05 | 2026-10-05
Safety | 1.3.1.2 | Backend API | Task | 8 | Ronak | 32 | 40 | 2026-10-05 | 2026-10-06
Safety | 1.3.1.3 | Web Front End | Task | 7 | Soumy | 16 | 23 | 2026-09-30 | 2026-10-01
Safety | 1.3.1.4 | Mobile | Task | 5 | Hardik | 44 | 49 | 2026-10-07 | 2026-10-07
Safety | 1.3.2 | US-16: Issue PPE via Person-First or Contractor-First Mode | User Story | 14 |  |  |  | 2026-10-01 | 2026-10-08
Safety | 1.3.2.2 | Backend API | Task | 6 | Ronak | 40 | 46 | 2026-10-06 | 2026-10-07
Safety | 1.3.2.3 | Web Front End | Task | 4 | Soumy | 23 | 27 | 2026-10-01 | 2026-10-01
Safety | 1.3.2.4 | Mobile | Task | 4 | Hardik | 49 | 53 | 2026-10-08 | 2026-10-08
Safety | 1.3.3 | US-17: Enforce First Issue / Replacement / Additional Issuance Rule | User Story | 12 |  |  |  | 2026-10-01 | 2026-10-09
Safety | 1.3.3.2 | Backend API | Task | 4 | Ronak | 46 | 50 | 2026-10-07 | 2026-10-08
Safety | 1.3.3.3 | Web Front End | Task | 4 | Soumy | 27 | 31 | 2026-10-01 | 2026-10-05
Safety | 1.3.3.4 | Mobile | Task | 4 | Hardik | 53 | 57 | 2026-10-08 | 2026-10-09
Safety | 1.3.4 | US-18: Auto-Consolidate PPE Issuance into Contractor-Wise MRIS | User Story | 22 |  |  |  | 2026-10-05 | 2026-10-12
Safety | 1.3.4.2 | Backend API | Task | 8 | Ronak | 50 | 58 | 2026-10-08 | 2026-10-09
Safety | 1.3.4.3 | Web Front End | Task | 6 | Soumy | 31 | 37 | 2026-10-05 | 2026-10-06
Safety | 1.3.4.4 | Mobile | Task | 8 | Hardik | 57 | 65 | 2026-10-09 | 2026-10-12
Safety | 1.3.5 | US-19: Update Clearance Flag on First Issue Confirmation | User Story | 4 |  |  |  | 2026-10-06 | 2026-10-12
Safety | 1.3.5.2 | Backend API | Task | 2 | Ronak | 58 | 60 | 2026-10-09 | 2026-10-09
Safety | 1.3.5.3 | Web Front End | Task | 1 | Soumy | 37 | 38 | 2026-10-06 | 2026-10-06
Safety | 1.3.5.4 | Mobile | Task | 1 | Hardik | 65 | 66 | 2026-10-12 | 2026-10-12
Safety | 1.4 | Epic 4: Entry Pass & Overall Clearance | Epic | 63 |  |  |  | 2026-10-06 | 2026-10-14
Safety | 1.4.1 | US-21: System Calculates Overall Clearance from Three Conditions | User Story | 24 |  |  |  | 2026-10-06 | 2026-10-13
Safety | 1.4.1.1 | Database | Task | 6 | Parth Jani | 46 | 52 | 2026-10-07 | 2026-10-08
Safety | 1.4.1.2 | Backend API | Task | 6 | Parth Jani | 52 | 58 | 2026-10-08 | 2026-10-09
Safety | 1.4.1.3 | Web Front End | Task | 6 | Soumy | 38 | 44 | 2026-10-06 | 2026-10-07
Safety | 1.4.1.4 | Mobile | Task | 6 | Hardik | 66 | 72 | 2026-10-12 | 2026-10-13
Safety | 1.4.2 | US-22: Admin Issues Entry Pass Gated on Overall Clearance | User Story | 14 |  |  |  | 2026-10-07 | 2026-10-13
Safety | 1.4.2.2 | Backend API | Task | 4 | Parth Jani | 58 | 62 | 2026-10-09 | 2026-10-09
Safety | 1.4.2.3 | Web Front End | Task | 5 | Soumy | 44 | 49 | 2026-10-07 | 2026-10-07
Safety | 1.4.2.4 | Mobile | Task | 5 | Hardik | 72 | 77 | 2026-10-13 | 2026-10-13
Safety | 1.4.3 | US-23: Admin Overrides Not-Cleared Status with Mandatory Reason | User Story | 11 |  |  |  | 2026-10-08 | 2026-10-14
Safety | 1.4.3.2 | Backend API | Task | 4 | Parth Jani | 62 | 66 | 2026-10-09 | 2026-10-12
Safety | 1.4.3.3 | Web Front End | Task | 4 | Soumy | 49 | 53 | 2026-10-08 | 2026-10-08
Safety | 1.4.3.4 | Mobile | Task | 3 | Hardik | 77 | 80 | 2026-10-14 | 2026-10-14
Safety | 1.4.4 | US-24: Admin Revokes Entry Pass | User Story | 7 |  |  |  | 2026-10-08 | 2026-10-14
Safety | 1.4.4.2 | Backend API | Task | 3 | Parth Jani | 66 | 69 | 2026-10-12 | 2026-10-12
Safety | 1.4.4.3 | Web Front End | Task | 2 | Soumy | 53 | 55 | 2026-10-08 | 2026-10-08
Safety | 1.4.4.4 | Mobile | Task | 2 | Hardik | 80 | 82 | 2026-10-14 | 2026-10-14
Safety | 1.4.5 | US-25: Periodic Entry Pass Reconciliation Report | User Story | 7 |  |  |  | 2026-10-08 | 2026-10-13
Safety | 1.4.5.2 | Backend API | Task | 4 | Parth Jani | 69 | 73 | 2026-10-12 | 2026-10-13
Safety | 1.4.5.3 | Web Front End | Task | 3 | Soumy | 55 | 58 | 2026-10-08 | 2026-10-09
Safety | 1.5 | Epic 5: Work Permit (PTW) | Epic | 129 |  |  |  | 2026-10-09 | 2026-10-21
Safety | 1.5.1 | US-26: Configure Permit Type Master with Classification Rules | User Story | 11 |  |  |  | 2026-10-09 | 2026-10-12
Safety | 1.5.1.1 | Database | Task | 2 | Ronak | 60 | 62 | 2026-10-09 | 2026-10-09
Safety | 1.5.1.2 | Backend API | Task | 4 | Ronak | 62 | 66 | 2026-10-09 | 2026-10-12
Safety | 1.5.1.3 | Web Front End | Task | 5 | Soumy | 58 | 63 | 2026-10-09 | 2026-10-09
Safety | 1.5.2 | US-27: Requestor Initiates PTW Request | User Story | 21 |  |  |  | 2026-10-12 | 2026-10-15
Safety | 1.5.2.2 | Backend API | Task | 6 | Ronak | 66 | 72 | 2026-10-12 | 2026-10-13
Safety | 1.5.2.3 | Web Front End | Task | 7 | Soumy | 63 | 70 | 2026-10-12 | 2026-10-12
Safety | 1.5.2.4 | Mobile | Task | 8 | Hardik | 82 | 90 | 2026-10-14 | 2026-10-15
Safety | 1.5.5 | US-30: Fresh Checklist Every Time with Copy-From-Previous for Static Fields Only | User Story | 16 |  |  |  | 2026-10-13 | 2026-10-16
Safety | 1.5.5.2 | Backend API | Task | 6 | Ronak | 72 | 78 | 2026-10-13 | 2026-10-14
Safety | 1.5.5.3 | Web Front End | Task | 5 | Soumy | 70 | 75 | 2026-10-13 | 2026-10-13
Safety | 1.5.5.4 | Mobile | Task | 5 | Hardik | 90 | 95 | 2026-10-15 | 2026-10-16
Safety | 1.5.6 | US-31: Enforce L1 and L2 Dual Approval Workflow | User Story | 12 |  |  |  | 2026-10-13 | 2026-10-19
Safety | 1.5.6.2 | Backend API | Task | 4 | Ronak | 78 | 82 | 2026-10-14 | 2026-10-14
Safety | 1.5.6.3 | Web Front End | Task | 4 | Soumy | 75 | 79 | 2026-10-13 | 2026-10-14
Safety | 1.5.6.4 | Mobile | Task | 4 | Hardik | 95 | 99 | 2026-10-16 | 2026-10-19
Safety | 1.5.7 | US-32: Compliance Counting and Notification Suppression for Multi-Day Permits | User Story | 15 |  |  |  | 2026-10-14 | 2026-10-19
Safety | 1.5.7.2 | Backend API | Task | 6 | Ronak | 82 | 88 | 2026-10-14 | 2026-10-15
Safety | 1.5.7.3 | Web Front End | Task | 4 | Soumy | 79 | 83 | 2026-10-14 | 2026-10-14
Safety | 1.5.7.4 | Mobile | Task | 5 | Hardik | 99 | 104 | 2026-10-19 | 2026-10-19
Safety | 1.5.8 | US-33: Requestor Extends Active Permit Unilaterally | User Story | 14 |  |  |  | 2026-10-14 | 2026-10-20
Safety | 1.5.8.2 | Backend API | Task | 6 | Ronak | 88 | 94 | 2026-10-15 | 2026-10-16
Safety | 1.5.8.3 | Web Front End | Task | 5 | Soumy | 83 | 88 | 2026-10-14 | 2026-10-15
Safety | 1.5.8.4 | Mobile | Task | 3 | Hardik | 104 | 107 | 2026-10-19 | 2026-10-20
Safety | 1.5.9 | US-34: SSO Places and Releases Hold Without Consuming Validity | User Story | 6 |  |  |  | 2026-10-15 | 2026-10-20
Safety | 1.5.9.2 | Backend API | Task | 2 | Ronak | 94 | 96 | 2026-10-16 | 2026-10-16
Safety | 1.5.9.3 | Web Front End | Task | 2 | Soumy | 88 | 90 | 2026-10-15 | 2026-10-15
Safety | 1.5.9.4 | Mobile | Task | 2 | Hardik | 107 | 109 | 2026-10-20 | 2026-10-20
Safety | 1.5.10 | US-35: EHS Manager Issues and Releases Work Stop | User Story | 7 |  |  |  | 2026-10-15 | 2026-10-20
Safety | 1.5.10.2 | Backend API | Task | 2 | Ronak | 96 | 98 | 2026-10-16 | 2026-10-16
Safety | 1.5.10.3 | Web Front End | Task | 2 | Soumy | 90 | 92 | 2026-10-15 | 2026-10-16
Safety | 1.5.10.4 | Mobile | Task | 3 | Hardik | 109 | 112 | 2026-10-20 | 2026-10-20
Safety | 1.5.11 | US-36: Two-Party Closure of Completed Permit | User Story | 11 |  |  |  | 2026-10-16 | 2026-10-21
Safety | 1.5.11.2 | Backend API | Task | 4 | Ronak | 98 | 102 | 2026-10-19 | 2026-10-19
Safety | 1.5.11.3 | Web Front End | Task | 4 | Soumy | 92 | 96 | 2026-10-16 | 2026-10-16
Safety | 1.5.11.4 | Mobile | Task | 3 | Hardik | 112 | 115 | 2026-10-21 | 2026-10-21
Safety | 1.5.12 | US-37: System Auto-Expires Permit and Calculates Compliance % | User Story | 8 |  |  |  | 2026-10-16 | 2026-10-21
Safety | 1.5.12.2 | Backend API | Task | 4 | Ronak | 102 | 106 | 2026-10-19 | 2026-10-20
Safety | 1.5.12.3 | Web Front End | Task | 2 | Soumy | 96 | 98 | 2026-10-16 | 2026-10-16
Safety | 1.5.12.4 | Mobile | Task | 2 | Hardik | 115 | 117 | 2026-10-21 | 2026-10-21
Safety | 1.5.13 | US-38: PTW Notification Matrix Across the Approval and Execution Lifecycle | User Story | 8 |  |  |  | 2026-10-19 | 2026-10-21
Safety | 1.5.13.2 | Backend API | Task | 4 | Ronak | 106 | 110 | 2026-10-20 | 2026-10-20
Safety | 1.5.13.3 | Web Front End | Task | 2 | Soumy | 98 | 100 | 2026-10-19 | 2026-10-19
Safety | 1.5.13.4 | Mobile | Task | 2 | Hardik | 117 | 119 | 2026-10-21 | 2026-10-21
Safety | 1.7 | Epic 7: Checklist & Rating Enhancements | Epic | 62 |  |  |  | 2026-10-13 | 2026-10-26
Safety | 1.7.1 | US-49: Configure Photo-Mandatory Toggle per Checklist Point | User Story | 20 |  |  |  | 2026-10-19 | 2026-10-22
Safety | 1.7.1.1 | Database | Task | 2 | Ronak | 110 | 112 | 2026-10-20 | 2026-10-20
Safety | 1.7.1.2 | Backend API | Task | 6 | Ronak | 112 | 118 | 2026-10-21 | 2026-10-21
Safety | 1.7.1.3 | Web Front End | Task | 6 | Soumy | 100 | 106 | 2026-10-19 | 2026-10-20
Safety | 1.7.1.4 | Mobile | Task | 6 | Hardik | 119 | 125 | 2026-10-22 | 2026-10-22
Safety | 1.7.2 | US-50: Configure Project-Level Checklist Approver | User Story | 16 |  |  |  | 2026-10-13 | 2026-10-23
Safety | 1.7.2.1 | Database | Task | 2 | Parth Jani | 73 | 75 | 2026-10-13 | 2026-10-13
Safety | 1.7.2.2 | Backend API | Task | 6 | Ronak | 118 | 124 | 2026-10-21 | 2026-10-22
Safety | 1.7.2.3 | Web Front End | Task | 5 | Soumy | 106 | 111 | 2026-10-20 | 2026-10-20
Safety | 1.7.2.4 | Mobile | Task | 3 | Hardik | 125 | 128 | 2026-10-22 | 2026-10-23
Safety | 1.7.3 | US-51: Add Comments Throughout Checklist Lifecycle | User Story | 9 |  |  |  | 2026-10-13 | 2026-10-23
Safety | 1.7.3.1 | Database | Task | 2 | Parth Jani | 75 | 77 | 2026-10-13 | 2026-10-13
Safety | 1.7.3.2 | Backend API | Task | 3 | Ronak | 124 | 127 | 2026-10-22 | 2026-10-23
Safety | 1.7.3.3 | Web Front End | Task | 2 | Soumy | 111 | 113 | 2026-10-20 | 2026-10-21
Safety | 1.7.3.4 | Mobile | Task | 2 | Hardik | 128 | 130 | 2026-10-23 | 2026-10-23
Safety | 1.7.4 | US-52: Enforce Rating Immutability on New Submission | User Story | 8 |  |  |  | 2026-10-14 | 2026-10-23
Safety | 1.7.4.1 | Database | Task | 2 | Parth Jani | 77 | 79 | 2026-10-14 | 2026-10-14
Safety | 1.7.4.2 | Backend API | Task | 2 | Ronak | 127 | 129 | 2026-10-23 | 2026-10-23
Safety | 1.7.4.3 | Web Front End | Task | 2 | Soumy | 113 | 115 | 2026-10-21 | 2026-10-21
Safety | 1.7.4.4 | Mobile | Task | 2 | Hardik | 130 | 132 | 2026-10-23 | 2026-10-23
Safety | 1.7.5 | US-53: Configure Target CCP Score per Project Rating Template | User Story | 9 |  |  |  | 2026-10-14 | 2026-10-26
Safety | 1.7.5.1 | Database | Task | 2 | Parth Jani | 79 | 81 | 2026-10-14 | 2026-10-14
Safety | 1.7.5.2 | Backend API | Task | 3 | Ronak | 129 | 132 | 2026-10-23 | 2026-10-23
Safety | 1.7.5.3 | Web Front End | Task | 2 | Soumy | 115 | 117 | 2026-10-21 | 2026-10-21
Safety | 1.7.5.4 | Mobile | Task | 2 | Hardik | 132 | 134 | 2026-10-23 | 2026-10-26
Safety | 1.8 | Epic 8: Safety MIS & Dashboards | Epic | 60 |  |  |  | 2026-10-14 | 2026-10-28
Safety | 1.8.1 | US-54: User Dashboard with My Tasks and Permits | User Story | 20 |  |  |  | 2026-10-14 | 2026-10-26
Safety | 1.8.1.2 | Backend API | Task | 8 | Parth Jani | 81 | 89 | 2026-10-14 | 2026-10-15
Safety | 1.8.1.3 | Web Front End | Task | 7 | Soumy | 117 | 124 | 2026-10-21 | 2026-10-22
Safety | 1.8.1.4 | Mobile | Task | 5 | Hardik | 134 | 139 | 2026-10-26 | 2026-10-26
Safety | 1.8.2 | US-55: Project Dashboard Across All Three Tracks | User Story | 20 |  |  |  | 2026-10-15 | 2026-10-27
Safety | 1.8.2.2 | Backend API | Task | 8 | Parth Jani | 89 | 97 | 2026-10-15 | 2026-10-16
Safety | 1.8.2.3 | Web Front End | Task | 6 | Soumy | 124 | 130 | 2026-10-22 | 2026-10-23
Safety | 1.8.2.4 | Mobile | Task | 6 | Hardik | 139 | 145 | 2026-10-26 | 2026-10-27
Safety | 1.8.3 | US-56: Management Cross-Project Dashboard with Trends | User Story | 20 |  |  |  | 2026-10-16 | 2026-10-28
Safety | 1.8.3.2 | Backend API | Task | 8 | Parth Jani | 97 | 105 | 2026-10-16 | 2026-10-19
Safety | 1.8.3.3 | Web Front End | Task | 6 | Soumy | 130 | 136 | 2026-10-23 | 2026-10-26
Safety | 1.8.3.4 | Mobile | Task | 6 | Hardik | 145 | 151 | 2026-10-27 | 2026-10-28
Safety | 1.9 | Epic 9:Integrations & NFRs | Epic | 34 |  |  |  | 2026-10-20 | 2026-10-29
Safety | 1.9.2 | US-59: Consume Labour Registration Data from Admin Module | User Story | 10 |  |  |  | 2026-10-20 | 2026-10-28
Safety | 1.9.2.1 | Database | Task | 1 | Parth Jani | 105 | 106 | 2026-10-20 | 2026-10-20
Safety | 1.9.2.2 | Backend API | Task | 4 | Ronak | 132 | 136 | 2026-10-23 | 2026-10-26
Safety | 1.9.2.3 | Web Front End | Task | 2 | Soumy | 136 | 138 | 2026-10-26 | 2026-10-26
Safety | 1.9.2.4 | Mobile | Task | 3 | Hardik | 151 | 154 | 2026-10-28 | 2026-10-28
Safety | 1.9.4 | US-61: Convert PPE Issuance to MRIS via D365 Write Integration | User Story | 24 |  |  |  | 2026-10-20 | 2026-10-29
Safety | 1.9.4.1 | Database | Task | 4 | Parth Jani | 106 | 110 | 2026-10-20 | 2026-10-20
Safety | 1.9.4.2 | Backend API | Task | 8 | Ronak | 136 | 144 | 2026-10-26 | 2026-10-27
Safety | 1.9.4.3 | Web Front End | Task | 7 | Ronak | 144 | 151 | 2026-10-27 | 2026-10-28
Safety | 1.9.4.4 | Mobile | Task | 5 | Hardik | 154 | 159 | 2026-10-29 | 2026-10-29
P&M | 1 | HIMAPP 2.0 — PLANT & MACHINERY (PM) MODULE — Implementation | Project | 1045 |  |  |  | 2026-11-10 | 2027-01-04
P&M | 1.1 | Epic 1: Equipment Management | Epic | 176 |  |  |  | 2026-11-10 | 2026-11-26
P&M | 1.1.1 | PNM-001: Sync Equipment Master from D365 | User Story | 15 |  |  |  | 2026-11-10 | 2026-11-11
P&M | 1.1.1.1 | Database | Task | 3 | Parth Jani | 0 | 3 | 2026-11-10 | 2026-11-10
P&M | 1.1.1.2 | Backend API | Task | 6 | Parth Jani | 3 | 9 | 2026-11-10 | 2026-11-11
P&M | 1.1.1.3 | Web Front End | Task | 6 | Soumy | 0 | 6 | 2026-11-10 | 2026-11-10
P&M | 1.1.2 | PNM-002: View Equipment List (Equipment 360) | User Story | 12 |  |  |  | 2026-11-10 | 2026-11-12
P&M | 1.1.2.1 | Backend API | Task | 6 | Parth Jani | 9 | 15 | 2026-11-11 | 2026-11-12
P&M | 1.1.2.2 | Web Front End | Task | 6 | Soumy | 6 | 12 | 2026-11-10 | 2026-11-11
P&M | 1.1.3 | PNM-003: Search Equipment | User Story | 8 |  |  |  | 2026-11-11 | 2026-11-12
P&M | 1.1.3.1 | Backend API | Task | 4 | Parth Jani | 15 | 19 | 2026-11-12 | 2026-11-12
P&M | 1.1.3.2 | Web Front End | Task | 4 | Soumy | 12 | 16 | 2026-11-11 | 2026-11-12
P&M | 1.1.4 | PNM-004: View Equipment Detail — Overview Tab | User Story | 8 |  |  |  | 2026-11-12 | 2026-11-13
P&M | 1.1.4.1 | Backend API | Task | 4 | Parth Jani | 19 | 23 | 2026-11-12 | 2026-11-13
P&M | 1.1.4.2 | Web Front End | Task | 4 | Soumy | 16 | 20 | 2026-11-12 | 2026-11-12
P&M | 1.1.5 | PNM-005: View Equipment Lifecycle History | User Story | 8 |  |  |  | 2026-11-12 | 2026-11-13
P&M | 1.1.5.1 | Backend API | Task | 4 | Parth Jani | 23 | 27 | 2026-11-13 | 2026-11-13
P&M | 1.1.5.2 | Web Front End | Task | 4 | Soumy | 20 | 24 | 2026-11-12 | 2026-11-13
P&M | 1.1.6 | PNM-006: Assign Equipment to Project (Initial Assignment) | User Story | 10 |  |  |  | 2026-11-13 | 2026-11-16
P&M | 1.1.6.1 | Database | Task | 2 | Parth Jani | 27 | 29 | 2026-11-13 | 2026-11-16
P&M | 1.1.6.2 | Backend API | Task | 4 | Parth Jani | 29 | 33 | 2026-11-16 | 2026-11-16
P&M | 1.1.6.3 | Web Front End | Task | 4 | Soumy | 24 | 28 | 2026-11-13 | 2026-11-13
P&M | 1.1.7 | PNM-008: Raise Equipment Condition Report (ECR) — Sender | User Story | 15 |  |  |  | 2026-11-10 | 2026-11-17
P&M | 1.1.7.1 | Database | Task | 3 | Parth Jani | 33 | 36 | 2026-11-16 | 2026-11-17
P&M | 1.1.7.2 | Backend API | Task | 6 | Parth Jani | 36 | 42 | 2026-11-17 | 2026-11-17
P&M | 1.1.7.3 | Web Front End | Task | 6 | Inderjeet | 0 | 6 | 2026-11-10 | 2026-11-10
P&M | 1.1.8 | PNM-009: Auto-Cancel Open Spare MRIS on Transfer Completion | User Story | 10 |  |  |  | 2026-11-16 | 2026-11-18
P&M | 1.1.8.1 | Database | Task | 2 | Parth Jani | 42 | 44 | 2026-11-18 | 2026-11-18
P&M | 1.1.8.2 | Backend API | Task | 4 | Parth Jani | 44 | 48 | 2026-11-18 | 2026-11-18
P&M | 1.1.8.3 | Web Front End | Task | 4 | Soumy | 28 | 32 | 2026-11-16 | 2026-11-16
P&M | 1.1.9 | PNM-010: Acknowledge Incoming Equipment — Receiver ECR | User Story | 15 |  |  |  | 2026-11-10 | 2026-11-20
P&M | 1.1.9.1 | Database | Task | 3 | Parth Jani | 48 | 51 | 2026-11-18 | 2026-11-19
P&M | 1.1.9.2 | Backend API | Task | 6 | Parth Jani | 51 | 57 | 2026-11-19 | 2026-11-20
P&M | 1.1.9.3 | Web Front End | Task | 6 | Inderjeet | 6 | 12 | 2026-11-10 | 2026-11-11
P&M | 1.1.10 | PNM-011: Auto-Complete Equipment Transfer | User Story | 10 |  |  |  | 2026-11-16 | 2026-11-20
P&M | 1.1.10.1 | Database | Task | 2 | Parth Jani | 57 | 59 | 2026-11-20 | 2026-11-20
P&M | 1.1.10.2 | Backend API | Task | 4 | Parth Jani | 59 | 63 | 2026-11-20 | 2026-11-20
P&M | 1.1.10.3 | Web Front End | Task | 4 | Soumy | 32 | 36 | 2026-11-16 | 2026-11-17
P&M | 1.1.11 | PNM-012: Resolve ECR Dispute | User Story | 10 |  |  |  | 2026-11-17 | 2026-11-23
P&M | 1.1.11.1 | Database | Task | 2 | Parth Jani | 63 | 65 | 2026-11-23 | 2026-11-23
P&M | 1.1.11.2 | Backend API | Task | 4 | Parth Jani | 65 | 69 | 2026-11-23 | 2026-11-23
P&M | 1.1.11.3 | Web Front End | Task | 4 | Soumy | 36 | 40 | 2026-11-17 | 2026-11-17
P&M | 1.1.12 | PNM-013: View Transfers (ECR) List | User Story | 8 |  |  |  | 2026-11-10 | 2026-11-18
P&M | 1.1.12.1 | Backend API | Task | 4 | Ronak | 0 | 4 | 2026-11-10 | 2026-11-10
P&M | 1.1.12.2 | Web Front End | Task | 4 | Soumy | 40 | 44 | 2026-11-17 | 2026-11-18
P&M | 1.1.13 | PNM-014: Raise Gate Pass for Off-Site Repair | User Story | 15 |  |  |  | 2026-11-11 | 2026-11-25
P&M | 1.1.13.1 | Database | Task | 3 | Parth Jani | 69 | 72 | 2026-11-23 | 2026-11-24
P&M | 1.1.13.2 | Backend API | Task | 6 | Parth Jani | 72 | 78 | 2026-11-24 | 2026-11-25
P&M | 1.1.13.3 | Web Front End | Task | 6 | Inderjeet | 12 | 18 | 2026-11-11 | 2026-11-12
P&M | 1.1.14 | PNM-015: Record Gate Pass Return | User Story | 10 |  |  |  | 2026-11-18 | 2026-11-25
P&M | 1.1.14.1 | Database | Task | 2 | Parth Jani | 78 | 80 | 2026-11-25 | 2026-11-25
P&M | 1.1.14.2 | Backend API | Task | 4 | Parth Jani | 80 | 84 | 2026-11-25 | 2026-11-25
P&M | 1.1.14.3 | Web Front End | Task | 4 | Soumy | 44 | 48 | 2026-11-18 | 2026-11-18
P&M | 1.1.15 | PNM-016: Record Meter Replacement | User Story | 10 |  |  |  | 2026-11-12 | 2026-11-26
P&M | 1.1.15.1 | Database | Task | 2 | Parth Jani | 84 | 86 | 2026-11-26 | 2026-11-26
P&M | 1.1.15.2 | Backend API | Task | 4 | Parth Jani | 86 | 90 | 2026-11-26 | 2026-11-26
P&M | 1.1.15.3 | Web Front End | Task | 4 | Inderjeet | 18 | 22 | 2026-11-12 | 2026-11-13
P&M | 1.1.16 | PNM-017: View Equipment Availability / Dashboard Widgets | User Story | 12 |  |  |  | 2026-11-10 | 2026-11-19
P&M | 1.1.16.1 | Backend API | Task | 4 | Ronak | 4 | 8 | 2026-11-10 | 2026-11-11
P&M | 1.1.16.2 | Web Front End | Task | 4 | Soumy | 48 | 52 | 2026-11-18 | 2026-11-19
P&M | 1.1.16.3 | Mobile | Task | 4 | Hardik | 0 | 4 | 2026-11-10 | 2026-11-10
P&M | 1.2 | Epic 2: Daily Equipment Checklist | Epic | 76 |  |  |  | 2026-11-10 | 2026-12-02
P&M | 1.2.1 | PNM-018: Configure Checklist Template per Equipment Category | User Story | 15 |  |  |  | 2026-11-10 | 2026-11-27
P&M | 1.2.1.1 | Database | Task | 2 | Parth Jani | 90 | 92 | 2026-11-26 | 2026-11-27
P&M | 1.2.1.2 | Backend API | Task | 4 | Parth Jani | 92 | 96 | 2026-11-27 | 2026-11-27
P&M | 1.2.1.3 | Web Front End | Task | 5 | Inderjeet | 22 | 27 | 2026-11-13 | 2026-11-13
P&M | 1.2.1.4 | Mobile | Task | 4 | Hardik | 4 | 8 | 2026-11-10 | 2026-11-11
P&M | 1.2.2 | PNM-019: Submit Daily Equipment Checklist | User Story | 21 |  |  |  | 2026-11-11 | 2026-11-30
P&M | 1.2.2.1 | Database | Task | 3 | Parth Jani | 96 | 99 | 2026-11-27 | 2026-11-30
P&M | 1.2.2.2 | Backend API | Task | 6 | Parth Jani | 99 | 105 | 2026-11-30 | 2026-11-30
P&M | 1.2.2.3 | Web Front End | Task | 6 | Soumy | 52 | 58 | 2026-11-19 | 2026-11-20
P&M | 1.2.2.4 | Mobile | Task | 6 | Hardik | 8 | 14 | 2026-11-11 | 2026-11-11
P&M | 1.2.3 | PNM-020: Trigger Safety Notification on Not-OK Safety-Flagged Item | User Story | 14 |  |  |  | 2026-11-12 | 2026-12-01
P&M | 1.2.3.1 | Database | Task | 2 | Parth Jani | 105 | 107 | 2026-12-01 | 2026-12-01
P&M | 1.2.3.2 | Backend API | Task | 4 | Parth Jani | 107 | 111 | 2026-12-01 | 2026-12-01
P&M | 1.2.3.3 | Web Front End | Task | 4 | Soumy | 58 | 62 | 2026-11-20 | 2026-11-20
P&M | 1.2.3.4 | Mobile | Task | 4 | Hardik | 14 | 18 | 2026-11-12 | 2026-11-12
P&M | 1.2.4 | PNM-021: Prompt to Raise Breakdown SR on Failed Checklist Item | User Story | 14 |  |  |  | 2026-11-12 | 2026-12-02
P&M | 1.2.4.1 | Database | Task | 2 | Parth Jani | 111 | 113 | 2026-12-01 | 2026-12-02
P&M | 1.2.4.2 | Backend API | Task | 4 | Parth Jani | 113 | 117 | 2026-12-02 | 2026-12-02
P&M | 1.2.4.3 | Web Front End | Task | 4 | Inderjeet | 27 | 31 | 2026-11-13 | 2026-11-16
P&M | 1.2.4.4 | Mobile | Task | 4 | Hardik | 18 | 22 | 2026-11-12 | 2026-11-13
P&M | 1.2.5 | PNM-022: View Checklist History | User Story | 12 |  |  |  | 2026-11-11 | 2026-11-23
P&M | 1.2.5.1 | Backend API | Task | 4 | Ronak | 8 | 12 | 2026-11-11 | 2026-11-11
P&M | 1.2.5.2 | Web Front End | Task | 4 | Soumy | 62 | 66 | 2026-11-20 | 2026-11-23
P&M | 1.2.5.3 | Mobile | Task | 4 | Hardik | 22 | 26 | 2026-11-13 | 2026-11-13
P&M | 1.3 | Epic 3: Digital Log Book | Epic | 155 |  |  |  | 2026-11-11 | 2026-12-14
P&M | 1.3.1 | PNM-023: Claim Equipment Ownership via First Fill | User Story | 14 |  |  |  | 2026-11-13 | 2026-12-03
P&M | 1.3.1.1 | Database | Task | 2 | Parth Jani | 117 | 119 | 2026-12-02 | 2026-12-02
P&M | 1.3.1.2 | Backend API | Task | 4 | Parth Jani | 119 | 123 | 2026-12-03 | 2026-12-03
P&M | 1.3.1.3 | Web Front End | Task | 4 | Soumy | 66 | 70 | 2026-11-23 | 2026-11-23
P&M | 1.3.1.4 | Mobile | Task | 4 | Hardik | 26 | 30 | 2026-11-13 | 2026-11-16
P&M | 1.3.2 | PNM-024: Transfer Equipment Ownership | User Story | 14 |  |  |  | 2026-11-16 | 2026-12-04
P&M | 1.3.2.1 | Database | Task | 2 | Parth Jani | 123 | 125 | 2026-12-03 | 2026-12-03
P&M | 1.3.2.2 | Backend API | Task | 4 | Parth Jani | 125 | 129 | 2026-12-03 | 2026-12-04
P&M | 1.3.2.3 | Web Front End | Task | 4 | Inderjeet | 31 | 35 | 2026-11-16 | 2026-11-16
P&M | 1.3.2.4 | Mobile | Task | 4 | Hardik | 30 | 34 | 2026-11-16 | 2026-11-16
P&M | 1.3.3 | PNM-025: Override Equipment Ownership (In-Charge) | User Story | 14 |  |  |  | 2026-11-16 | 2026-12-07
P&M | 1.3.3.1 | Database | Task | 2 | Parth Jani | 129 | 131 | 2026-12-04 | 2026-12-04
P&M | 1.3.3.2 | Backend API | Task | 4 | Parth Jani | 131 | 135 | 2026-12-04 | 2026-12-07
P&M | 1.3.3.3 | Web Front End | Task | 4 | Inderjeet | 35 | 39 | 2026-11-17 | 2026-11-17
P&M | 1.3.3.4 | Mobile | Task | 4 | Hardik | 34 | 38 | 2026-11-16 | 2026-11-17
P&M | 1.3.4 | PNM-026: Notify on No Owner by Cutoff | User Story | 14 |  |  |  | 2026-11-17 | 2026-12-08
P&M | 1.3.4.1 | Database | Task | 2 | Parth Jani | 135 | 137 | 2026-12-07 | 2026-12-07
P&M | 1.3.4.2 | Backend API | Task | 4 | Parth Jani | 137 | 141 | 2026-12-07 | 2026-12-08
P&M | 1.3.4.3 | Web Front End | Task | 4 | Soumy | 70 | 74 | 2026-11-24 | 2026-11-24
P&M | 1.3.4.4 | Mobile | Task | 4 | Hardik | 38 | 42 | 2026-11-17 | 2026-11-17
P&M | 1.3.5 | PNM-027: Non-Submission Notification & Escalation Schedule | User Story | 21 |  |  |  | 2026-11-18 | 2026-12-09
P&M | 1.3.5.1 | Database | Task | 3 | Parth Jani | 141 | 144 | 2026-12-08 | 2026-12-08
P&M | 1.3.5.2 | Backend API | Task | 6 | Parth Jani | 144 | 150 | 2026-12-08 | 2026-12-09
P&M | 1.3.5.3 | Web Front End | Task | 6 | Soumy | 74 | 80 | 2026-11-24 | 2026-11-25
P&M | 1.3.5.4 | Mobile | Task | 6 | Hardik | 42 | 48 | 2026-11-18 | 2026-11-18
P&M | 1.3.6 | PNM-028: Submit Digital Log Book Entry | User Story | 21 |  |  |  | 2026-11-18 | 2026-12-10
P&M | 1.3.6.1 | Database | Task | 3 | Parth Jani | 150 | 153 | 2026-12-09 | 2026-12-09
P&M | 1.3.6.2 | Backend API | Task | 6 | Parth Jani | 153 | 159 | 2026-12-09 | 2026-12-10
P&M | 1.3.6.3 | Web Front End | Task | 6 | Soumy | 80 | 86 | 2026-11-25 | 2026-11-26
P&M | 1.3.6.4 | Mobile | Task | 6 | Hardik | 48 | 54 | 2026-11-18 | 2026-11-19
P&M | 1.3.7 | PNM-029: View Equipment Context Panel on Log Book | User Story | 12 |  |  |  | 2026-11-11 | 2026-11-26
P&M | 1.3.7.1 | Backend API | Task | 4 | Ronak | 12 | 16 | 2026-11-11 | 2026-11-12
P&M | 1.3.7.2 | Web Front End | Task | 4 | Soumy | 86 | 90 | 2026-11-26 | 2026-11-26
P&M | 1.3.7.3 | Mobile | Task | 4 | Hardik | 54 | 58 | 2026-11-19 | 2026-11-20
P&M | 1.3.8 | PNM-030: Evaluate PM Triggers After Log Book Submission | User Story | 21 |  |  |  | 2026-11-17 | 2026-12-11
P&M | 1.3.8.1 | Database | Task | 3 | Parth Jani | 159 | 162 | 2026-12-10 | 2026-12-11
P&M | 1.3.8.2 | Backend API | Task | 6 | Parth Jani | 162 | 168 | 2026-12-11 | 2026-12-11
P&M | 1.3.8.3 | Web Front End | Task | 6 | Inderjeet | 39 | 45 | 2026-11-17 | 2026-11-18
P&M | 1.3.8.4 | Mobile | Task | 6 | Hardik | 58 | 64 | 2026-11-20 | 2026-11-23
P&M | 1.3.9 | PNM-031: View Log Book History | User Story | 12 |  |  |  | 2026-11-12 | 2026-11-27
P&M | 1.3.9.1 | Backend API | Task | 4 | Ronak | 16 | 20 | 2026-11-12 | 2026-11-12
P&M | 1.3.9.2 | Web Front End | Task | 4 | Soumy | 90 | 94 | 2026-11-26 | 2026-11-27
P&M | 1.3.9.3 | Mobile | Task | 4 | Hardik | 64 | 68 | 2026-11-23 | 2026-11-23
P&M | 1.3.10 | PNM-032: View Checklist & Log Book Compliance Dashboard | User Story | 12 |  |  |  | 2026-11-23 | 2026-12-14
P&M | 1.3.10.1 | Backend API | Task | 4 | Parth Jani | 168 | 172 | 2026-12-14 | 2026-12-14
P&M | 1.3.10.2 | Web Front End | Task | 4 | Soumy | 94 | 98 | 2026-11-27 | 2026-11-27
P&M | 1.3.10.3 | Mobile | Task | 4 | Hardik | 68 | 72 | 2026-11-23 | 2026-11-24
P&M | 1.4 | Epic 4: Breakdown Management | Epic | 262 |  |  |  | 2026-11-12 | 2026-12-23
P&M | 1.4.1 | PNM-033: Raise Breakdown Service Request | User Story | 21 |  |  |  | 2026-11-24 | 2026-12-15
P&M | 1.4.1.1 | Database | Task | 3 | Parth Jani | 172 | 175 | 2026-12-14 | 2026-12-14
P&M | 1.4.1.2 | Backend API | Task | 6 | Parth Jani | 175 | 181 | 2026-12-15 | 2026-12-15
P&M | 1.4.1.3 | Web Front End | Task | 6 | Soumy | 98 | 104 | 2026-11-30 | 2026-11-30
P&M | 1.4.1.4 | Mobile | Task | 6 | Hardik | 72 | 78 | 2026-11-24 | 2026-11-25
P&M | 1.4.2 | PNM-034: Auto-Classify Breakdown Priority | User Story | 21 |  |  |  | 2026-11-18 | 2026-12-17
P&M | 1.4.2.1 | Database | Task | 3 | Parth Jani | 181 | 184 | 2026-12-15 | 2026-12-16
P&M | 1.4.2.2 | Backend API | Task | 6 | Parth Jani | 184 | 190 | 2026-12-16 | 2026-12-17
P&M | 1.4.2.3 | Web Front End | Task | 6 | Inderjeet | 45 | 51 | 2026-11-18 | 2026-11-19
P&M | 1.4.2.4 | Mobile | Task | 6 | Hardik | 78 | 84 | 2026-11-25 | 2026-11-25
P&M | 1.4.3 | PNM-035: Assign Mechanic to Breakdown SR | User Story | 14 |  |  |  | 2026-11-12 | 2026-12-17
P&M | 1.4.3.1 | Database | Task | 2 | Parth Jani | 190 | 192 | 2026-12-17 | 2026-12-17
P&M | 1.4.3.2 | Backend API | Task | 4 | Ronak | 20 | 24 | 2026-11-12 | 2026-11-13
P&M | 1.4.3.3 | Web Front End | Task | 4 | Soumy | 104 | 108 | 2026-11-30 | 2026-12-01
P&M | 1.4.3.4 | Mobile | Task | 4 | Hardik | 84 | 88 | 2026-11-26 | 2026-11-26
P&M | 1.4.4 | PNM-036: Reassign Mechanic on Breakdown SR | User Story | 21 |  |  |  | 2026-11-13 | 2026-12-17
P&M | 1.4.4.1 | Database | Task | 3 | Parth Jani | 192 | 195 | 2026-12-17 | 2026-12-17
P&M | 1.4.4.2 | Backend API | Task | 6 | Ronak | 24 | 30 | 2026-11-13 | 2026-11-16
P&M | 1.4.4.3 | Web Front End | Task | 6 | Soumy | 108 | 114 | 2026-12-01 | 2026-12-02
P&M | 1.4.4.4 | Mobile | Task | 6 | Hardik | 88 | 94 | 2026-11-26 | 2026-11-27
P&M | 1.4.5 | PNM-037: Start Work on Breakdown SR | User Story | 14 |  |  |  | 2026-11-16 | 2026-12-18
P&M | 1.4.5.1 | Database | Task | 2 | Parth Jani | 195 | 197 | 2026-12-17 | 2026-12-18
P&M | 1.4.5.2 | Backend API | Task | 4 | Ronak | 30 | 34 | 2026-11-16 | 2026-11-16
P&M | 1.4.5.3 | Web Front End | Task | 4 | Inderjeet | 51 | 55 | 2026-11-19 | 2026-11-19
P&M | 1.4.5.4 | Mobile | Task | 4 | Hardik | 94 | 98 | 2026-11-27 | 2026-11-27
P&M | 1.4.6 | PNM-038: Record BD SR Diagnosis | User Story | 21 |  |  |  | 2026-11-16 | 2026-12-18
P&M | 1.4.6.1 | Database | Task | 3 | Parth Jani | 197 | 200 | 2026-12-18 | 2026-12-18
P&M | 1.4.6.2 | Backend API | Task | 6 | Ronak | 34 | 40 | 2026-11-16 | 2026-11-17
P&M | 1.4.6.3 | Web Front End | Task | 6 | Inderjeet | 55 | 61 | 2026-11-19 | 2026-11-20
P&M | 1.4.6.4 | Mobile | Task | 6 | Hardik | 98 | 104 | 2026-11-30 | 2026-11-30
P&M | 1.4.7 | PNM-039: Raise Spare Parts MRIS from Breakdown SR | User Story | 14 |  |  |  | 2026-11-17 | 2026-12-18
P&M | 1.4.7.1 | Database | Task | 2 | Parth Jani | 200 | 202 | 2026-12-18 | 2026-12-18
P&M | 1.4.7.2 | Backend API | Task | 4 | Ronak | 40 | 44 | 2026-11-17 | 2026-11-18
P&M | 1.4.7.3 | Web Front End | Task | 4 | Soumy | 114 | 118 | 2026-12-02 | 2026-12-02
P&M | 1.4.7.4 | Mobile | Task | 4 | Hardik | 104 | 108 | 2026-11-30 | 2026-12-01
P&M | 1.4.8 | PNM-040: Resume Breakdown SR from On Hold | User Story | 14 |  |  |  | 2026-11-18 | 2026-12-21
P&M | 1.4.8.1 | Database | Task | 2 | Parth Jani | 202 | 204 | 2026-12-18 | 2026-12-21
P&M | 1.4.8.2 | Backend API | Task | 4 | Ronak | 44 | 48 | 2026-11-18 | 2026-11-18
P&M | 1.4.8.3 | Web Front End | Task | 4 | Soumy | 118 | 122 | 2026-12-02 | 2026-12-03
P&M | 1.4.8.4 | Mobile | Task | 4 | Hardik | 108 | 112 | 2026-12-01 | 2026-12-01
P&M | 1.4.9 | PNM-041: Resolve Breakdown SR | User Story | 21 |  |  |  | 2026-11-18 | 2026-12-21
P&M | 1.4.9.1 | Database | Task | 3 | Parth Jani | 204 | 207 | 2026-12-21 | 2026-12-21
P&M | 1.4.9.2 | Backend API | Task | 6 | Ronak | 48 | 54 | 2026-11-18 | 2026-11-19
P&M | 1.4.9.3 | Web Front End | Task | 6 | Soumy | 122 | 128 | 2026-12-03 | 2026-12-04
P&M | 1.4.9.4 | Mobile | Task | 6 | Hardik | 112 | 118 | 2026-12-02 | 2026-12-02
P&M | 1.4.10 | PNM-042: Capture Maintenance Activities During Breakdown Repair (PM Counter Sync) | User Story | 21 |  |  |  | 2026-11-19 | 2026-12-21
P&M | 1.4.10.1 | Database | Task | 3 | Parth Jani | 207 | 210 | 2026-12-21 | 2026-12-21
P&M | 1.4.10.2 | Backend API | Task | 6 | Ronak | 54 | 60 | 2026-11-19 | 2026-11-20
P&M | 1.4.10.3 | Web Front End | Task | 6 | Inderjeet | 61 | 67 | 2026-11-20 | 2026-11-23
P&M | 1.4.10.4 | Mobile | Task | 6 | Hardik | 118 | 124 | 2026-12-02 | 2026-12-03
P&M | 1.4.11 | PNM-043: Confirm Fix and Close Breakdown SR | User Story | 14 |  |  |  | 2026-11-20 | 2026-12-22
P&M | 1.4.11.1 | Database | Task | 2 | Parth Jani | 210 | 212 | 2026-12-22 | 2026-12-22
P&M | 1.4.11.2 | Backend API | Task | 4 | Ronak | 60 | 64 | 2026-11-20 | 2026-11-23
P&M | 1.4.11.3 | Web Front End | Task | 4 | Soumy | 128 | 132 | 2026-12-04 | 2026-12-04
P&M | 1.4.11.4 | Mobile | Task | 4 | Hardik | 124 | 128 | 2026-12-03 | 2026-12-04
P&M | 1.4.12 | PNM-044: Reopen Breakdown SR | User Story | 14 |  |  |  | 2026-11-23 | 2026-12-22
P&M | 1.4.12.1 | Database | Task | 2 | Parth Jani | 212 | 214 | 2026-12-22 | 2026-12-22
P&M | 1.4.12.2 | Backend API | Task | 4 | Ronak | 64 | 68 | 2026-11-23 | 2026-11-23
P&M | 1.4.12.3 | Web Front End | Task | 4 | Soumy | 132 | 136 | 2026-12-04 | 2026-12-07
P&M | 1.4.12.4 | Mobile | Task | 4 | Hardik | 128 | 132 | 2026-12-04 | 2026-12-04
P&M | 1.4.13 | PNM-045: View Breakdown SR Timeline / Activity Log | User Story | 12 |  |  |  | 2026-11-23 | 2026-12-07
P&M | 1.4.13.1 | Backend API | Task | 4 | Ronak | 68 | 72 | 2026-11-23 | 2026-11-24
P&M | 1.4.13.2 | Web Front End | Task | 4 | Soumy | 136 | 140 | 2026-12-07 | 2026-12-07
P&M | 1.4.13.3 | Mobile | Task | 4 | Hardik | 132 | 136 | 2026-12-04 | 2026-12-07
P&M | 1.4.14 | PNM-046: Attach Photos to Breakdown SR | User Story | 14 |  |  |  | 2026-11-24 | 2026-12-22
P&M | 1.4.14.1 | Database | Task | 2 | Parth Jani | 214 | 216 | 2026-12-22 | 2026-12-22
P&M | 1.4.14.2 | Backend API | Task | 4 | Ronak | 72 | 76 | 2026-11-24 | 2026-11-24
P&M | 1.4.14.3 | Web Front End | Task | 4 | Soumy | 140 | 144 | 2026-12-08 | 2026-12-08
P&M | 1.4.14.4 | Mobile | Task | 4 | Hardik | 136 | 140 | 2026-12-07 | 2026-12-07
P&M | 1.4.15 | PNM-047: Search and Filter Breakdown SR List | User Story | 12 |  |  |  | 2026-11-24 | 2026-12-09
P&M | 1.4.15.1 | Backend API | Task | 4 | Ronak | 76 | 80 | 2026-11-24 | 2026-11-25
P&M | 1.4.15.2 | Web Front End | Task | 4 | Soumy | 144 | 148 | 2026-12-08 | 2026-12-09
P&M | 1.4.15.3 | Mobile | Task | 4 | Hardik | 140 | 144 | 2026-12-08 | 2026-12-08
P&M | 1.4.16 | PNM-048: Flag and Alert on SR Ageing | User Story | 14 |  |  |  | 2026-11-25 | 2026-12-23
P&M | 1.4.16.1 | Database | Task | 2 | Parth Jani | 216 | 218 | 2026-12-22 | 2026-12-23
P&M | 1.4.16.2 | Backend API | Task | 4 | Ronak | 80 | 84 | 2026-11-25 | 2026-11-25
P&M | 1.4.16.3 | Web Front End | Task | 4 | Soumy | 148 | 152 | 2026-12-09 | 2026-12-09
P&M | 1.4.16.4 | Mobile | Task | 4 | Hardik | 144 | 148 | 2026-12-08 | 2026-12-09
P&M | 1.5 | Epic 5: Preventive Maintenance | Epic | 122 |  |  |  | 2026-11-26 | 2026-12-28
P&M | 1.5.1 | PNM-049: Auto-Generate PM Service Request | User Story | 14 |  |  |  | 2026-11-26 | 2026-12-23
P&M | 1.5.1.1 | Database | Task | 2 | Parth Jani | 218 | 220 | 2026-12-23 | 2026-12-23
P&M | 1.5.1.2 | Backend API | Task | 4 | Ronak | 84 | 88 | 2026-11-26 | 2026-11-26
P&M | 1.5.1.3 | Web Front End | Task | 4 | Soumy | 152 | 156 | 2026-12-09 | 2026-12-10
P&M | 1.5.1.4 | Mobile | Task | 4 | Hardik | 148 | 152 | 2026-12-09 | 2026-12-09
P&M | 1.5.2 | PNM-050: Manually Create PM Service Request | User Story | 14 |  |  |  | 2026-11-26 | 2026-12-23
P&M | 1.5.2.1 | Database | Task | 2 | Parth Jani | 220 | 222 | 2026-12-23 | 2026-12-23
P&M | 1.5.2.2 | Backend API | Task | 4 | Ronak | 88 | 92 | 2026-11-26 | 2026-11-27
P&M | 1.5.2.3 | Web Front End | Task | 4 | Soumy | 156 | 160 | 2026-12-10 | 2026-12-10
P&M | 1.5.2.4 | Mobile | Task | 4 | Hardik | 152 | 156 | 2026-12-09 | 2026-12-10
P&M | 1.5.3 | PNM-051: Assign Mechanic to PM SR | User Story | 14 |  |  |  | 2026-11-27 | 2026-12-23
P&M | 1.5.3.1 | Database | Task | 2 | Parth Jani | 222 | 224 | 2026-12-23 | 2026-12-23
P&M | 1.5.3.2 | Backend API | Task | 4 | Ronak | 92 | 96 | 2026-11-27 | 2026-11-27
P&M | 1.5.3.3 | Web Front End | Task | 4 | Soumy | 160 | 164 | 2026-12-10 | 2026-12-11
P&M | 1.5.3.4 | Mobile | Task | 4 | Hardik | 156 | 160 | 2026-12-10 | 2026-12-10
P&M | 1.5.4 | PNM-052: Execute PM Checklist and Mark Item Outcomes | User Story | 21 |  |  |  | 2026-11-27 | 2026-12-24
P&M | 1.5.4.1 | Database | Task | 3 | Parth Jani | 224 | 227 | 2026-12-24 | 2026-12-24
P&M | 1.5.4.2 | Backend API | Task | 6 | Ronak | 96 | 102 | 2026-11-27 | 2026-11-30
P&M | 1.5.4.3 | Web Front End | Task | 6 | Soumy | 164 | 170 | 2026-12-11 | 2026-12-14
P&M | 1.5.4.4 | Mobile | Task | 6 | Hardik | 160 | 166 | 2026-12-10 | 2026-12-11
P&M | 1.5.5 | PNM-053: Review and Decide on PM Item Deferrals at Closure | User Story | 21 |  |  |  | 2026-11-30 | 2026-12-24
P&M | 1.5.5.1 | Database | Task | 3 | Parth Jani | 227 | 230 | 2026-12-24 | 2026-12-24
P&M | 1.5.5.2 | Backend API | Task | 6 | Ronak | 102 | 108 | 2026-11-30 | 2026-12-01
P&M | 1.5.5.3 | Web Front End | Task | 6 | Soumy | 170 | 176 | 2026-12-14 | 2026-12-15
P&M | 1.5.5.4 | Mobile | Task | 6 | Hardik | 166 | 172 | 2026-12-11 | 2026-12-14
P&M | 1.5.6 | PNM-054: Close Preventive Maintenance SR | User Story | 14 |  |  |  | 2026-12-01 | 2026-12-28
P&M | 1.5.6.1 | Database | Task | 2 | Parth Jani | 230 | 232 | 2026-12-24 | 2026-12-28
P&M | 1.5.6.2 | Backend API | Task | 4 | Ronak | 108 | 112 | 2026-12-01 | 2026-12-01
P&M | 1.5.6.3 | Web Front End | Task | 4 | Soumy | 176 | 180 | 2026-12-15 | 2026-12-15
P&M | 1.5.6.4 | Mobile | Task | 4 | Hardik | 172 | 176 | 2026-12-14 | 2026-12-15
P&M | 1.5.7 | PNM-055: View PM Schedule and Compliance Status | User Story | 12 |  |  |  | 2026-12-02 | 2026-12-16
P&M | 1.5.7.1 | Backend API | Task | 4 | Ronak | 112 | 116 | 2026-12-02 | 2026-12-02
P&M | 1.5.7.2 | Web Front End | Task | 4 | Soumy | 180 | 184 | 2026-12-15 | 2026-12-16
P&M | 1.5.7.3 | Mobile | Task | 4 | Hardik | 176 | 180 | 2026-12-15 | 2026-12-15
P&M | 1.5.8 | PNM-056: View PM History | User Story | 12 |  |  |  | 2026-12-02 | 2026-12-16
P&M | 1.5.8.1 | Backend API | Task | 4 | Ronak | 116 | 120 | 2026-12-02 | 2026-12-03
P&M | 1.5.8.2 | Web Front End | Task | 4 | Soumy | 184 | 188 | 2026-12-16 | 2026-12-16
P&M | 1.5.8.3 | Mobile | Task | 4 | Hardik | 180 | 184 | 2026-12-15 | 2026-12-16
P&M | 1.6 | Epic 8: Fuel/Spare Parts MRIS | Epic | 82 |  |  |  | 2026-12-03 | 2026-12-29
P&M | 1.6.1 | PNM-069: Select Spare Parts for SR-Linked MRIS | User Story | 14 |  |  |  | 2026-12-03 | 2026-12-28
P&M | 1.6.1.1 | Database | Task | 2 | Parth Jani | 232 | 234 | 2026-12-28 | 2026-12-28
P&M | 1.6.1.2 | Backend API | Task | 4 | Ronak | 120 | 124 | 2026-12-03 | 2026-12-03
P&M | 1.6.1.3 | Web Front End | Task | 4 | Soumy | 188 | 192 | 2026-12-16 | 2026-12-17
P&M | 1.6.1.4 | Mobile | Task | 4 | Hardik | 184 | 188 | 2026-12-16 | 2026-12-16
P&M | 1.6.2 | PNM-070: Approve Spare Parts MRIS | User Story | 14 |  |  |  | 2026-12-03 | 2026-12-28
P&M | 1.6.2.1 | Database | Task | 2 | Parth Jani | 234 | 236 | 2026-12-28 | 2026-12-28
P&M | 1.6.2.2 | Backend API | Task | 4 | Ronak | 124 | 128 | 2026-12-03 | 2026-12-04
P&M | 1.6.2.3 | Web Front End | Task | 4 | Soumy | 192 | 196 | 2026-12-17 | 2026-12-17
P&M | 1.6.2.4 | Mobile | Task | 4 | Hardik | 188 | 192 | 2026-12-16 | 2026-12-17
P&M | 1.6.3 | PNM-071: Issue Material Against Spare Parts MRIS | User Story | 14 |  |  |  | 2026-12-04 | 2026-12-28
P&M | 1.6.3.1 | Database | Task | 2 | Parth Jani | 236 | 238 | 2026-12-28 | 2026-12-28
P&M | 1.6.3.2 | Backend API | Task | 4 | Ronak | 128 | 132 | 2026-12-04 | 2026-12-04
P&M | 1.6.3.3 | Web Front End | Task | 4 | Soumy | 196 | 200 | 2026-12-18 | 2026-12-18
P&M | 1.6.3.4 | Mobile | Task | 4 | Hardik | 192 | 196 | 2026-12-17 | 2026-12-17
P&M | 1.6.4 | PNM-072: Acknowledge Spare Parts Receipt | User Story | 14 |  |  |  | 2026-12-04 | 2026-12-29
P&M | 1.6.4.1 | Database | Task | 2 | Parth Jani | 238 | 240 | 2026-12-29 | 2026-12-29
P&M | 1.6.4.2 | Backend API | Task | 4 | Ronak | 132 | 136 | 2026-12-04 | 2026-12-07
P&M | 1.6.4.3 | Web Front End | Task | 4 | Soumy | 200 | 204 | 2026-12-18 | 2026-12-21
P&M | 1.6.4.4 | Mobile | Task | 4 | Hardik | 196 | 200 | 2026-12-18 | 2026-12-18
P&M | 1.6.5 | PNM-073: View Spare Parts Consumption History | User Story | 12 |  |  |  | 2026-12-07 | 2026-12-21
P&M | 1.6.5.1 | Backend API | Task | 4 | Ronak | 136 | 140 | 2026-12-07 | 2026-12-07
P&M | 1.6.5.2 | Web Front End | Task | 4 | Soumy | 204 | 208 | 2026-12-21 | 2026-12-21
P&M | 1.6.5.3 | Mobile | Task | 4 | Hardik | 200 | 204 | 2026-12-18 | 2026-12-21
P&M | 1.6.6 | PNM-074: Auto-Cancel Spare MRIS on Equipment Transfer | User Story | 14 |  |  |  | 2026-12-08 | 2026-12-29
P&M | 1.6.6.1 | Database | Task | 2 | Parth Jani | 240 | 242 | 2026-12-29 | 2026-12-29
P&M | 1.6.6.2 | Backend API | Task | 4 | Ronak | 140 | 144 | 2026-12-08 | 2026-12-08
P&M | 1.6.6.3 | Web Front End | Task | 4 | Soumy | 208 | 212 | 2026-12-21 | 2026-12-22
P&M | 1.6.6.4 | Mobile | Task | 4 | Hardik | 204 | 208 | 2026-12-21 | 2026-12-21
P&M | 1.7 | Epic 9: Reports & Analytics | Epic | 124 |  |  |  | 2026-12-08 | 2026-12-30
P&M | 1.7.1 | PNM-076: View Equipment Utilization Report | User Story | 12 |  |  |  | 2026-12-08 | 2026-12-22
P&M | 1.7.1.1 | Backend API | Task | 4 | Ronak | 144 | 148 | 2026-12-08 | 2026-12-09
P&M | 1.7.1.2 | Web Front End | Task | 4 | Soumy | 212 | 216 | 2026-12-22 | 2026-12-22
P&M | 1.7.1.3 | Mobile | Task | 4 | Hardik | 208 | 212 | 2026-12-21 | 2026-12-22
P&M | 1.7.2 | PNM-077: View Downtime Report (Total, MTTR, Net Repair Time, Hold Breakdown) | User Story | 12 |  |  |  | 2026-12-09 | 2026-12-23
P&M | 1.7.2.1 | Backend API | Task | 4 | Ronak | 148 | 152 | 2026-12-09 | 2026-12-09
P&M | 1.7.2.2 | Web Front End | Task | 4 | Soumy | 216 | 220 | 2026-12-22 | 2026-12-23
P&M | 1.7.2.3 | Mobile | Task | 4 | Hardik | 212 | 216 | 2026-12-22 | 2026-12-22
P&M | 1.7.3 | PNM-078: View Breakdown Reports | User Story | 12 |  |  |  | 2026-12-09 | 2026-12-23
P&M | 1.7.3.1 | Backend API | Task | 4 | Ronak | 152 | 156 | 2026-12-09 | 2026-12-10
P&M | 1.7.3.2 | Web Front End | Task | 4 | Soumy | 220 | 224 | 2026-12-23 | 2026-12-23
P&M | 1.7.3.3 | Mobile | Task | 4 | Hardik | 216 | 220 | 2026-12-22 | 2026-12-23
P&M | 1.7.4 | PNM-079: View PM Reports (Adherence & Deferral Summary) | User Story | 12 |  |  |  | 2026-12-10 | 2026-12-24
P&M | 1.7.4.1 | Backend API | Task | 4 | Ronak | 156 | 160 | 2026-12-10 | 2026-12-10
P&M | 1.7.4.2 | Web Front End | Task | 4 | Soumy | 224 | 228 | 2026-12-24 | 2026-12-24
P&M | 1.7.4.3 | Mobile | Task | 4 | Hardik | 220 | 224 | 2026-12-23 | 2026-12-23
P&M | 1.7.5 | PNM-080: View Fuel Consumption Report | User Story | 12 |  |  |  | 2026-12-10 | 2026-12-28
P&M | 1.7.5.1 | Backend API | Task | 4 | Ronak | 160 | 164 | 2026-12-10 | 2026-12-11
P&M | 1.7.5.2 | Web Front End | Task | 4 | Soumy | 228 | 232 | 2026-12-24 | 2026-12-28
P&M | 1.7.5.3 | Mobile | Task | 4 | Hardik | 224 | 228 | 2026-12-24 | 2026-12-24
P&M | 1.7.6 | PNM-081: View Spare Parts Consumption Report | User Story | 12 |  |  |  | 2026-12-11 | 2026-12-28
P&M | 1.7.6.1 | Backend API | Task | 4 | Ronak | 164 | 168 | 2026-12-11 | 2026-12-11
P&M | 1.7.6.2 | Web Front End | Task | 4 | Soumy | 232 | 236 | 2026-12-28 | 2026-12-28
P&M | 1.7.6.3 | Mobile | Task | 4 | Hardik | 228 | 232 | 2026-12-24 | 2026-12-28
P&M | 1.7.7 | PNM-082: View Idle Equipment Report | User Story | 12 |  |  |  | 2026-12-14 | 2026-12-29
P&M | 1.7.7.1 | Backend API | Task | 4 | Ronak | 168 | 172 | 2026-12-14 | 2026-12-14
P&M | 1.7.7.2 | Web Front End | Task | 4 | Soumy | 236 | 240 | 2026-12-28 | 2026-12-29
P&M | 1.7.7.3 | Mobile | Task | 4 | Hardik | 232 | 236 | 2026-12-28 | 2026-12-28
P&M | 1.7.8 | PNM-083: Detect and Report Recurring Failures | User Story | 14 |  |  |  | 2026-12-14 | 2026-12-29
P&M | 1.7.8.1 | Database | Task | 2 | Parth Jani | 242 | 244 | 2026-12-29 | 2026-12-29
P&M | 1.7.8.2 | Backend API | Task | 4 | Ronak | 172 | 176 | 2026-12-14 | 2026-12-15
P&M | 1.7.8.3 | Web Front End | Task | 4 | Soumy | 240 | 244 | 2026-12-29 | 2026-12-29
P&M | 1.7.8.4 | Mobile | Task | 4 | Hardik | 236 | 240 | 2026-12-28 | 2026-12-29
P&M | 1.7.9 | PNM-084: View Mechanic Performance Report | User Story | 12 |  |  |  | 2026-12-15 | 2026-12-30
P&M | 1.7.9.1 | Backend API | Task | 4 | Ronak | 176 | 180 | 2026-12-15 | 2026-12-15
P&M | 1.7.9.2 | Web Front End | Task | 4 | Soumy | 244 | 248 | 2026-12-29 | 2026-12-30
P&M | 1.7.9.3 | Mobile | Task | 4 | Hardik | 240 | 244 | 2026-12-29 | 2026-12-29
P&M | 1.7.10 | PNM-085: Export and Print Reports | User Story | 14 |  |  |  | 2026-12-15 | 2026-12-30
P&M | 1.7.10.1 | Database | Task | 2 | Parth Jani | 244 | 246 | 2026-12-29 | 2026-12-30
P&M | 1.7.10.2 | Backend API | Task | 4 | Ronak | 180 | 184 | 2026-12-15 | 2026-12-16
P&M | 1.7.10.3 | Web Front End | Task | 4 | Soumy | 248 | 252 | 2026-12-30 | 2026-12-30
P&M | 1.7.10.4 | Mobile | Task | 4 | Hardik | 244 | 248 | 2026-12-29 | 2026-12-30
P&M | 1.10 | Epic 10: Masters | Epic | 48 |  |  |  | 2026-12-16 | 2027-01-04
P&M | 1.10.1 | PNM-086: Configure Maintenance Activity Details Master | User Story | 3 |  |  |  | 2026-12-16 | 2026-12-31
P&M | 1.10.1.1 | Database | Task | 1 | Parth Jani | 246 | 247 | 2026-12-30 | 2026-12-30
P&M | 1.10.1.2 | Backend API | Task | 1 | Ronak | 184 | 185 | 2026-12-16 | 2026-12-16
P&M | 1.10.1.3 | Web Front End | Task | 1 | Soumy | 252 | 253 | 2026-12-31 | 2026-12-31
P&M | 1.10.2 | PNM-087: Configure Equipment Checklist Points Master | User Story | 3 |  |  |  | 2026-12-16 | 2026-12-31
P&M | 1.10.2.1 | Database | Task | 1 | Parth Jani | 247 | 248 | 2026-12-30 | 2026-12-30
P&M | 1.10.2.2 | Backend API | Task | 1 | Ronak | 185 | 186 | 2026-12-16 | 2026-12-16
P&M | 1.10.2.3 | Web Front End | Task | 1 | Soumy | 253 | 254 | 2026-12-31 | 2026-12-31
P&M | 1.10.3 | PNM-088: Configure Breakdown Reason Codes Master | User Story | 3 |  |  |  | 2026-12-16 | 2026-12-31
P&M | 1.10.3.1 | Database | Task | 1 | Parth Jani | 248 | 249 | 2026-12-30 | 2026-12-30
P&M | 1.10.3.2 | Backend API | Task | 1 | Ronak | 186 | 187 | 2026-12-16 | 2026-12-16
P&M | 1.10.3.3 | Web Front End | Task | 1 | Soumy | 254 | 255 | 2026-12-31 | 2026-12-31
P&M | 1.10.4 | PNM-089: Configure Sub-Part Names Master | User Story | 3 |  |  |  | 2026-12-16 | 2026-12-31
P&M | 1.10.4.1 | Database | Task | 1 | Parth Jani | 249 | 250 | 2026-12-30 | 2026-12-30
P&M | 1.10.4.2 | Backend API | Task | 1 | Ronak | 187 | 188 | 2026-12-16 | 2026-12-16
P&M | 1.10.4.3 | Web Front End | Task | 1 | Soumy | 255 | 256 | 2026-12-31 | 2026-12-31
P&M | 1.10.5 | PNM-090: Configure In-house Maintenance Remarks Master | User Story | 3 |  |  |  | 2026-12-16 | 2026-12-31
P&M | 1.10.5.1 | Database | Task | 1 | Parth Jani | 250 | 251 | 2026-12-30 | 2026-12-30
P&M | 1.10.5.2 | Backend API | Task | 1 | Ronak | 188 | 189 | 2026-12-16 | 2026-12-16
P&M | 1.10.5.3 | Web Front End | Task | 1 | Soumy | 256 | 257 | 2026-12-31 | 2026-12-31
P&M | 1.10.6 | PNM-091: Configure Specification Field Definitions Master | User Story | 3 |  |  |  | 2026-12-17 | 2026-12-31
P&M | 1.10.6.1 | Database | Task | 1 | Parth Jani | 251 | 252 | 2026-12-30 | 2026-12-30
P&M | 1.10.6.2 | Backend API | Task | 1 | Ronak | 189 | 190 | 2026-12-17 | 2026-12-17
P&M | 1.10.6.3 | Web Front End | Task | 1 | Soumy | 257 | 258 | 2026-12-31 | 2026-12-31
P&M | 1.10.7 | PNM-092: Configure Work Description Types Master | User Story | 3 |  |  |  | 2026-12-17 | 2026-12-31
P&M | 1.10.7.1 | Database | Task | 1 | Parth Jani | 252 | 253 | 2026-12-31 | 2026-12-31
P&M | 1.10.7.2 | Backend API | Task | 1 | Ronak | 190 | 191 | 2026-12-17 | 2026-12-17
P&M | 1.10.7.3 | Web Front End | Task | 1 | Soumy | 258 | 259 | 2026-12-31 | 2026-12-31
P&M | 1.10.8 | PNM-093: Configure Failure Type Master | User Story | 3 |  |  |  | 2026-12-17 | 2027-01-01
P&M | 1.10.8.1 | Database | Task | 1 | Parth Jani | 253 | 254 | 2026-12-31 | 2026-12-31
P&M | 1.10.8.2 | Backend API | Task | 1 | Ronak | 191 | 192 | 2026-12-17 | 2026-12-17
P&M | 1.10.8.3 | Web Front End | Task | 1 | Soumy | 259 | 260 | 2027-01-01 | 2027-01-01
P&M | 1.10.9 | PNM-094: Configure Sub-System Master | User Story | 3 |  |  |  | 2026-12-17 | 2027-01-01
P&M | 1.10.9.1 | Database | Task | 1 | Parth Jani | 254 | 255 | 2026-12-31 | 2026-12-31
P&M | 1.10.9.2 | Backend API | Task | 1 | Ronak | 192 | 193 | 2026-12-17 | 2026-12-17
P&M | 1.10.9.3 | Web Front End | Task | 1 | Soumy | 260 | 261 | 2027-01-01 | 2027-01-01
P&M | 1.10.10 | PNM-095: Configure Location Master | User Story | 3 |  |  |  | 2026-12-17 | 2027-01-01
P&M | 1.10.10.1 | Database | Task | 1 | Parth Jani | 255 | 256 | 2026-12-31 | 2026-12-31
P&M | 1.10.10.2 | Backend API | Task | 1 | Ronak | 193 | 194 | 2026-12-17 | 2026-12-17
P&M | 1.10.10.3 | Web Front End | Task | 1 | Soumy | 261 | 262 | 2027-01-01 | 2027-01-01
P&M | 1.10.11 | PNM-096: Configure Fuel Type Master | User Story | 3 |  |  |  | 2026-12-17 | 2027-01-01
P&M | 1.10.11.1 | Database | Task | 1 | Parth Jani | 256 | 257 | 2026-12-31 | 2026-12-31
P&M | 1.10.11.2 | Backend API | Task | 1 | Ronak | 194 | 195 | 2026-12-17 | 2026-12-17
P&M | 1.10.11.3 | Web Front End | Task | 1 | Soumy | 262 | 263 | 2027-01-01 | 2027-01-01
P&M | 1.10.12 | PNM-097: Configure Material / Spare Parts Catalogue | User Story | 3 |  |  |  | 2026-12-17 | 2027-01-01
P&M | 1.10.12.1 | Database | Task | 1 | Parth Jani | 257 | 258 | 2026-12-31 | 2026-12-31
P&M | 1.10.12.2 | Backend API | Task | 1 | Ronak | 195 | 196 | 2026-12-17 | 2026-12-17
P&M | 1.10.12.3 | Web Front End | Task | 1 | Soumy | 263 | 264 | 2027-01-01 | 2027-01-01
P&M | 1.10.13 | PNM-098: Configure PM Schedule Master | User Story | 3 |  |  |  | 2026-12-18 | 2027-01-01
P&M | 1.10.13.1 | Database | Task | 1 | Parth Jani | 258 | 259 | 2026-12-31 | 2026-12-31
P&M | 1.10.13.2 | Backend API | Task | 1 | Ronak | 196 | 197 | 2026-12-18 | 2026-12-18
P&M | 1.10.13.3 | Web Front End | Task | 1 | Soumy | 264 | 265 | 2027-01-01 | 2027-01-01
P&M | 1.10.14 | PNM-099: Configure Opening Counter Readings (Equipment-Level) | User Story | 3 |  |  |  | 2026-12-18 | 2027-01-01
P&M | 1.10.14.1 | Database | Task | 1 | Parth Jani | 259 | 260 | 2027-01-01 | 2027-01-01
P&M | 1.10.14.2 | Backend API | Task | 1 | Ronak | 197 | 198 | 2026-12-18 | 2026-12-18
P&M | 1.10.14.3 | Web Front End | Task | 1 | Soumy | 265 | 266 | 2027-01-01 | 2027-01-01
P&M | 1.10.15 | PNM-100: Configure Maintenance Points (Equipment-Level) | User Story | 3 |  |  |  | 2026-12-18 | 2027-01-04
P&M | 1.10.15.1 | Database | Task | 1 | Parth Jani | 260 | 261 | 2027-01-01 | 2027-01-01
P&M | 1.10.15.2 | Backend API | Task | 1 | Ronak | 198 | 199 | 2026-12-18 | 2026-12-18
P&M | 1.10.15.3 | Web Front End | Task | 1 | Soumy | 266 | 267 | 2027-01-04 | 2027-01-04
P&M | 1.10.16 | PNM-101: Configure Sub-Part Details and Specification Values (Equipment-Level) | User Story | 3 |  |  |  | 2026-12-18 | 2027-01-04
P&M | 1.10.16.1 | Database | Task | 1 | Parth Jani | 261 | 262 | 2027-01-01 | 2027-01-01
P&M | 1.10.16.2 | Backend API | Task | 1 | Ronak | 199 | 200 | 2026-12-18 | 2026-12-18
P&M | 1.10.16.3 | Web Front End | Task | 1 | Soumy | 267 | 268 | 2027-01-04 | 2027-01-04
Store | 1 | HIMAPP 2.0 — Store Module Implementation | Project | 286 |  |  |  | 2027-01-14 | 2027-01-28
Store | 1.1 | Epic 1: Store Master Data & Configuration | Epic | 18 |  |  |  | 2027-01-14 | 2027-01-15
Store | 1.1.1 | US-01: Configure Gate Pass Type Master with Seeded Values | User Story | 6 |  |  |  | 2027-01-14 | 2027-01-14
Store | 1.1.1.1 | Database | Task | 2 | Inderjeet | 0 | 2 | 2027-01-14 | 2027-01-14
Store | 1.1.1.2 | Backend API | Task | 4 | Ronak | 0 | 4 | 2027-01-14 | 2027-01-14
Store | 1.1.1.3 | Web Front End | Task | 0 | Soumy | 0 | 0 | 2027-01-14 | 2027-01-14
Store | 1.1.2 | US-02: Configure Consignment Material Owner Master | User Story | 5 |  |  |  | 2027-01-14 | 2027-01-14
Store | 1.1.2.1 | Database | Task | 1 | Inderjeet | 2 | 3 | 2027-01-14 | 2027-01-14
Store | 1.1.2.2 | Backend API | Task | 2 | Ronak | 4 | 6 | 2027-01-14 | 2027-01-14
Store | 1.1.2.3 | Web Front End | Task | 2 | Soumy | 0 | 2 | 2027-01-14 | 2027-01-14
Store | 1.1.3 | US-03: Sync D365 Master Data (Item, Item on Hand, Activity, Equipment) | User Story | 0 |  |  |  | 2027-01-14 | 2027-01-14
Store | 1.1.3.1 | Database | Task | 0 | Inderjeet | 3 | 3 | 2027-01-14 | 2027-01-14
Store | 1.1.3.2 | Backend API | Task | 0 | Ronak | 6 | 6 | 2027-01-14 | 2027-01-14
Store | 1.1.3.3 | Web Front End | Task | 0 | Soumy | 2 | 2 | 2027-01-14 | 2027-01-14
Store | 1.1.4 | US-04: Configure Store Behaviour per Project | User Story | 7 |  |  |  | 2027-01-14 | 2027-01-15
Store | 1.1.4.1 | Database | Task | 1 | Inderjeet | 3 | 4 | 2027-01-14 | 2027-01-14
Store | 1.1.4.2 | Backend API | Task | 3 | Ronak | 6 | 9 | 2027-01-14 | 2027-01-15
Store | 1.1.4.3 | Web Front End | Task | 3 | Soumy | 2 | 5 | 2027-01-14 | 2027-01-14
Store | 1.2 | Epic 2: Gate Pass — Creation & Approval | Epic | 53 |  |  |  | 2027-01-14 | 2027-01-19
Store | 1.2.1 | US-05: Store In-Charge Creates Direct Gate Pass with Auto-Generated Number (Path A) | User Story | 17 |  |  |  | 2027-01-14 | 2027-01-15
Store | 1.2.1.1 | Database | Task | 4 | Inderjeet | 4 | 8 | 2027-01-14 | 2027-01-15
Store | 1.2.1.2 | Backend API | Task | 5 | Ronak | 9 | 14 | 2027-01-15 | 2027-01-15
Store | 1.2.1.3 | Web Front End | Task | 4 | Soumy | 5 | 9 | 2027-01-14 | 2027-01-15
Store | 1.2.1.4 | Mobile | Task | 4 | Hardik | 0 | 4 | 2027-01-14 | 2027-01-14
Store | 1.2.2 | US-06: Add Multiple Line Items of Mixed Types on One Gate Pass | User Story | 0 |  |  |  | 2027-01-14 | 2027-01-18
Store | 1.2.2.1 | Database | Task | 0 | Inderjeet | 8 | 8 | 2027-01-15 | 2027-01-15
Store | 1.2.2.2 | Backend API | Task | 0 | Ronak | 14 | 14 | 2027-01-18 | 2027-01-18
Store | 1.2.2.3 | Web Front End | Task | 0 | Soumy | 9 | 9 | 2027-01-15 | 2027-01-15
Store | 1.2.2.4 | Mobile | Task | 0 | Hardik | 4 | 4 | 2027-01-14 | 2027-01-14
Store | 1.2.3 | US-07: Guided 3-Step Creation Wizard with Field Validations | User Story | 8 |  |  |  | 2027-01-14 | 2027-01-18
Store | 1.2.3.2 | Backend API | Task | 2 | Ronak | 14 | 16 | 2027-01-18 | 2027-01-18
Store | 1.2.3.3 | Web Front End | Task | 3 | Soumy | 9 | 12 | 2027-01-15 | 2027-01-15
Store | 1.2.3.4 | Mobile | Task | 3 | Hardik | 4 | 7 | 2027-01-14 | 2027-01-14
Store | 1.2.4 | US-08: P&M In-Charge Requests SR-Linked Gate Pass from SR Screen (Path B) | User Story | 0 |  |  |  | 2027-01-15 | 2027-01-18
Store | 1.2.4.1 | Database | Task | 0 | Inderjeet | 8 | 8 | 2027-01-15 | 2027-01-15
Store | 1.2.4.2 | Backend API | Task | 0 | Ronak | 16 | 16 | 2027-01-18 | 2027-01-18
Store | 1.2.4.3 | Web Front End | Task | 0 | Soumy | 12 | 12 | 2027-01-15 | 2027-01-15
Store | 1.2.4.4 | Mobile | Task | 0 | Hardik | 7 | 7 | 2027-01-15 | 2027-01-15
Store | 1.2.5 | US-09: Store Approves or Rejects SR-Linked Gate Pass Request | User Story | 6 |  |  |  | 2027-01-15 | 2027-01-18
Store | 1.2.5.2 | Backend API | Task | 2 | Ronak | 16 | 18 | 2027-01-18 | 2027-01-18
Store | 1.2.5.3 | Web Front End | Task | 2 | Soumy | 12 | 14 | 2027-01-15 | 2027-01-15
Store | 1.2.5.4 | Mobile | Task | 2 | Hardik | 7 | 9 | 2027-01-15 | 2027-01-15
Store | 1.2.6 | US-10: Two-Level Approval Workflow (L1 Store In-Charge, L2 Project Manager) | User Story | 13 |  |  |  | 2027-01-15 | 2027-01-19
Store | 1.2.6.1 | Database | Task | 1 | Inderjeet | 8 | 9 | 2027-01-15 | 2027-01-15
Store | 1.2.6.2 | Backend API | Task | 5 | Ronak | 18 | 23 | 2027-01-18 | 2027-01-19
Store | 1.2.6.3 | Web Front End | Task | 4 | Soumy | 14 | 18 | 2027-01-18 | 2027-01-18
Store | 1.2.6.4 | Mobile | Task | 3 | Hardik | 9 | 12 | 2027-01-15 | 2027-01-15
Store | 1.2.7 | US-11: Approval Inbox with Ageing Reminders and Escalation | User Story | 0 |  |  |  | 2027-01-15 | 2027-01-19
Store | 1.2.7.2 | Backend API | Task | 0 | Ronak | 23 | 23 | 2027-01-19 | 2027-01-19
Store | 1.2.7.3 | Web Front End | Task | 0 | Soumy | 18 | 18 | 2027-01-18 | 2027-01-18
Store | 1.2.7.4 | Mobile | Task | 0 | Hardik | 12 | 12 | 2027-01-15 | 2027-01-15
Store | 1.2.8 | US-12: Cancel Gate Pass with Immutable Mandatory Reason | User Story | 5 |  |  |  | 2027-01-15 | 2027-01-19
Store | 1.2.8.2 | Backend API | Task | 2 | Ronak | 23 | 25 | 2027-01-19 | 2027-01-19
Store | 1.2.8.3 | Web Front End | Task | 2 | Soumy | 18 | 20 | 2027-01-18 | 2027-01-18
Store | 1.2.8.4 | Mobile | Task | 1 | Hardik | 12 | 13 | 2027-01-15 | 2027-01-15
Store | 1.2.9 | US-13: Backdated Gate Pass Entry with Mandatory Reason | User Story | 4 |  |  |  | 2027-01-15 | 2027-01-19
Store | 1.2.9.2 | Backend API | Task | 2 | Ronak | 25 | 27 | 2027-01-19 | 2027-01-19
Store | 1.2.9.3 | Web Front End | Task | 1 | Soumy | 20 | 21 | 2027-01-18 | 2027-01-18
Store | 1.2.9.4 | Mobile | Task | 1 | Hardik | 13 | 14 | 2027-01-15 | 2027-01-15
Store | 1.3 | Epic 3: Gate Pass — Movement, Returns & Closure | Epic | 75 |  |  |  | 2027-01-15 | 2027-01-27
Store | 1.3.1 | US-14: Record Departure / Dispatch of Approved Outward Gate Pass | User Story | 9 |  |  |  | 2027-01-15 | 2027-01-20
Store | 1.3.1.1 | Database | Task | 1 | Inderjeet | 9 | 10 | 2027-01-15 | 2027-01-15
Store | 1.3.1.2 | Backend API | Task | 3 | Ronak | 27 | 30 | 2027-01-19 | 2027-01-20
Store | 1.3.1.3 | Web Front End | Task | 3 | Soumy | 21 | 24 | 2027-01-19 | 2027-01-19
Store | 1.3.1.4 | Mobile | Task | 2 | Hardik | 14 | 16 | 2027-01-18 | 2027-01-18
Store | 1.3.2 | US-15: Record Inward Receipt for Inward Gate Passes | User Story | 6 |  |  |  | 2027-01-18 | 2027-01-20
Store | 1.3.2.2 | Backend API | Task | 2 | Ronak | 30 | 32 | 2027-01-20 | 2027-01-20
Store | 1.3.2.3 | Web Front End | Task | 2 | Soumy | 24 | 26 | 2027-01-19 | 2027-01-19
Store | 1.3.2.4 | Mobile | Task | 2 | Hardik | 16 | 18 | 2027-01-18 | 2027-01-18
Store | 1.3.3 | US-16: Record Full and Partial Returns with Per-Line Condition | User Story | 14 |  |  |  | 2027-01-15 | 2027-01-21
Store | 1.3.3.1 | Database | Task | 1 | Inderjeet | 10 | 11 | 2027-01-15 | 2027-01-15
Store | 1.3.3.2 | Backend API | Task | 5 | Ronak | 32 | 37 | 2027-01-20 | 2027-01-21
Store | 1.3.3.3 | Web Front End | Task | 4 | Soumy | 26 | 30 | 2027-01-19 | 2027-01-20
Store | 1.3.3.4 | Mobile | Task | 4 | Hardik | 18 | 22 | 2027-01-18 | 2027-01-19
Store | 1.3.4 | US-17: Raise Quantity Adjustment for Unreturnable Pending Quantity | User Story | 9 |  |  |  | 2027-01-15 | 2027-01-21
Store | 1.3.4.1 | Database | Task | 1 | Inderjeet | 11 | 12 | 2027-01-15 | 2027-01-15
Store | 1.3.4.2 | Backend API | Task | 3 | Ronak | 37 | 40 | 2027-01-21 | 2027-01-21
Store | 1.3.4.3 | Web Front End | Task | 3 | Soumy | 30 | 33 | 2027-01-20 | 2027-01-20
Store | 1.3.4.4 | Mobile | Task | 2 | Hardik | 22 | 24 | 2027-01-19 | 2027-01-19
Store | 1.3.5 | US-18: Approve Adjustment with Segregation of Duties (Different L1 + PM L2) | User Story | 9 |  |  |  | 2027-01-19 | 2027-01-22
Store | 1.3.5.2 | Backend API | Task | 4 | Ronak | 40 | 44 | 2027-01-21 | 2027-01-22
Store | 1.3.5.3 | Web Front End | Task | 3 | Soumy | 33 | 36 | 2027-01-20 | 2027-01-21
Store | 1.3.5.4 | Mobile | Task | 2 | Hardik | 24 | 26 | 2027-01-19 | 2027-01-19
Store | 1.3.6 | US-19: Close Gate Pass at Zero Pending Quantity | User Story | 5 |  |  |  | 2027-01-19 | 2027-01-22
Store | 1.3.6.2 | Backend API | Task | 2 | Ronak | 44 | 46 | 2027-01-22 | 2027-01-22
Store | 1.3.6.3 | Web Front End | Task | 2 | Soumy | 36 | 38 | 2027-01-21 | 2027-01-21
Store | 1.3.6.4 | Mobile | Task | 1 | Hardik | 26 | 27 | 2027-01-19 | 2027-01-19
Store | 1.3.7 | US-20: Track and Alert Overdue Returns | User Story | 8 |  |  |  | 2027-01-19 | 2027-01-25
Store | 1.3.7.2 | Backend API | Task | 4 | Ronak | 46 | 50 | 2027-01-22 | 2027-01-25
Store | 1.3.7.3 | Web Front End | Task | 2 | Soumy | 38 | 40 | 2027-01-21 | 2027-01-21
Store | 1.3.7.4 | Mobile | Task | 2 | Hardik | 27 | 29 | 2027-01-19 | 2027-01-20
Store | 1.3.8 | US-21: Generate Gate Pass PDF Document with Signatures | User Story | 7 |  |  |  | 2027-01-21 | 2027-01-25
Store | 1.3.8.2 | Backend API | Task | 5 | Ronak | 50 | 55 | 2027-01-25 | 2027-01-25
Store | 1.3.8.3 | Web Front End | Task | 2 | Soumy | 40 | 42 | 2027-01-21 | 2027-01-21
Store | 1.3.9 | US-22: Gate Pass List View with Search, Filters and Overdue Flags | User Story | 8 |  |  |  | 2027-01-20 | 2027-01-27
Store | 1.3.9.2 | Backend API | Task | 2 | Ronak | 55 | 57 | 2027-01-25 | 2027-01-27
Store | 1.3.9.3 | Web Front End | Task | 4 | Soumy | 42 | 46 | 2027-01-22 | 2027-01-22
Store | 1.3.9.4 | Mobile | Task | 2 | Hardik | 29 | 31 | 2027-01-20 | 2027-01-20
Store | 1.3.10 | US-23: Offline Gate Pass Creation with Sync on Reconnect | User Story | 0 |  |  |  | 2027-01-20 | 2027-01-27
Store | 1.3.10.2 | Backend API | Task | 0 | Ronak | 57 | 57 | 2027-01-27 | 2027-01-27
Store | 1.3.10.4 | Mobile | Task | 0 | Hardik | 31 | 31 | 2027-01-20 | 2027-01-20
Store | 1.4 | Epic 4: Consignment Material Tracking | Epic | 77 |  |  |  | 2027-01-14 | 2027-01-28
Store | 1.4.1 | US-24: Prompt Consignment Flag on Inward Gate Pass and Auto-Create Consignment Record | User Story | 15 |  |  |  | 2027-01-15 | 2027-01-27
Store | 1.4.1.1 | Database | Task | 4 | Inderjeet | 12 | 16 | 2027-01-15 | 2027-01-18
Store | 1.4.1.2 | Backend API | Task | 5 | Ronak | 57 | 62 | 2027-01-27 | 2027-01-27
Store | 1.4.1.3 | Web Front End | Task | 4 | Soumy | 46 | 50 | 2027-01-22 | 2027-01-25
Store | 1.4.1.4 | Mobile | Task | 2 | Hardik | 31 | 33 | 2027-01-20 | 2027-01-20
Store | 1.4.2 | US-25: Create Consignment Record Manually | User Story | 5 |  |  |  | 2027-01-20 | 2027-01-28
Store | 1.4.2.2 | Backend API | Task | 2 | Ronak | 62 | 64 | 2027-01-27 | 2027-01-28
Store | 1.4.2.3 | Web Front End | Task | 2 | Soumy | 50 | 52 | 2027-01-25 | 2027-01-25
Store | 1.4.2.4 | Mobile | Task | 1 | Hardik | 33 | 34 | 2027-01-20 | 2027-01-20
Store | 1.4.3 | US-26: Record Consignment Consumption with Balance Hard Block | User Story | 13 |  |  |  | 2027-01-14 | 2027-01-25
Store | 1.4.3.1 | Database | Task | 1 | Inderjeet | 16 | 17 | 2027-01-18 | 2027-01-18
Store | 1.4.3.2 | Backend API | Task | 5 | Parth Jani | 0 | 5 | 2027-01-14 | 2027-01-14
Store | 1.4.3.3 | Web Front End | Task | 4 | Soumy | 52 | 56 | 2027-01-25 | 2027-01-25
Store | 1.4.3.4 | Mobile | Task | 3 | Hardik | 34 | 37 | 2027-01-20 | 2027-01-21
Store | 1.4.4 | US-27: Record Return of Unused Consignment Material to Owner | User Story | 10 |  |  |  | 2027-01-14 | 2027-01-19
Store | 1.4.4.1 | Database | Task | 1 | Inderjeet | 17 | 18 | 2027-01-18 | 2027-01-18
Store | 1.4.4.2 | Backend API | Task | 4 | Parth Jani | 5 | 9 | 2027-01-14 | 2027-01-15
Store | 1.4.4.3 | Web Front End | Task | 3 | Inderjeet | 18 | 21 | 2027-01-18 | 2027-01-18
Store | 1.4.4.4 | Mobile | Task | 2 | Inderjeet | 21 | 23 | 2027-01-19 | 2027-01-19
Store | 1.4.5 | US-28: Generate Consignment Return Document PDF with Reconciliation Summary | User Story | 7 |  |  |  | 2027-01-15 | 2027-01-19
Store | 1.4.5.2 | Backend API | Task | 5 | Parth Jani | 9 | 14 | 2027-01-15 | 2027-01-15
Store | 1.4.5.3 | Web Front End | Task | 2 | Inderjeet | 23 | 25 | 2027-01-19 | 2027-01-19
Store | 1.4.6 | US-29: Auto-Derive Consignment Status Across the Lifecycle | User Story | 5 |  |  |  | 2027-01-18 | 2027-01-19
Store | 1.4.6.2 | Backend API | Task | 3 | Parth Jani | 14 | 17 | 2027-01-18 | 2027-01-18
Store | 1.4.6.3 | Web Front End | Task | 1 | Inderjeet | 25 | 26 | 2027-01-19 | 2027-01-19
Store | 1.4.6.4 | Mobile | Task | 1 | Inderjeet | 26 | 27 | 2027-01-19 | 2027-01-19
Store | 1.4.7 | US-30: Flag Client Supplied Balances Nearing Project End | User Story | 5 |  |  |  | 2027-01-18 | 2027-01-20
Store | 1.4.7.2 | Backend API | Task | 2 | Parth Jani | 17 | 19 | 2027-01-18 | 2027-01-18
Store | 1.4.7.3 | Web Front End | Task | 2 | Inderjeet | 27 | 29 | 2027-01-19 | 2027-01-20
Store | 1.4.7.4 | Mobile | Task | 1 | Inderjeet | 29 | 30 | 2027-01-20 | 2027-01-20
Store | 1.4.8 | US-31: Consignment List with Owner-Type and Status Filters | User Story | 7 |  |  |  | 2027-01-18 | 2027-01-20
Store | 1.4.8.2 | Backend API | Task | 2 | Parth Jani | 19 | 21 | 2027-01-18 | 2027-01-18
Store | 1.4.8.3 | Web Front End | Task | 3 | Inderjeet | 30 | 33 | 2027-01-20 | 2027-01-20
Store | 1.4.8.4 | Mobile | Task | 2 | Inderjeet | 33 | 35 | 2027-01-20 | 2027-01-20
Store | 1.4.9 | US-32: Maintain Vendor Sample Register with No Stock Impact | User Story | 10 |  |  |  | 2027-01-19 | 2027-01-21
Store | 1.4.9.1 | Database | Task | 1 | Inderjeet | 35 | 36 | 2027-01-21 | 2027-01-21
Store | 1.4.9.2 | Backend API | Task | 3 | Parth Jani | 21 | 24 | 2027-01-19 | 2027-01-19
Store | 1.4.9.3 | Web Front End | Task | 4 | Inderjeet | 36 | 40 | 2027-01-21 | 2027-01-21
Store | 1.4.9.4 | Mobile | Task | 2 | Inderjeet | 40 | 42 | 2027-01-21 | 2027-01-21
Store | 1.5 | Epic 5: MRIS — Requisition, Approval & Issue | Epic | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.1 | US-33: Raise General Store MRIS with Mandatory Activity Allocation | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.1.1 | Database | Task | 0 | Inderjeet | 42 | 42 | 2027-01-22 | 2027-01-22
Store | 1.5.1.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.1.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.1.4 | Mobile | Task | 0 | Hardik | 37 | 37 | 2027-01-21 | 2027-01-21
Store | 1.5.2 | US-34: Raise SR-Linked Spare Parts MRIS from Within SR | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.2.1 | Database | Task | 0 | Inderjeet | 42 | 42 | 2027-01-22 | 2027-01-22
Store | 1.5.2.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.2.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.2.4 | Mobile | Task | 0 | Hardik | 37 | 37 | 2027-01-21 | 2027-01-21
Store | 1.5.3 | US-35: Raise Fuel MRIS with 4-Party Anti-Theft Workflow | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.3.1 | Database | Task | 0 | Inderjeet | 42 | 42 | 2027-01-22 | 2027-01-22
Store | 1.5.3.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.3.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.3.4 | Mobile | Task | 0 | Hardik | 37 | 37 | 2027-01-21 | 2027-01-21
Store | 1.5.4 | US-36: Flag Fuel Discrepancy Immutably and Notify Management | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.4.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.4.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.4.4 | Mobile | Task | 0 | Hardik | 37 | 37 | 2027-01-21 | 2027-01-21
Store | 1.5.5 | US-37: Approve or Reject MRIS per Entry-Point Approver Configuration | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.5.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.5.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.5.4 | Mobile | Task | 0 | Hardik | 37 | 37 | 2027-01-21 | 2027-01-21
Store | 1.5.6 | US-38: Store Issues MRIS with Real-Time Availability Re-Validation | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.6.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.6.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.6.4 | Mobile | Task | 0 | Hardik | 37 | 37 | 2027-01-21 | 2027-01-21
Store | 1.5.7 | US-39: Partial Fulfilment with Auto-Created Back-Order MRIS | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.7.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.7.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.7.4 | Mobile | Task | 0 | Hardik | 37 | 37 | 2027-01-21 | 2027-01-21
Store | 1.5.8 | US-40: D365 Write-Back on Issue with Silent-Failure Retry Policy | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.8.1 | Database | Task | 0 | Inderjeet | 42 | 42 | 2027-01-22 | 2027-01-22
Store | 1.5.8.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.8.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.9 | US-41: Daily D365 Reconciliation Report | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.9.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.9.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.10 | US-42: Auto-Cancel Open MRIS on Equipment Transfer (ECR) Completion | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.10.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.10.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.11 | US-43: Auto-Generate PPE MRIS from Safety Module Issuance | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.11.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.11.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.12 | US-44: MRIS Queue with Entry-Point, Status and Project Filters | User Story | 0 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.5.12.2 | Backend API | Task | 0 | Parth Jani | 24 | 24 | 2027-01-19 | 2027-01-19
Store | 1.5.12.3 | Web Front End | Task | 0 | Soumy | 56 | 56 | 2027-01-27 | 2027-01-27
Store | 1.5.12.4 | Mobile | Task | 0 | Hardik | 37 | 37 | 2027-01-21 | 2027-01-21
Store | 1.6 | Epic 6: Store Dashboard & Reports | Epic | 42 |  |  |  | 2027-01-19 | 2027-01-27
Store | 1.6.1 | US-45: Store Dashboard KPI Cards Across All Features | User Story | 14 |  |  |  | 2027-01-19 | 2027-01-22
Store | 1.6.1.1 | Database | Task | 1 | Inderjeet | 42 | 43 | 2027-01-22 | 2027-01-22
Store | 1.6.1.2 | Backend API | Task | 5 | Parth Jani | 24 | 29 | 2027-01-19 | 2027-01-20
Store | 1.6.1.3 | Web Front End | Task | 5 | Inderjeet | 43 | 48 | 2027-01-22 | 2027-01-22
Store | 1.6.1.4 | Mobile | Task | 3 | Hardik | 37 | 40 | 2027-01-21 | 2027-01-21
Store | 1.6.2 | US-46: Dashboard Active Queues (MRIS, Gate Pass, Overdue, Consignment) | User Story | 9 |  |  |  | 2027-01-20 | 2027-01-25
Store | 1.6.2.2 | Backend API | Task | 3 | Parth Jani | 29 | 32 | 2027-01-20 | 2027-01-20
Store | 1.6.2.3 | Web Front End | Task | 4 | Inderjeet | 48 | 52 | 2027-01-22 | 2027-01-25
Store | 1.6.2.4 | Mobile | Task | 2 | Hardik | 40 | 42 | 2027-01-21 | 2027-01-21
Store | 1.6.3 | US-47: Dashboard Summary Panels (Gate Activity, MRIS Mix, D365 Status) | User Story | 4 |  |  |  | 2027-01-20 | 2027-01-25
Store | 1.6.3.2 | Backend API | Task | 2 | Parth Jani | 32 | 34 | 2027-01-20 | 2027-01-20
Store | 1.6.3.3 | Web Front End | Task | 2 | Inderjeet | 52 | 54 | 2027-01-25 | 2027-01-25
Store | 1.6.4 | US-48: Management Summary View for PM and P&M HOD | User Story | 7 |  |  |  | 2027-01-20 | 2027-01-27
Store | 1.6.4.2 | Backend API | Task | 3 | Parth Jani | 34 | 37 | 2027-01-20 | 2027-01-21
Store | 1.6.4.3 | Web Front End | Task | 4 | Inderjeet | 54 | 58 | 2027-01-25 | 2027-01-27
Store | 1.6.5 | US-49: Gate Pass Reports & Analytics with Export | User Story | 8 |  |  |  | 2027-01-21 | 2027-01-27
Store | 1.6.5.2 | Backend API | Task | 4 | Parth Jani | 37 | 41 | 2027-01-21 | 2027-01-21
Store | 1.6.5.3 | Web Front End | Task | 4 | Inderjeet | 58 | 62 | 2027-01-27 | 2027-01-27
Store | 1.7 | Epic 7: Roles, Notifications, Integrations & NFRs | Epic | 21 |  |  |  | 2027-01-21 | 2027-01-28
Store | 1.7.1 | US-50: Enforce Store vs P&M Role Boundaries and Project Scope | User Story | 0 |  |  |  | 2027-01-21 | 2027-01-27
Store | 1.7.1.1 | Database | Task | 0 | Inderjeet | 62 | 62 | 2027-01-27 | 2027-01-27
Store | 1.7.1.2 | Backend API | Task | 0 | Parth Jani | 41 | 41 | 2027-01-21 | 2027-01-21
Store | 1.7.1.3 | Web Front End | Task | 0 | Inderjeet | 62 | 62 | 2027-01-27 | 2027-01-27
Store | 1.7.1.4 | Mobile | Task | 0 | Hardik | 42 | 42 | 2027-01-22 | 2027-01-22
Store | 1.7.2 | US-51: Deliver Store Notification Matrix N-01 to N-13 Across Channels | User Story | 8 |  |  |  | 2027-01-21 | 2027-01-28
Store | 1.7.2.1 | Database | Task | 1 | Inderjeet | 62 | 63 | 2027-01-27 | 2027-01-27
Store | 1.7.2.2 | Backend API | Task | 5 | Parth Jani | 41 | 46 | 2027-01-21 | 2027-01-22
Store | 1.7.2.3 | Web Front End | Task | 1 | Inderjeet | 63 | 64 | 2027-01-28 | 2027-01-28
Store | 1.7.2.4 | Mobile | Task | 1 | Hardik | 42 | 43 | 2027-01-22 | 2027-01-22
Store | 1.7.3 | US-52: Immutable Records, No Hard Deletes, and Complete Audit Trail | User Story | 6 |  |  |  | 2027-01-22 | 2027-01-28
Store | 1.7.3.1 | Database | Task | 1 | Inderjeet | 64 | 65 | 2027-01-28 | 2027-01-28
Store | 1.7.3.2 | Backend API | Task | 4 | Parth Jani | 46 | 50 | 2027-01-22 | 2027-01-25
Store | 1.7.3.3 | Web Front End | Task | 1 | Inderjeet | 65 | 66 | 2027-01-28 | 2027-01-28
Store | 1.7.4 | US-53: Meet Store Module Performance and Responsiveness Targets | User Story | 7 |  |  |  | 2027-01-22 | 2027-01-28
Store | 1.7.4.2 | Backend API | Task | 3 | Parth Jani | 50 | 53 | 2027-01-25 | 2027-01-25
Store | 1.7.4.3 | Web Front End | Task | 2 | Inderjeet | 66 | 68 | 2027-01-28 | 2027-01-28
Store | 1.7.4.4 | Mobile | Task | 2 | Hardik | 43 | 45 | 2027-01-22 | 2027-01-22
Formulas:
Start Date = MIN([Start Date, row below]:I222)
Start Date = WORKDAY(Settings!$D10,INT([Start Hr]/HoursPerDay)+1,Holidays)
End Date = MAX([End Date, row below]:J222)
End Date = IF([Estimated Hours]=0,[Start Date],WORKDAY(Settings!$D10,ROUNDUP([End Hr]/HoursPerDay,0),Holidays))

## Summary
Module-wise Schedule (modules sequential, 3 working-day buffer between modules)
Module | Total Hours | Working Days | Start Date | End Date
Execution | 564 | 22 | 2026-07-16 | 2026-08-14
Admin | 400 | 16 | 2026-08-26 | 2026-09-16
Safety | 558 | 23 | 2026-09-28 | 2026-10-29
P&M | 1045 | 39 | 2026-11-10 | 2027-01-04
Store | 286 | 10 | 2027-01-14 | 2027-01-28
TOTAL | 2853 | 138 | 2026-07-16 | 2027-01-28
Developer-wise Hours by Module (developers work in parallel)
Developer | Execution | Admin | Safety | P&M | Store | Total Hours | First Task Start | Last Task End
Parth Jani | 150 | 79 | 110 | 262 | 53 | 654 | 2026-07-16 | 2027-01-25
Ronak | 144 | 111 | 151 | 200 | 64 | 670 | 2026-07-16 | 2027-01-28
Soumy | 147 | 100 | 138 | 268 | 56 | 709 | 2026-07-16 | 2027-01-25
Hardik | 123 | 110 | 159 | 248 | 45 | 685 | 2026-07-16 | 2027-01-22
Inderjeet | 0 | 0 | 0 | 67 | 68 | 135 | 2026-11-10 | 2027-01-28
TOTAL | 564 | 400 | 558 | 1045 | 286 | 2853
Formulas:
Working Days = NETWORKDAYS([Start Date],[End Date],Holidays)
Start Date = MIN(D3:[Start Date, row above])
End Date = MAX(E3:[End Date, row above])