## Sheet1
Type | Task
Row Labels | Sum of Estimated Hours
Hardik | 123
Parth Jani | 150
Ronak | 144
Soumy | 147
Grand Total | 564

## WBS
WBS ID | Task Name | Type | Estimated Hours | Developer
1 | HIMAPP 2.0 — SITE EXECUTION MODULE — Implementation | Project
1.1 | Epic 1: Manpower & Labour Deployment (AM Entry) | Epic | 40
1.1.1 | US-01: Field Engineer Logs Morning Manpower Deployment | User Story | 20 | Developer
1.1.1.1 | Database | Task | 3 | Ronak
1.1.1.2 | Backend API | Task | 6 | Ronak
1.1.1.3 | Web Front End | Task | 5 | Soumy
1.1.1.4 | Mobile | Task | 6 | Hardik
1.1.2 | US-02: System Carries Saved Manpower Forward into Daily DPR | User Story | 10 | Developer
1.1.2.1 | Database | Task | 2 | Ronak
1.1.2.2 | Backend API | Task | 3 | Ronak
1.1.2.3 | Web Front End | Task | 3 | Soumy
1.1.2.4 | Mobile | Task | 2 | Hardik
1.1.3 | US-03: Add, Tag, and Remove Contractors with Work Category | User Story | 10 | Developer
1.1.3.1 | Database | Task | 2 | Ronak
1.1.3.2 | Backend API | Task | 3 | Ronak
1.1.3.3 | Web Front End | Task | 3 | Soumy
1.1.3.4 | Mobile | Task | 2 | Hardik
1.2 | Epic 2: Site DPR & Project DPR Consolidation | Epic | 124
1.2.1 | US-04: Engineer Records Per-Section Activity Quantities Against Plan | User Story | 14 | Developer
1.2.1.1 | Database | Task | 2 | Parth Jani
1.2.1.2 | Backend API | Task | 3 | Parth Jani
1.2.1.3 | Web Front End | Task | 4 | Soumy
1.2.1.4 | Mobile | Task | 5 | Hardik
1.2.2 | US-05: QS Enters Quantities via Cross-Section Quantity Matrix | User Story | 13 | Developer
1.2.2.1 | Database | Task | 2 | Parth Jani
1.2.2.2 | Backend API | Task | 4 | Parth Jani
1.2.2.3 | Web Front End | Task | 4 | Soumy
1.2.2.4 | Mobile | Task | 3 | Hardik
1.2.3 | US-06: Bulk Quantity Entry via Excel Template Upload | User Story | 12 | Developer
1.2.3.1 | Database | Task | 1 | Parth Jani
1.2.3.2 | Backend API | Task | 6 | Parth Jani
1.2.3.3 | Web Front End | Task | 5 | Soumy
1.2.4 | US-07: Capture Hindrances with Auto-Classification | User Story | 12 | Developer
1.2.4.1 | Database | Task | 1 | Parth Jani
1.2.4.2 | Backend API | Task | 4 | Parth Jani
1.2.4.3 | Web Front End | Task | 4 | Soumy
1.2.4.4 | Mobile | Task | 3 | Hardik
1.2.5 | US-08: Capture GPS Tag and Site Photo for Daily Record | User Story | 12 | Developer
1.2.5.1 | Database | Task | 1 | Parth Jani
1.2.5.2 | Backend API | Task | 3 | Parth Jani
1.2.5.3 | Web Front End | Task | 2 | Soumy
1.2.5.4 | Mobile | Task | 6 | Hardik
1.2.6 | US-09: Capture Tomorrow's Plan Note | User Story | 6 | Developer
1.2.6.1 | Database | Task | 1 | Parth Jani
1.2.6.2 | Backend API | Task | 2 | Parth Jani
1.2.6.3 | Web Front End | Task | 2 | Soumy
1.2.6.4 | Mobile | Task | 1 | Hardik
1.2.7 | US-10: System Calculates DPR Completion % from Required Inputs | User Story | 7 | Developer
1.2.7.2 | Backend API | Task | 2 | Parth Jani
1.2.7.3 | Web Front End | Task | 2 | Soumy
1.2.7.4 | Mobile | Task | 3 | Hardik
1.2.8 | US-11: Engineer Submits DPR for Manager Approval | User Story | 11 | Developer
1.2.8.2 | Backend API | Task | 4 | Parth Jani
1.2.8.3 | Web Front End | Task | 4 | Soumy
1.2.8.4 | Mobile | Task | 3 | Hardik
1.2.9 | US-12: Manager Approves or Reopens Submitted DPR | User Story | 11 | Developer
1.2.9.2 | Backend API | Task | 3 | Parth Jani
1.2.9.3 | Mobile | Task | 4 | Hardik
1.2.9.3 | Web Front End | Task | 4 | Soumy
1.2.10 | US-13: Share DPR via WhatsApp and Export as PDF | User Story | 11 | Developer
1.2.10.1 | Database | Task | 1 | Parth Jani
1.2.10.2 | Backend API | Task | 3 | Parth Jani
1.2.10.3 | Web Front End | Task | 3 | Soumy
1.2.10.4 | Mobile | Task | 4 | Hardik
1.2.11 | US-14: QS Views Consolidated Project DPR Across All Areas | User Story | 15 | Developer
1.2.11.1 | Database | Task | 3 | Parth Jani
1.2.11.2 | Backend API | Task | 4 | Parth Jani
1.2.11.3 | Mobile | Task | 4 | Hardik
1.2.11.3 | Web Front End | Task | 4 | Soumy
1.3 | Epic 3: Daily Labour Slip (DDLS) | Epic | 76
1.3.1 | US-15: User Creates a Daily Labour Slip with Auto-Priced Lines | User Story | 20 | Developer
1.3.1.1 | Database | Task | 2 | Ronak
1.3.1.2 | Backend API | Task | 4 | Ronak
1.3.1.3 | Web Front End | Task | 6 | Soumy
1.3.1.4 | Mobile | Task | 8 | Hardik
1.3.2 | US-16: System Derives Work Hours, Mandays and Flags Over-Limit Lines | User Story | 0 | Developer
1.3.2.2 | Backend API | Task | 0 | Ronak
1.3.2.3 | Web Front End | Task | 0 | Soumy
1.3.3 | US-17: Require Lumpsum or Exception Justification on Flagged Lines | User Story | 10 | Developer
1.3.3.2 | Backend API | Task | 3 | Ronak
1.3.3.3 | Web Front End | Task | 3 | Soumy
1.3.3.4 | Mobile | Task | 4 | Hardik
1.3.4 | US-18: Bulk Import Labour Slip Lines via Excel | User Story | 12 | Developer
1.3.4.2 | Backend API | Task | 8 | Ronak
1.3.4.3 | Web Front End | Task | 4 | Soumy
1.3.5 | US-19: Save Draft and Submit Slip for Approval | User Story | 12 | Developer
1.3.5.2 | Backend API | Task | 3 | Ronak
1.3.5.3 | Web Front End | Task | 3 | Soumy
1.3.5.4 | Mobile | Task | 6 | Hardik
1.3.6 | US-20: User Views, Edits, and Resubmits Slips from My Submissions | User Story | 10 | Developer
1.3.6.1 | Database | Task | 2 | Ronak
1.3.6.2 | Backend API | Task | 3 | Ronak
1.3.6.3 | Web Front End | Task | 3 | Soumy
1.3.6.4 | Mobile | Task | 2 | Hardik
1.3.7 | US-21: Maintain a Project-Wide Labour Slip Feed | User Story | 12 | Developer
1.3.7.1 | Mobile | Task | 4 | Ronak
1.3.7.2 | Backend API | Task | 4 | Ronak
1.3.7.3 | Web Front End | Task | 4 | Soumy
1.4 | Epic 4: Approvals & Cost Intelligence | Epic | 71
1.4.1 | US-22: Approver Reviews Pending Slip Queue | User Story | 13 | Developer
1.4.1.1 | Database | Task | 2 | Parth Jani
1.4.1.2 | Backend API | Task | 6 | Parth Jani
1.4.1.3 | Web Front End | Task | 5 | Soumy
1.4.2 | US-23: System Surfaces Approval Intelligence: Mandays and Rate Variance vs History | User Story | 18 | Developer
1.4.2.1 | Database | Task | 6 | Parth Jani
1.4.2.2 | Backend API | Task | 6 | Parth Jani
1.4.2.3 | Web Front End | Task | 6 | Soumy
1.4.3 | US-24: System Flags Duplicate Slip Submission | User Story | 8 | Developer
1.4.3.2 | Backend API | Task | 2 | Parth Jani
1.4.3.3 | Mobile | Task | 4 | Hardik
1.4.3.3 | Web Front End | Task | 2 | Soumy
1.4.4 | US-25: System Flags Slips Exceeding the Cost Threshold | User Story | 12 | Developer
1.4.4.1 | Database | Task | 2 | Parth Jani
1.4.4.2 | Backend API | Task | 3 | Parth Jani
1.4.4.3 | Web Front End | Task | 3 | Soumy
1.4.4.4 | Mobile | Task | 4 | Hardik
1.4.5 | US-26: Approver Approves a Slip | User Story | 10 | Developer
1.4.5.1 | Database | Task | 2 | Parth Jani
1.4.5.2 | Backend API | Task | 4 | Parth Jani
1.4.5.3 | Web Front End | Task | 4 | Soumy
1.4.6 | US-27: Approver Rejects a Slip with Mandatory Reason and Remark | User Story | 10 | Developer
1.4.6.1 | Database | Task | 2 | Parth Jani
1.4.6.2 | Backend API | Task | 4 | Parth Jani
1.4.6.3 | Web Front End | Task | 4 | Soumy
1.5 | Epic 5: D365 Reconciliation & Billing | Epic | 25
1.5.1 | US-28: Finance Books Approved Slips to D365 | User Story | 0 | Developer
1.5.1.1 | Database | Task | 0 | Ronak
1.5.1.2 | Backend API | Task | 0 | Ronak
1.5.1.3 | Web Front End | Task | 0 | Soumy
1.5.2 | US-29: System Tracks Approved vs Booked vs Pending Reconciliation Totals | User Story | 5 | Developer
1.5.2.1 | Database | Task | 1 | Ronak
1.5.2.2 | Backend API | Task | 2 | Ronak
1.5.2.3 | Web Front End | Task | 2 | Soumy
1.5.3 | US-30: Generate Billing Register of Approved Slips | User Story | 15 | Developer
1.5.3.1 | Database | Task | 4 | Ronak
1.5.3.2 | Backend API | Task | 6 | Ronak
1.5.3.3 | Web Front End | Task | 5 | Soumy
1.5.4 | US-31: Export Reconciliation and Billing Data to PDF | User Story | 5 | Developer
1.5.4.1 | Database | Task | 1 | Ronak
1.5.4.2 | Backend API | Task | 2 | Ronak
1.5.4.3 | Web Front End | Task | 2 | Soumy
1.6 | Epic 6: Planning & Targets | Epic | 40
1.6.1 | US-32: QS Defines Planning Period and Daily Targets per Area | User Story | 15 | Developer
1.6.1.1 | Database | Task | 4 | Parth Jani
1.6.1.2 | Backend API | Task | 6 | Parth Jani
1.6.1.3 | Web Front End | Task | 5 | Soumy
1.6.2 | US-33: QS Marks Applicable Activities per Section | User Story | 10 | Developer
1.6.2.1 | Database | Task | 2 | Parth Jani
1.6.2.2 | Backend API | Task | 4 | Parth Jani
1.6.2.3 | Web Front End | Task | 4 | Soumy
1.6.3 | US-34: QS Attaches Drawings or BOQ to the Plan | User Story | 10 | Developer
1.6.3.1 | Database | Task | 2 | Parth Jani
1.6.3.2 | Backend API | Task | 4 | Parth Jani
1.6.3.3 | Web Front End | Task | 4 | Soumy
1.6.4 | US-35: Reset Plan to Defaults or Copy Default Targets | User Story | 5 | Developer
1.6.4.1 | Database | Task | 1 | Parth Jani
1.6.4.2 | Backend API | Task | 2 | Parth Jani
1.6.4.3 | Web Front End | Task | 2 | Soumy
1.7 | Epic 7: Rate Master & Validation Configuration | Epic | 32
1.7.1 | US-36: ERP Support Configures Indicative Trade Rates per Project | User Story | 17 | Developer
1.7.1.1 | Database | Task | 6 | Ronak
1.7.1.2 | Backend API | Task | 6 | Ronak
1.7.1.3 | Web Front End | Task | 5 | Soumy
1.7.2 | US-37: ERP Support Configures Max Working Hours/Day Validation Cap | User Story | 10 | Developer
1.7.2.1 | Database | Task | 2 | Ronak
1.7.2.2 | Backend API | Task | 4 | Ronak
1.7.2.3 | Web Front End | Task | 4 | Soumy
1.7.3 | US-38: Reset Project Rates to Company Master Defaults | User Story | 5 | Developer
1.7.3.1 | Database | Task | 1 | Ronak
1.7.3.2 | Backend API | Task | 2 | Ronak
1.7.3.3 | Web Front End | Task | 2 | Soumy
1.8 | Epic 8: Central Control — Portfolio, Provisioning, Masters & Guardrails | Epic | 94
1.8.1 | US-39: Central QS Views Portfolio Status Across All Projects | User Story | 19 | Developer
1.8.1.1 | Database | Task | 6 | Ronak
1.8.1.2 | Backend API | Task | 6 | Parth Jani
1.8.1.3 | Web Front End | Task | 7 | Hardik
1.8.2 | US-40: Central QS Launches a New Project and Assigns a QS | User Story | 15 | Developer
1.8.2.1 | Database | Task | 4 | Ronak
1.8.2.2 | Backend API | Task | 6 | Parth Jani
1.8.2.3 | Web Front End | Task | 5 | Hardik
1.8.3 | US-41: QS Completes On-Site Setup Steps for a Provisioned Project | User Story | 15 | Developer
1.8.3.1 | Database | Task | 4 | Ronak
1.8.3.2 | Backend API | Task | 6 | Parth Jani
1.8.3.3 | Web Front End | Task | 5 | Hardik
1.8.4 | US-42: Central QS Configures Company-Wide Rate and Activity Masters | User Story | 15 | Developer
1.8.4.1 | Database | Task | 4 | Ronak
1.8.4.2 | Backend API | Task | 6 | Parth Jani
1.8.4.3 | Web Front End | Task | 5 | Hardik
1.8.5 | US-43: Central QS Configures Per-Project QS Guardrails | User Story | 15 | Developer
1.8.5.1 | Database | Task | 4 | Ronak
1.8.5.2 | Backend API | Task | 6 | Parth Jani
1.8.5.3 | Web Front End | Task | 5 | Hardik
1.8.6 | US-44: View Company-Wide Billing Roll-up by Region and Project | User Story | 15 | Developer
1.8.6.1 | Database | Task | 4 | Ronak
1.8.6.2 | Backend API | Task | 6 | Parth Jani
1.8.6.3 | Web Front End | Task | 5 | Hardik
1.8.7 | US-45: Enforce Role-Based Navigation and Access Across Site Execution Roles | User Story | 0 | Developer
1.8.7.1 | Database | Task | 0 | Ronak
1.8.7.2 | Backend API | Task | 0 | Parth Jani
1.8.7.3 | Web Front End | Task | 0 | Hardik
1.9 | Epic 9: Dashboard & Reporting | Epic | 62
1.9.1 | US-46: Site Manager Views Site Command Dashboard KPIs | User Story | 20 | Developer
1.9.1.1 | Database | Task | 4 | Ronak
1.9.1.2 | Backend API | Task | 6 | Ronak
1.9.1.3 | Mobile | Task | 5 | Hardik
1.9.1.3 | Web Front End | Task | 5 | Soumy
1.9.2 | US-47: Dashboard Shows 7-Day Labour Cost Trend and Area Progress | User Story | 15 | Developer
1.9.2.1 | Database | Task | 2 | Ronak
1.9.2.2 | Backend API | Task | 4 | Ronak
1.9.2.3 | Mobile | Task | 5 | Hardik
1.9.2.3 | Web Front End | Task | 4 | Soumy
1.9.3 | US-48: Dashboard Highlights Top Contractors by Approved Value | User Story | 7 | Developer
1.9.3.1 | Database | Task | 1 | Ronak
1.9.3.2 | Backend API | Task | 2 | Ronak
1.9.3.3 | Mobile | Task | 2 | Hardik
1.9.3.3 | Web Front End | Task | 2 | Soumy
1.9.4 | US-49: Maintain Offline-Safe Local Save with Synced Status Indicator | User Story | 20 | Developer
1.9.4.1 | Database | Task | 4 | Ronak
1.9.4.2 | Backend API | Task | 6 | Ronak
1.9.4.3 | Mobile | Task | 5 | Hardik
1.9.4.3 | Web Front End | Task | 5 | Soumy

## Epic Timeline
WBS ID | Task Name | Estimated Hours | Days
1.1 | Epic 1: Manpower & Labour Deployment (AM Entry) | 40 | 6.6667
1.2 | Epic 2: Site DPR & Project DPR Consolidation | 125 | 20.8333 | Row Labels | Estimated Hours | Days
1.3 | Epic 3: Daily Labour Slip (DDLS) | 69 | 11.5 | Hardik | 123 | 20.5
1.4 | Epic 4: Approvals & Cost Intelligence | 67 | 11.1667 | Parth Jani | 150 | 25
1.5 | Epic 5: D365 Reconciliation & Billing | 40 | 6.6667 | Ronak | 144 | 24
1.6 | Epic 6: Planning & Targets | 40 | 6.6667 | Soumy | 147 | 24.5
1.7 | Epic 7: Rate Master & Validation Configuration | 28 | 4.6667 | Grand Total | 564 | 25
1.8 | Epic 8: Central Control — Portfolio, Provisioning, Masters & Guardrails | 94 | 15.6667
1.9 | Epic 9: Dashboard & Reporting | 62 | 10.3333
| Total | 565 | 94.1667