## Sheet1
Type | Task
Row Labels | Sum of Estimated Hours | Estimation Days
Hardik | 248 | 35.4286
Parth | 262 | 37.4286
Ronak | 200 | 28.5714
Soumy | 268 | 38.2857
Inderjeet | 67 | 9.5714
Grand Total | 1045 | 38.2857

## WBS
WBS ID | Task Name | Type | Estimated Hours | Developer
1 | HIMAPP 2.0 — PLANT & MACHINERY (PM) MODULE — Implementation | Project | 1045
1.1 | Epic 1: Equipment Management | Epic | 176
1.1.1 | PNM-001: Sync Equipment Master from D365 | User Story | 15 | Developer
1.1.1.1 | Database | Task | 3 | Parth
1.1.1.2 | Backend API | Task | 6 | Parth
1.1.1.3 | Web Front End | Task | 6 | Soumy
1.1.2 | PNM-002: View Equipment List (Equipment 360) | User Story | 12 | Developer
1.1.2.1 | Backend API | Task | 6 | Parth
1.1.2.2 | Web Front End | Task | 6 | Soumy
1.1.3 | PNM-003: Search Equipment | User Story | 8 | Developer
1.1.3.1 | Backend API | Task | 4 | Parth
1.1.3.2 | Web Front End | Task | 4 | Soumy
1.1.4 | PNM-004: View Equipment Detail — Overview Tab | User Story | 8 | Developer
1.1.4.1 | Backend API | Task | 4 | Parth
1.1.4.2 | Web Front End | Task | 4 | Soumy
1.1.5 | PNM-005: View Equipment Lifecycle History | User Story | 8 | Developer
1.1.5.1 | Backend API | Task | 4 | Parth
1.1.5.2 | Web Front End | Task | 4 | Soumy
1.1.6 | PNM-006: Assign Equipment to Project (Initial Assignment) | User Story | 10 | Developer
1.1.6.1 | Database | Task | 2 | Parth
1.1.6.2 | Backend API | Task | 4 | Parth
1.1.6.3 | Web Front End | Task | 4 | Soumy
1.1.7 | PNM-008: Raise Equipment Condition Report (ECR) — Sender | User Story | 15 | Developer
1.1.7.1 | Database | Task | 3 | Parth
1.1.7.2 | Backend API | Task | 6 | Parth
1.1.7.3 | Web Front End | Task | 6 | Inderjeet
1.1.8 | PNM-009: Auto-Cancel Open Spare MRIS on Transfer Completion | User Story | 10 | Developer
1.1.8.1 | Database | Task | 2 | Parth
1.1.8.2 | Backend API | Task | 4 | Parth
1.1.8.3 | Web Front End | Task | 4 | Soumy
1.1.9 | PNM-010: Acknowledge Incoming Equipment — Receiver ECR | User Story | 15 | Developer
1.1.9.1 | Database | Task | 3 | Parth
1.1.9.2 | Backend API | Task | 6 | Parth
1.1.9.3 | Web Front End | Task | 6 | Inderjeet
1.1.10 | PNM-011: Auto-Complete Equipment Transfer | User Story | 10 | Developer
1.1.10.1 | Database | Task | 2 | Parth
1.1.10.2 | Backend API | Task | 4 | Parth
1.1.10.3 | Web Front End | Task | 4 | Soumy
1.1.11 | PNM-012: Resolve ECR Dispute | User Story | 10 | Developer
1.1.11.1 | Database | Task | 2 | Parth
1.1.11.2 | Backend API | Task | 4 | Parth
1.1.11.3 | Web Front End | Task | 4 | Soumy
1.1.12 | PNM-013: View Transfers (ECR) List | User Story | 8 | Developer
1.1.12.1 | Backend API | Task | 4 | Ronak
1.1.12.2 | Web Front End | Task | 4 | Soumy
1.1.13 | PNM-014: Raise Gate Pass for Off-Site Repair | User Story | 15 | Developer
1.1.13.1 | Database | Task | 3 | Parth
1.1.13.2 | Backend API | Task | 6 | Parth
1.1.13.3 | Web Front End | Task | 6 | Inderjeet
1.1.14 | PNM-015: Record Gate Pass Return | User Story | 10 | Developer
1.1.14.1 | Database | Task | 2 | Parth
1.1.14.2 | Backend API | Task | 4 | Parth
1.1.14.3 | Web Front End | Task | 4 | Soumy
1.1.15 | PNM-016: Record Meter Replacement | User Story | 10 | Developer
1.1.15.1 | Database | Task | 2 | Parth
1.1.15.2 | Backend API | Task | 4 | Parth
1.1.15.3 | Web Front End | Task | 4 | Inderjeet
1.1.16 | PNM-017: View Equipment Availability / Dashboard Widgets | User Story | 12 | Developer
1.1.16.1 | Backend API | Task | 4 | Ronak
1.1.16.2 | Web Front End | Task | 4 | Soumy
1.1.16.3 | Mobile | Task | 4 | Hardik
1.2 | Epic 2: Daily Equipment Checklist | Epic | 76
1.2.1 | PNM-018: Configure Checklist Template per Equipment Category | User Story | 15 | Developer
1.2.1.1 | Database | Task | 2 | Parth
1.2.1.2 | Backend API | Task | 4 | Parth
1.2.1.3 | Web Front End | Task | 5 | Inderjeet
1.2.1.4 | Mobile | Task | 4 | Hardik
1.2.2 | PNM-019: Submit Daily Equipment Checklist | User Story | 21 | Developer
1.2.2.1 | Database | Task | 3 | Parth
1.2.2.2 | Backend API | Task | 6 | Parth
1.2.2.3 | Web Front End | Task | 6 | Soumy
1.2.2.4 | Mobile | Task | 6 | Hardik
1.2.3 | PNM-020: Trigger Safety Notification on Not-OK Safety-Flagged Item | User Story | 14 | Developer
1.2.3.1 | Database | Task | 2 | Parth
1.2.3.2 | Backend API | Task | 4 | Parth
1.2.3.3 | Web Front End | Task | 4 | Soumy
1.2.3.4 | Mobile | Task | 4 | Hardik
1.2.4 | PNM-021: Prompt to Raise Breakdown SR on Failed Checklist Item | User Story | 14 | Developer
1.2.4.1 | Database | Task | 2 | Parth
1.2.4.2 | Backend API | Task | 4 | Parth
1.2.4.3 | Web Front End | Task | 4 | Inderjeet
1.2.4.4 | Mobile | Task | 4 | Hardik
1.2.5 | PNM-022: View Checklist History | User Story | 12 | Developer
1.2.5.1 | Backend API | Task | 4 | Ronak
1.2.5.2 | Web Front End | Task | 4 | Soumy
1.2.5.3 | Mobile | Task | 4 | Hardik
1.3 | Epic 3: Digital Log Book | Epic | 155
1.3.1 | PNM-023: Claim Equipment Ownership via First Fill | User Story | 14 | Developer
1.3.1.1 | Database | Task | 2 | Parth
1.3.1.2 | Backend API | Task | 4 | Parth
1.3.1.3 | Web Front End | Task | 4 | Soumy
1.3.1.4 | Mobile | Task | 4 | Hardik
1.3.2 | PNM-024: Transfer Equipment Ownership | User Story | 14 | Developer
1.3.2.1 | Database | Task | 2 | Parth
1.3.2.2 | Backend API | Task | 4 | Parth
1.3.2.3 | Web Front End | Task | 4 | Inderjeet
1.3.2.4 | Mobile | Task | 4 | Hardik
1.3.3 | PNM-025: Override Equipment Ownership (In-Charge) | User Story | 14 | Developer
1.3.3.1 | Database | Task | 2 | Parth
1.3.3.2 | Backend API | Task | 4 | Parth
1.3.3.3 | Web Front End | Task | 4 | Inderjeet
1.3.3.4 | Mobile | Task | 4 | Hardik
1.3.4 | PNM-026: Notify on No Owner by Cutoff | User Story | 14 | Developer
1.3.4.1 | Database | Task | 2 | Parth
1.3.4.2 | Backend API | Task | 4 | Parth
1.3.4.3 | Web Front End | Task | 4 | Soumy
1.3.4.4 | Mobile | Task | 4 | Hardik
1.3.5 | PNM-027: Non-Submission Notification & Escalation Schedule | User Story | 21 | Developer
1.3.5.1 | Database | Task | 3 | Parth
1.3.5.2 | Backend API | Task | 6 | Parth
1.3.5.3 | Web Front End | Task | 6 | Soumy
1.3.5.4 | Mobile | Task | 6 | Hardik
1.3.6 | PNM-028: Submit Digital Log Book Entry | User Story | 21 | Developer
1.3.6.1 | Database | Task | 3 | Parth
1.3.6.2 | Backend API | Task | 6 | Parth
1.3.6.3 | Web Front End | Task | 6 | Soumy
1.3.6.4 | Mobile | Task | 6 | Hardik
1.3.7 | PNM-029: View Equipment Context Panel on Log Book | User Story | 12 | Developer
1.3.7.1 | Backend API | Task | 4 | Ronak
1.3.7.2 | Web Front End | Task | 4 | Soumy
1.3.7.3 | Mobile | Task | 4 | Hardik
1.3.8 | PNM-030: Evaluate PM Triggers After Log Book Submission | User Story | 21 | Developer
1.3.8.1 | Database | Task | 3 | Parth
1.3.8.2 | Backend API | Task | 6 | Parth
1.3.8.3 | Web Front End | Task | 6 | Inderjeet
1.3.8.4 | Mobile | Task | 6 | Hardik
1.3.9 | PNM-031: View Log Book History | User Story | 12 | Developer
1.3.9.1 | Backend API | Task | 4 | Ronak
1.3.9.2 | Web Front End | Task | 4 | Soumy
1.3.9.3 | Mobile | Task | 4 | Hardik
1.3.10 | PNM-032: View Checklist & Log Book Compliance Dashboard | User Story | 12 | Developer
1.3.10.1 | Backend API | Task | 4 | Parth
1.3.10.2 | Web Front End | Task | 4 | Soumy
1.3.10.3 | Mobile | Task | 4 | Hardik
1.4 | Epic 4: Breakdown Management | Epic | 262
1.4.1 | PNM-033: Raise Breakdown Service Request | User Story | 21 | Developer
1.4.1.1 | Database | Task | 3 | Parth
1.4.1.2 | Backend API | Task | 6 | Parth
1.4.1.3 | Web Front End | Task | 6 | Soumy
1.4.1.4 | Mobile | Task | 6 | Hardik
1.4.2 | PNM-034: Auto-Classify Breakdown Priority | User Story | 21 | Developer
1.4.2.1 | Database | Task | 3 | Parth
1.4.2.2 | Backend API | Task | 6 | Parth
1.4.2.3 | Web Front End | Task | 6 | Inderjeet
1.4.2.4 | Mobile | Task | 6 | Hardik
1.4.3 | PNM-035: Assign Mechanic to Breakdown SR | User Story | 14 | Developer
1.4.3.1 | Database | Task | 2 | Parth
1.4.3.2 | Backend API | Task | 4 | Ronak
1.4.3.3 | Web Front End | Task | 4 | Soumy
1.4.3.4 | Mobile | Task | 4 | Hardik
1.4.4 | PNM-036: Reassign Mechanic on Breakdown SR | User Story | 21 | Developer
1.4.4.1 | Database | Task | 3 | Parth
1.4.4.2 | Backend API | Task | 6 | Ronak
1.4.4.3 | Web Front End | Task | 6 | Soumy
1.4.4.4 | Mobile | Task | 6 | Hardik
1.4.5 | PNM-037: Start Work on Breakdown SR | User Story | 14 | Developer
1.4.5.1 | Database | Task | 2 | Parth
1.4.5.2 | Backend API | Task | 4 | Ronak
1.4.5.3 | Web Front End | Task | 4 | Inderjeet
1.4.5.4 | Mobile | Task | 4 | Hardik
1.4.6 | PNM-038: Record BD SR Diagnosis | User Story | 21 | Developer
1.4.6.1 | Database | Task | 3 | Parth
1.4.6.2 | Backend API | Task | 6 | Ronak
1.4.6.3 | Web Front End | Task | 6 | Inderjeet
1.4.6.4 | Mobile | Task | 6 | Hardik
1.4.7 | PNM-039: Raise Spare Parts MRIS from Breakdown SR | User Story | 14 | Developer
1.4.7.1 | Database | Task | 2 | Parth
1.4.7.2 | Backend API | Task | 4 | Ronak
1.4.7.3 | Web Front End | Task | 4 | Soumy
1.4.7.4 | Mobile | Task | 4 | Hardik
1.4.8 | PNM-040: Resume Breakdown SR from On Hold | User Story | 14 | Developer
1.4.8.1 | Database | Task | 2 | Parth
1.4.8.2 | Backend API | Task | 4 | Ronak
1.4.8.3 | Web Front End | Task | 4 | Soumy
1.4.8.4 | Mobile | Task | 4 | Hardik
1.4.9 | PNM-041: Resolve Breakdown SR | User Story | 21 | Developer
1.4.9.1 | Database | Task | 3 | Parth
1.4.9.2 | Backend API | Task | 6 | Ronak
1.4.9.3 | Web Front End | Task | 6 | Soumy
1.4.9.4 | Mobile | Task | 6 | Hardik
1.4.10 | PNM-042: Capture Maintenance Activities During Breakdown Repair (PM Counter Sync) | User Story | 21 | Developer
1.4.10.1 | Database | Task | 3 | Parth
1.4.10.2 | Backend API | Task | 6 | Ronak
1.4.10.3 | Web Front End | Task | 6 | Inderjeet
1.4.10.4 | Mobile | Task | 6 | Hardik
1.4.11 | PNM-043: Confirm Fix and Close Breakdown SR | User Story | 14 | Developer
1.4.11.1 | Database | Task | 2 | Parth
1.4.11.2 | Backend API | Task | 4 | Ronak
1.4.11.3 | Web Front End | Task | 4 | Soumy
1.4.11.4 | Mobile | Task | 4 | Hardik
1.4.12 | PNM-044: Reopen Breakdown SR | User Story | 14 | Developer
1.4.12.1 | Database | Task | 2 | Parth
1.4.12.2 | Backend API | Task | 4 | Ronak
1.4.12.3 | Web Front End | Task | 4 | Soumy
1.4.12.4 | Mobile | Task | 4 | Hardik
1.4.13 | PNM-045: View Breakdown SR Timeline / Activity Log | User Story | 12 | Developer
1.4.13.1 | Backend API | Task | 4 | Ronak
1.4.13.2 | Web Front End | Task | 4 | Soumy
1.4.13.3 | Mobile | Task | 4 | Hardik
1.4.14 | PNM-046: Attach Photos to Breakdown SR | User Story | 14 | Developer
1.4.14.1 | Database | Task | 2 | Parth
1.4.14.2 | Backend API | Task | 4 | Ronak
1.4.14.3 | Web Front End | Task | 4 | Soumy
1.4.14.4 | Mobile | Task | 4 | Hardik
1.4.15 | PNM-047: Search and Filter Breakdown SR List | User Story | 12 | Developer
1.4.15.1 | Backend API | Task | 4 | Ronak
1.4.15.2 | Web Front End | Task | 4 | Soumy
1.4.15.3 | Mobile | Task | 4 | Hardik
1.4.16 | PNM-048: Flag and Alert on SR Ageing | User Story | 14 | Developer
1.4.16.1 | Database | Task | 2 | Parth
1.4.16.2 | Backend API | Task | 4 | Ronak
1.4.16.3 | Web Front End | Task | 4 | Soumy
1.4.16.4 | Mobile | Task | 4 | Hardik
1.5 | Epic 5: Preventive Maintenance | Epic | 122
1.5.1 | PNM-049: Auto-Generate PM Service Request | User Story | 14 | Developer
1.5.1.1 | Database | Task | 2 | Parth
1.5.1.2 | Backend API | Task | 4 | Ronak
1.5.1.3 | Web Front End | Task | 4 | Soumy
1.5.1.4 | Mobile | Task | 4 | Hardik
1.5.2 | PNM-050: Manually Create PM Service Request | User Story | 14 | Developer
1.5.2.1 | Database | Task | 2 | Parth
1.5.2.2 | Backend API | Task | 4 | Ronak
1.5.2.3 | Web Front End | Task | 4 | Soumy
1.5.2.4 | Mobile | Task | 4 | Hardik
1.5.3 | PNM-051: Assign Mechanic to PM SR | User Story | 14 | Developer
1.5.3.1 | Database | Task | 2 | Parth
1.5.3.2 | Backend API | Task | 4 | Ronak
1.5.3.3 | Web Front End | Task | 4 | Soumy
1.5.3.4 | Mobile | Task | 4 | Hardik
1.5.4 | PNM-052: Execute PM Checklist and Mark Item Outcomes | User Story | 21 | Developer
1.5.4.1 | Database | Task | 3 | Parth
1.5.4.2 | Backend API | Task | 6 | Ronak
1.5.4.3 | Web Front End | Task | 6 | Soumy
1.5.4.4 | Mobile | Task | 6 | Hardik
1.5.5 | PNM-053: Review and Decide on PM Item Deferrals at Closure | User Story | 21 | Developer
1.5.5.1 | Database | Task | 3 | Parth
1.5.5.2 | Backend API | Task | 6 | Ronak
1.5.5.3 | Web Front End | Task | 6 | Soumy
1.5.5.4 | Mobile | Task | 6 | Hardik
1.5.6 | PNM-054: Close Preventive Maintenance SR | User Story | 14 | Developer
1.5.6.1 | Database | Task | 2 | Parth
1.5.6.2 | Backend API | Task | 4 | Ronak
1.5.6.3 | Web Front End | Task | 4 | Soumy
1.5.6.4 | Mobile | Task | 4 | Hardik
1.5.7 | PNM-055: View PM Schedule and Compliance Status | User Story | 12 | Developer
1.5.7.1 | Backend API | Task | 4 | Ronak
1.5.7.2 | Web Front End | Task | 4 | Soumy
1.5.7.3 | Mobile | Task | 4 | Hardik
1.5.8 | PNM-056: View PM History | User Story | 12 | Developer
1.5.8.1 | Backend API | Task | 4 | Ronak
1.5.8.2 | Web Front End | Task | 4 | Soumy
1.5.8.3 | Mobile | Task | 4 | Hardik
1.6 | Epic 8: Fuel/Spare Parts MRIS | Epic | 82
1.6.1 | PNM-069: Select Spare Parts for SR-Linked MRIS | User Story | 14 | Developer
1.6.1.1 | Database | Task | 2 | Parth
1.6.1.2 | Backend API | Task | 4 | Ronak
1.6.1.3 | Web Front End | Task | 4 | Soumy
1.6.1.4 | Mobile | Task | 4 | Hardik
1.6.2 | PNM-070: Approve Spare Parts MRIS | User Story | 14 | Developer
1.6.2.1 | Database | Task | 2 | Parth
1.6.2.2 | Backend API | Task | 4 | Ronak
1.6.2.3 | Web Front End | Task | 4 | Soumy
1.6.2.4 | Mobile | Task | 4 | Hardik
1.6.3 | PNM-071: Issue Material Against Spare Parts MRIS | User Story | 14 | Developer
1.6.3.1 | Database | Task | 2 | Parth
1.6.3.2 | Backend API | Task | 4 | Ronak
1.6.3.3 | Web Front End | Task | 4 | Soumy
1.6.3.4 | Mobile | Task | 4 | Hardik
1.6.4 | PNM-072: Acknowledge Spare Parts Receipt | User Story | 14 | Developer
1.6.4.1 | Database | Task | 2 | Parth
1.6.4.2 | Backend API | Task | 4 | Ronak
1.6.4.3 | Web Front End | Task | 4 | Soumy
1.6.4.4 | Mobile | Task | 4 | Hardik
1.6.5 | PNM-073: View Spare Parts Consumption History | User Story | 12 | Developer
1.6.5.1 | Backend API | Task | 4 | Ronak
1.6.5.2 | Web Front End | Task | 4 | Soumy
1.6.5.3 | Mobile | Task | 4 | Hardik
1.6.6 | PNM-074: Auto-Cancel Spare MRIS on Equipment Transfer | User Story | 14 | Developer
1.6.6.1 | Database | Task | 2 | Parth
1.6.6.2 | Backend API | Task | 4 | Ronak
1.6.6.3 | Web Front End | Task | 4 | Soumy
1.6.6.4 | Mobile | Task | 4 | Hardik
1.7 | Epic 9: Reports & Analytics | Epic | 124
1.7.1 | PNM-076: View Equipment Utilization Report | User Story | 12 | Developer
1.7.1.1 | Backend API | Task | 4 | Ronak
1.7.1.2 | Web Front End | Task | 4 | Soumy
1.7.1.3 | Mobile | Task | 4 | Hardik
1.7.2 | PNM-077: View Downtime Report (Total, MTTR, Net Repair Time, Hold Breakdown) | User Story | 12 | Developer
1.7.2.1 | Backend API | Task | 4 | Ronak
1.7.2.2 | Web Front End | Task | 4 | Soumy
1.7.2.3 | Mobile | Task | 4 | Hardik
1.7.3 | PNM-078: View Breakdown Reports | User Story | 12 | Developer
1.7.3.1 | Backend API | Task | 4 | Ronak
1.7.3.2 | Web Front End | Task | 4 | Soumy
1.7.3.3 | Mobile | Task | 4 | Hardik
1.7.4 | PNM-079: View PM Reports (Adherence & Deferral Summary) | User Story | 12 | Developer
1.7.4.1 | Backend API | Task | 4 | Ronak
1.7.4.2 | Web Front End | Task | 4 | Soumy
1.7.4.3 | Mobile | Task | 4 | Hardik
1.7.5 | PNM-080: View Fuel Consumption Report | User Story | 12 | Developer
1.7.5.1 | Backend API | Task | 4 | Ronak
1.7.5.2 | Web Front End | Task | 4 | Soumy
1.7.5.3 | Mobile | Task | 4 | Hardik
1.7.6 | PNM-081: View Spare Parts Consumption Report | User Story | 12 | Developer
1.7.6.1 | Backend API | Task | 4 | Ronak
1.7.6.2 | Web Front End | Task | 4 | Soumy
1.7.6.3 | Mobile | Task | 4 | Hardik
1.7.7 | PNM-082: View Idle Equipment Report | User Story | 12 | Developer
1.7.7.1 | Backend API | Task | 4 | Ronak
1.7.7.2 | Web Front End | Task | 4 | Soumy
1.7.7.3 | Mobile | Task | 4 | Hardik
1.7.8 | PNM-083: Detect and Report Recurring Failures | User Story | 14 | Developer
1.7.8.1 | Database | Task | 2 | Parth
1.7.8.2 | Backend API | Task | 4 | Ronak
1.7.8.3 | Web Front End | Task | 4 | Soumy
1.7.8.4 | Mobile | Task | 4 | Hardik
1.7.9 | PNM-084: View Mechanic Performance Report | User Story | 12 | Developer
1.7.9.1 | Backend API | Task | 4 | Ronak
1.7.9.2 | Web Front End | Task | 4 | Soumy
1.7.9.3 | Mobile | Task | 4 | Hardik
1.7.10 | PNM-085: Export and Print Reports | User Story | 14 | Developer
1.7.10.1 | Database | Task | 2 | Parth
1.7.10.2 | Backend API | Task | 4 | Ronak
1.7.10.3 | Web Front End | Task | 4 | Soumy
1.7.10.4 | Mobile | Task | 4 | Hardik
1.10 | Epic 10: Masters | Epic | 48
1.10.1 | PNM-086: Configure Maintenance Activity Details Master | User Story | 3 | Developer
1.10.1.1 | Database | Task | 1 | Parth
1.10.1.2 | Backend API | Task | 1 | Ronak
1.10.1.3 | Web Front End | Task | 1 | Soumy
1.10.2 | PNM-087: Configure Equipment Checklist Points Master | User Story | 3 | Developer
1.10.2.1 | Database | Task | 1 | Parth
1.10.2.2 | Backend API | Task | 1 | Ronak
1.10.2.3 | Web Front End | Task | 1 | Soumy
1.10.3 | PNM-088: Configure Breakdown Reason Codes Master | User Story | 3 | Developer
1.10.3.1 | Database | Task | 1 | Parth
1.10.3.2 | Backend API | Task | 1 | Ronak
1.10.3.3 | Web Front End | Task | 1 | Soumy
1.10.4 | PNM-089: Configure Sub-Part Names Master | User Story | 3 | Developer
1.10.4.1 | Database | Task | 1 | Parth
1.10.4.2 | Backend API | Task | 1 | Ronak
1.10.4.3 | Web Front End | Task | 1 | Soumy
1.10.5 | PNM-090: Configure In-house Maintenance Remarks Master | User Story | 3 | Developer
1.10.5.1 | Database | Task | 1 | Parth
1.10.5.2 | Backend API | Task | 1 | Ronak
1.10.5.3 | Web Front End | Task | 1 | Soumy
1.10.6 | PNM-091: Configure Specification Field Definitions Master | User Story | 3 | Developer
1.10.6.1 | Database | Task | 1 | Parth
1.10.6.2 | Backend API | Task | 1 | Ronak
1.10.6.3 | Web Front End | Task | 1 | Soumy
1.10.7 | PNM-092: Configure Work Description Types Master | User Story | 3 | Developer
1.10.7.1 | Database | Task | 1 | Parth
1.10.7.2 | Backend API | Task | 1 | Ronak
1.10.7.3 | Web Front End | Task | 1 | Soumy
1.10.8 | PNM-093: Configure Failure Type Master | User Story | 3 | Developer
1.10.8.1 | Database | Task | 1 | Parth
1.10.8.2 | Backend API | Task | 1 | Ronak
1.10.8.3 | Web Front End | Task | 1 | Soumy
1.10.9 | PNM-094: Configure Sub-System Master | User Story | 3 | Developer
1.10.9.1 | Database | Task | 1 | Parth
1.10.9.2 | Backend API | Task | 1 | Ronak
1.10.9.3 | Web Front End | Task | 1 | Soumy
1.10.10 | PNM-095: Configure Location Master | User Story | 3 | Developer
1.10.10.1 | Database | Task | 1 | Parth
1.10.10.2 | Backend API | Task | 1 | Ronak
1.10.10.3 | Web Front End | Task | 1 | Soumy
1.10.11 | PNM-096: Configure Fuel Type Master | User Story | 3 | Developer
1.10.11.1 | Database | Task | 1 | Parth
1.10.11.2 | Backend API | Task | 1 | Ronak
1.10.11.3 | Web Front End | Task | 1 | Soumy
1.10.12 | PNM-097: Configure Material / Spare Parts Catalogue | User Story | 3 | Developer
1.10.12.1 | Database | Task | 1 | Parth
1.10.12.2 | Backend API | Task | 1 | Ronak
1.10.12.3 | Web Front End | Task | 1 | Soumy
1.10.13 | PNM-098: Configure PM Schedule Master | User Story | 3 | Developer
1.10.13.1 | Database | Task | 1 | Parth
1.10.13.2 | Backend API | Task | 1 | Ronak
1.10.13.3 | Web Front End | Task | 1 | Soumy
1.10.14 | PNM-099: Configure Opening Counter Readings (Equipment-Level) | User Story | 3 | Developer
1.10.14.1 | Database | Task | 1 | Parth
1.10.14.2 | Backend API | Task | 1 | Ronak
1.10.14.3 | Web Front End | Task | 1 | Soumy
1.10.15 | PNM-100: Configure Maintenance Points (Equipment-Level) | User Story | 3 | Developer
1.10.15.1 | Database | Task | 1 | Parth
1.10.15.2 | Backend API | Task | 1 | Ronak
1.10.15.3 | Web Front End | Task | 1 | Soumy
1.10.16 | PNM-101: Configure Sub-Part Details and Specification Values (Equipment-Level) | User Story | 3 | Developer
1.10.16.1 | Database | Task | 1 | Parth
1.10.16.2 | Backend API | Task | 1 | Ronak
1.10.16.3 | Web Front End | Task | 1 | Soumy

## Epic Timeline
WBS ID | Task Name | Estimated Hours | Days
1.1 | Epic 1: Equipment Management | 176 | 29.3333 | Row Labels | Sum of Estimated Hours | Estimation Days
1.2 | Epic 2: Daily Equipment Checklist | 76 | 12.6667 | Hardik | 248 | 35.4286
1.3 | Epic 3: Digital Log Book | 155 | 25.8333 | Parth | 262 | 37.4286
1.4 | Epic 4: Breakdown Management | 262 | 43.6667 | Ronak | 200 | 28.5714
1.5 | Epic 5: Preventive Maintenance | 122 | 20.3333 | Soumy | 268 | 38.2857
1.8 | Epic 8: Spare Parts MRIS | 82 | 13.6667 | Inderjeet | 67 | 9.5714
1.9 | Epic 9: Reports & Analytics | 124 | 20.6667 | Grand Total | 1045 | 38.2857
1.10 | Epic 10: Masters | 48 | 8
| Total | 1045 | 174.1667