## Sheet1
Type | Task
Row Labels | Sum of Estimated Hours
Hardik | 159
Parth Jani | 110
Ronak | 151
Soumy | 138
Grand Total | 558

## WBS
WBS ID | Task Name | Type | Estimated Hours | Developer
1 | HIMAPP 2.0 — Safety Module Implementation | Project
1.1 | Epic 1: Safety Induction | Epic | 84
1.1.1 | US-01: Creates Group Induction Session | User Story | 18 | Developer
1.1.1.1 | Database | Task | 6 | Ronak
1.1.1.2 | Backend API | Task | 4 | Ronak
1.1.1.3 | Web Front End | Task | 4 | Parth Jani
1.1.1.4 | Mobile | Task | 4 | Hardik
1.1.3 | US-03: Labourer Provides Signature or Thumbprint Acknowledgement | User Story | 24
1.1.3.2 | Backend API | Task | 4 | Ronak
1.1.3.3 | Web Front End | Task | 10 | Parth Jani
1.1.3.4 | Mobile | Task | 10 | Hardik
1.1.4 | US-04: Manage Induction Topic Library with Free-Text Add | User Story | 11
1.1.4.2 | Backend API | Task | 4 | Ronak
1.1.4.3 | Web Front End | Task | 4 | Parth Jani
1.1.4.4 | Mobile | Task | 3 | Hardik
1.1.5 | US-05: System Calculates Per-Person Induction Validity with Override | User Story | 6
1.1.5.2 | Backend API | Task | 2 | Ronak
1.1.5.3 | Web Front End | Task | 2 | Parth Jani
1.1.5.4 | Mobile | Task | 2 | Hardik
1.1.7 | US-07: Issue First-Time PPE Inline on Induction Screen | User Story | 18
1.1.7.2 | Backend API | Task | 6 | Ronak
1.1.7.3 | Web Front End | Task | 6 | Parth Jani
1.1.7.4 | Mobile | Task | 6 | Hardik
1.1.8 | US-08: Pending Induction List Auto-Populated from Registrations | User Story | 7
1.1.8.2 | Backend API | Task | 2 | Ronak
1.1.8.3 | Web Front End | Task | 2 | Parth Jani
1.1.8.4 | Mobile | Task | 3 | Hardik
1.2 | Epic 2: Labour Tests & Medical Records (BOCW) | Epic | 50
1.2.1 | US-09: Configure Project-Level Labour Test Requirements | User Story | 16
1.2.1.1 | Database | Task | 4 | Parth Jani
1.2.1.2 | Backend API | Task | 4 | Parth Jani
1.2.1.3 | Web Front End | Task | 4 | Soumy
1.2.1.4 | Mobile | Task | 4 | Hardik
1.2.2 | US-10: Hard Block PPE Issuance on Pending or Failed Mandatory Test Status Change to Fail | User Story | 6
1.2.2.2 | Backend API | Task | 2 | Parth Jani
1.2.2.3 | Web Front End | Task | 2 | Soumy
1.2.2.4 | Mobile | Task | 2 | Hardik
1.2.3 | US-11: Doctor Creates Medical Test Record (Form XI / BOCW) | User Story | 16
1.2.3.2 | Backend API | Task | 4 | Parth Jani
1.2.3.3 | Web Front End | Task | 6 | Soumy
1.2.3.4 | Mobile | Task | 6 | Hardik
1.2.5 | US-13: Track Pending Medical Examinations with Dashboard KPI | User Story | 6
1.2.5.2 | Backend API | Task | 2 | Parth Jani
1.2.5.3 | Web Front End | Task | 2 | Soumy
1.2.5.4 | Mobile | Task | 2 | Hardik
1.2.6 | US-14: Maintain Multiple Permanent Medical Records per Labourer | User Story | 6
1.2.6.2 | Backend API | Task | 2 | Parth Jani
1.2.6.3 | Web Front End | Task | 2 | Soumy
1.2.6.4 | Mobile | Task | 2 | Hardik
1.3 | Epic 3: PPE Issuance | Epic | 76
1.3.1 | US-15: Configure PPE Master with Labour Type Baseline Mapping | User Story | 24
1.3.1.1 | Database | Task | 4 | Ronak
1.3.1.2 | Backend API | Task | 8 | Ronak
1.3.1.3 | Web Front End | Task | 7 | Soumy
1.3.1.4 | Mobile | Task | 5 | Hardik
1.3.2 | US-16: Issue PPE via Person-First or Contractor-First Mode | User Story | 14
1.3.2.2 | Backend API | Task | 6 | Ronak
1.3.2.3 | Web Front End | Task | 4 | Soumy
1.3.2.4 | Mobile | Task | 4 | Hardik
1.3.3 | US-17: Enforce First Issue / Replacement / Additional Issuance Rule | User Story | 12
1.3.3.2 | Backend API | Task | 4 | Ronak
1.3.3.3 | Web Front End | Task | 4 | Soumy
1.3.3.4 | Mobile | Task | 4 | Hardik
1.3.4 | US-18: Auto-Consolidate PPE Issuance into Contractor-Wise MRIS | User Story | 22
1.3.4.2 | Backend API | Task | 8 | Ronak
1.3.4.3 | Web Front End | Task | 6 | Soumy
1.3.4.4 | Mobile | Task | 8 | Hardik
1.3.5 | US-19: Update Clearance Flag on First Issue Confirmation | User Story | 4
1.3.5.2 | Backend API | Task | 2 | Ronak
1.3.5.3 | Web Front End | Task | 1 | Soumy
1.3.5.4 | Mobile | Task | 1 | Hardik
1.4 | Epic 4: Entry Pass & Overall Clearance | Epic | 63
1.4.1 | US-21: System Calculates Overall Clearance from Three Conditions | User Story | 24
1.4.1.1 | Database | Task | 6 | Parth Jani
1.4.1.2 | Backend API | Task | 6 | Parth Jani
1.4.1.3 | Web Front End | Task | 6 | Soumy
1.4.1.4 | Mobile | Task | 6 | Hardik
1.4.2 | US-22: Admin Issues Entry Pass Gated on Overall Clearance | User Story | 14
1.4.2.2 | Backend API | Task | 4 | Parth Jani
1.4.2.3 | Web Front End | Task | 5 | Soumy
1.4.2.4 | Mobile | Task | 5 | Hardik
1.4.3 | US-23: Admin Overrides Not-Cleared Status with Mandatory Reason | User Story | 11
1.4.3.2 | Backend API | Task | 4 | Parth Jani
1.4.3.3 | Web Front End | Task | 4 | Soumy
1.4.3.4 | Mobile | Task | 3 | Hardik
1.4.4 | US-24: Admin Revokes Entry Pass | User Story | 7
1.4.4.2 | Backend API | Task | 3 | Parth Jani
1.4.4.3 | Web Front End | Task | 2 | Soumy
1.4.4.4 | Mobile | Task | 2 | Hardik
1.4.5 | US-25: Periodic Entry Pass Reconciliation Report | User Story | 7
1.4.5.2 | Backend API | Task | 4 | Parth Jani
1.4.5.3 | Web Front End | Task | 3 | Soumy
1.5 | Epic 5: Work Permit (PTW) | Epic | 129
1.5.1 | US-26: Configure Permit Type Master with Classification Rules | User Story | 11
1.5.1.1 | Database | Task | 2 | Ronak
1.5.1.2 | Backend API | Task | 4 | Ronak
1.5.1.3 | Web Front End | Task | 5 | Soumy
1.5.2 | US-27: Requestor Initiates PTW Request | User Story | 21
1.5.2.2 | Backend API | Task | 6 | Ronak
1.5.2.3 | Web Front End | Task | 7 | Soumy
1.5.2.4 | Mobile | Task | 8 | Hardik
1.5.5 | US-30: Fresh Checklist Every Time with Copy-From-Previous for Static Fields Only | User Story | 16
1.5.5.2 | Backend API | Task | 6 | Ronak
1.5.5.3 | Web Front End | Task | 5 | Soumy
1.5.5.4 | Mobile | Task | 5 | Hardik
1.5.6 | US-31: Enforce L1 and L2 Dual Approval Workflow | User Story | 12
1.5.6.2 | Backend API | Task | 4 | Ronak
1.5.6.3 | Web Front End | Task | 4 | Soumy
1.5.6.4 | Mobile | Task | 4 | Hardik
1.5.7 | US-32: Compliance Counting and Notification Suppression for Multi-Day Permits | User Story | 15
1.5.7.2 | Backend API | Task | 6 | Ronak
1.5.7.3 | Web Front End | Task | 4 | Soumy
1.5.7.4 | Mobile | Task | 5 | Hardik
1.5.8 | US-33: Requestor Extends Active Permit Unilaterally | User Story | 14
1.5.8.2 | Backend API | Task | 6 | Ronak
1.5.8.3 | Web Front End | Task | 5 | Soumy
1.5.8.4 | Mobile | Task | 3 | Hardik
1.5.9 | US-34: SSO Places and Releases Hold Without Consuming Validity | User Story | 6
1.5.9.2 | Backend API | Task | 2 | Ronak
1.5.9.3 | Web Front End | Task | 2 | Soumy
1.5.9.4 | Mobile | Task | 2 | Hardik
1.5.10 | US-35: EHS Manager Issues and Releases Work Stop | User Story | 7
1.5.10.2 | Backend API | Task | 2 | Ronak
1.5.10.3 | Web Front End | Task | 2 | Soumy
1.5.10.4 | Mobile | Task | 3 | Hardik
1.5.11 | US-36: Two-Party Closure of Completed Permit | User Story | 11
1.5.11.2 | Backend API | Task | 4 | Ronak
1.5.11.3 | Web Front End | Task | 4 | Soumy
1.5.11.4 | Mobile | Task | 3 | Hardik
1.5.12 | US-37: System Auto-Expires Permit and Calculates Compliance % | User Story | 8
1.5.12.2 | Backend API | Task | 4 | Ronak
1.5.12.3 | Web Front End | Task | 2 | Soumy
1.5.12.4 | Mobile | Task | 2 | Hardik
1.5.13 | US-38: PTW Notification Matrix Across the Approval and Execution Lifecycle | User Story | 8
1.5.13.2 | Backend API | Task | 4 | Ronak
1.5.13.3 | Web Front End | Task | 2 | Soumy
1.5.13.4 | Mobile | Task | 2 | Hardik
1.7 | Epic 7: Checklist & Rating Enhancements | Epic | 62
1.7.1 | US-49: Configure Photo-Mandatory Toggle per Checklist Point | User Story | 20
1.7.1.1 | Database | Task | 2 | Ronak
1.7.1.2 | Backend API | Task | 6 | Ronak
1.7.1.3 | Web Front End | Task | 6 | Soumy
1.7.1.4 | Mobile | Task | 6 | Hardik
1.7.2 | US-50: Configure Project-Level Checklist Approver | User Story | 16
1.7.2.1 | Database | Task | 2 | Parth Jani
1.7.2.2 | Backend API | Task | 6 | Ronak
1.7.2.3 | Web Front End | Task | 5 | Soumy
1.7.2.4 | Mobile | Task | 3 | Hardik
1.7.3 | US-51: Add Comments Throughout Checklist Lifecycle | User Story | 9
1.7.3.1 | Database | Task | 2 | Parth Jani
1.7.3.2 | Backend API | Task | 3 | Ronak
1.7.3.3 | Web Front End | Task | 2 | Soumy
1.7.3.4 | Mobile | Task | 2 | Hardik
1.7.4 | US-52: Enforce Rating Immutability on New Submission | User Story | 8
1.7.4.1 | Database | Task | 2 | Parth Jani
1.7.4.2 | Backend API | Task | 2 | Ronak
1.7.4.3 | Web Front End | Task | 2 | Soumy
1.7.4.4 | Mobile | Task | 2 | Hardik
1.7.5 | US-53: Configure Target CCP Score per Project Rating Template | User Story | 9
1.7.5.1 | Database | Task | 2 | Parth Jani
1.7.5.2 | Backend API | Task | 3 | Ronak
1.7.5.3 | Web Front End | Task | 2 | Soumy
1.7.5.4 | Mobile | Task | 2 | Hardik
1.8 | Epic 8: Safety MIS & Dashboards | Epic | 60
1.8.1 | US-54: User Dashboard with My Tasks and Permits | User Story | 20
1.8.1.2 | Backend API | Task | 8 | Parth Jani
1.8.1.3 | Web Front End | Task | 7 | Soumy
1.8.1.4 | Mobile | Task | 5 | Hardik
1.8.2 | US-55: Project Dashboard Across All Three Tracks | User Story | 20
1.8.2.2 | Backend API | Task | 8 | Parth Jani
1.8.2.3 | Web Front End | Task | 6 | Soumy
1.8.2.4 | Mobile | Task | 6 | Hardik
1.8.3 | US-56: Management Cross-Project Dashboard with Trends | User Story | 20
1.8.3.2 | Backend API | Task | 8 | Parth Jani
1.8.3.3 | Web Front End | Task | 6 | Soumy
1.8.3.4 | Mobile | Task | 6 | Hardik
1.9 | Epic 9:Integrations & NFRs | Epic | 34
1.9.2 | US-59: Consume Labour Registration Data from Admin Module | User Story | 10
1.9.2.1 | Database | Task | 1 | Parth Jani
1.9.2.2 | Backend API | Task | 4 | Ronak
1.9.2.3 | Web Front End | Task | 2 | Soumy
1.9.2.4 | Mobile | Task | 3 | Hardik
1.9.4 | US-61: Convert PPE Issuance to MRIS via D365 Write Integration | User Story | 24
1.9.4.1 | Database | Task | 4 | Parth Jani
1.9.4.2 | Backend API | Task | 8 | Ronak
1.9.4.3 | Web Front End | Task | 7 | Ronak
1.9.4.4 | Mobile | Task | 5 | Hardik

## Epic Timeline
HIMAPP 2.0 SAFETY MODULE — EPIC-LEVEL TIMELINE
WBS ID | Epic | Estimated Hours | Days
1.1 | Epic 1: Safety Induction | 84 | 14 | Row Labels | Sum of Estimated Hours | Days
1.2 | Epic 2: Labour Tests & Medical Records (BOCW) | 50 | 8.3333 | Hardik | 159 | 26.5
1.3 | Epic 3: PPE Issuance | 76 | 12.6667 | Parth Jani | 110 | 18.3333
1.4 | Epic 4: Entry Pass & Overall Clearance | 63 | 10.5 | Ronak | 151 | 25.1667
1.5 | Epic 5: Work Permit (PTW) | 129 | 21.5 | Soumy | 138 | 23
1.7 | Epic 7: Checklist & Rating Enhancements | 62 | 10.3333 | Grand Total | 558 | 26.5
1.8 | Epic 8: Safety MIS & Dashboards | 60 | 10
1.9 | Epic 9: Roles, Integrations & NFRs | 34 | 5.6667
| PROJECT TOTAL | 558 | 93