## WBS
WBS ID | Task Name | Type | Estimated Hours | Developer
1 | HIMAPP 2.0 — Store Module Implementation | Project
1.1 | Epic 1: Store Master Data & Configuration | Epic | 21
1.1.1 | US-01: Configure Gate Pass Type Master with Seeded Values | User Story | 6
1.1.1.1 | Database | Task | 2 | Indejeet
1.1.1.2 | Backend API | Task | 4 | Ronak
1.1.1.3 | Web Front End | Task | 0 | Soumy
1.1.2 | US-02: Configure Consignment Material Owner Master | User Story | 5
1.1.2.1 | Database | Task | 1 | Indejeet
1.1.2.2 | Backend API | Task | 2 | Ronak
1.1.2.3 | Web Front End | Task | 2 | Soumy
1.1.3 | US-03: Sync D365 Master Data (Item, Item on Hand, Activity, Equipment) | User Story | 0
1.1.3.1 | Database | Task | 0 | Indejeet
1.1.3.2 | Backend API | Task | 0 | Ronak
1.1.3.3 | Web Front End | Task | 0 | Soumy
1.1.4 | US-04: Configure Store Behaviour per Project | User Story | 7
1.1.4.1 | Database | Task | 1 | Indejeet
1.1.4.2 | Backend API | Task | 3 | Ronak
1.1.4.3 | Web Front End | Task | 3 | Soumy
1.2 | Epic 2: Gate Pass — Creation & Approval | Epic | 53
1.2.1 | US-05: Store In-Charge Creates Direct Gate Pass with Auto-Generated Number (Path A) | User Story | 17
1.2.1.1 | Database | Task | 4 | Indejeet
1.2.1.2 | Backend API | Task | 5 | Ronak
1.2.1.3 | Web Front End | Task | 4 | Soumy
1.2.1.4 | Mobile | Task | 4 | Hardik
1.2.2 | US-06: Add Multiple Line Items of Mixed Types on One Gate Pass | User Story | 0
1.2.2.1 | Database | Task | 0 | Indejeet
1.2.2.2 | Backend API | Task | 0 | Ronak
1.2.2.3 | Web Front End | Task | 0 | Soumy
1.2.2.4 | Mobile | Task | 0 | Hardik
1.2.3 | US-07: Guided 3-Step Creation Wizard with Field Validations | User Story | 8
1.2.3.2 | Backend API | Task | 2 | Ronak
1.2.3.3 | Web Front End | Task | 3 | Soumy
1.2.3.4 | Mobile | Task | 3 | Hardik
1.2.4 | US-08: P&M In-Charge Requests SR-Linked Gate Pass from SR Screen (Path B) | User Story | 0
1.2.4.1 | Database | Task | 0 | Indejeet
1.2.4.2 | Backend API | Task | 0 | Ronak
1.2.4.3 | Web Front End | Task | 0 | Soumy
1.2.4.4 | Mobile | Task | 0 | Hardik
1.2.5 | US-09: Store Approves or Rejects SR-Linked Gate Pass Request | User Story | 6
1.2.5.2 | Backend API | Task | 2 | Ronak
1.2.5.3 | Web Front End | Task | 2 | Soumy
1.2.5.4 | Mobile | Task | 2 | Hardik
1.2.6 | US-10: Two-Level Approval Workflow (L1 Store In-Charge, L2 Project Manager) | User Story | 13
1.2.6.1 | Database | Task | 1 | Indejeet
1.2.6.2 | Backend API | Task | 5 | Ronak
1.2.6.3 | Web Front End | Task | 4 | Soumy
1.2.6.4 | Mobile | Task | 3 | Hardik
1.2.7 | US-11: Approval Inbox with Ageing Reminders and Escalation | User Story | 0
1.2.7.2 | Backend API | Task | 0 | Ronak
1.2.7.3 | Web Front End | Task | 0 | Soumy
1.2.7.4 | Mobile | Task | 0 | Hardik
1.2.8 | US-12: Cancel Gate Pass with Immutable Mandatory Reason | User Story | 5
1.2.8.2 | Backend API | Task | 2 | Ronak
1.2.8.3 | Web Front End | Task | 2 | Soumy
1.2.8.4 | Mobile | Task | 1 | Hardik
1.2.9 | US-13: Backdated Gate Pass Entry with Mandatory Reason | User Story | 4
1.2.9.2 | Backend API | Task | 2 | Ronak
1.2.9.3 | Web Front End | Task | 1 | Soumy
1.2.9.4 | Mobile | Task | 1 | Hardik
1.3 | Epic 3: Gate Pass — Movement, Returns & Closure | Epic | 75
1.3.1 | US-14: Record Departure / Dispatch of Approved Outward Gate Pass | User Story | 9
1.3.1.1 | Database | Task | 1 | Indejeet
1.3.1.2 | Backend API | Task | 3 | Ronak
1.3.1.3 | Web Front End | Task | 3 | Soumy
1.3.1.4 | Mobile | Task | 2 | Hardik
1.3.2 | US-15: Record Inward Receipt for Inward Gate Passes | User Story | 6
1.3.2.2 | Backend API | Task | 2 | Ronak
1.3.2.3 | Web Front End | Task | 2 | Soumy
1.3.2.4 | Mobile | Task | 2 | Hardik
1.3.3 | US-16: Record Full and Partial Returns with Per-Line Condition | User Story | 14
1.3.3.1 | Database | Task | 1 | Indejeet
1.3.3.2 | Backend API | Task | 5 | Ronak
1.3.3.3 | Web Front End | Task | 4 | Soumy
1.3.3.4 | Mobile | Task | 4 | Hardik
1.3.4 | US-17: Raise Quantity Adjustment for Unreturnable Pending Quantity | User Story | 9
1.3.4.1 | Database | Task | 1 | Indejeet
1.3.4.2 | Backend API | Task | 3 | Ronak
1.3.4.3 | Web Front End | Task | 3 | Soumy
1.3.4.4 | Mobile | Task | 2 | Hardik
1.3.5 | US-18: Approve Adjustment with Segregation of Duties (Different L1 + PM L2) | User Story | 9
1.3.5.2 | Backend API | Task | 4 | Ronak
1.3.5.3 | Web Front End | Task | 3 | Soumy
1.3.5.4 | Mobile | Task | 2 | Hardik
1.3.6 | US-19: Close Gate Pass at Zero Pending Quantity | User Story | 5
1.3.6.2 | Backend API | Task | 2 | Ronak
1.3.6.3 | Web Front End | Task | 2 | Soumy
1.3.6.4 | Mobile | Task | 1 | Hardik
1.3.7 | US-20: Track and Alert Overdue Returns | User Story | 8
1.3.7.2 | Backend API | Task | 4 | Ronak
1.3.7.3 | Web Front End | Task | 2 | Soumy
1.3.7.4 | Mobile | Task | 2 | Hardik
1.3.8 | US-21: Generate Gate Pass PDF Document with Signatures | User Story | 7
1.3.8.2 | Backend API | Task | 5 | Ronak
1.3.8.3 | Web Front End | Task | 2 | Soumy
1.3.9 | US-22: Gate Pass List View with Search, Filters and Overdue Flags | User Story | 8
1.3.9.2 | Backend API | Task | 2 | Ronak
1.3.9.3 | Web Front End | Task | 4 | Soumy
1.3.9.4 | Mobile | Task | 2 | Hardik
1.3.10 | US-23: Offline Gate Pass Creation with Sync on Reconnect | User Story | 0
1.3.10.2 | Backend API | Task | 0 | Ronak
1.3.10.4 | Mobile | Task | 0 | Hardik
1.4 | Epic 4: Consignment Material Tracking | Epic | 77
1.4.1 | US-24: Prompt Consignment Flag on Inward Gate Pass and Auto-Create Consignment Record | User Story | 15
1.4.1.1 | Database | Task | 4 | Indejeet
1.4.1.2 | Backend API | Task | 5 | Ronak
1.4.1.3 | Web Front End | Task | 4 | Soumy
1.4.1.4 | Mobile | Task | 2 | Hardik
1.4.2 | US-25: Create Consignment Record Manually | User Story | 5
1.4.2.2 | Backend API | Task | 2 | Ronak
1.4.2.3 | Web Front End | Task | 2 | Soumy
1.4.2.4 | Mobile | Task | 1 | Hardik
1.4.3 | US-26: Record Consignment Consumption with Balance Hard Block | User Story | 13
1.4.3.1 | Database | Task | 1 | Indejeet
1.4.3.2 | Backend API | Task | 5 | Parth Jani
1.4.3.3 | Web Front End | Task | 4 | Soumy
1.4.3.4 | Mobile | Task | 3 | Hardik
1.4.4 | US-27: Record Return of Unused Consignment Material to Owner | User Story | 10
1.4.4.1 | Database | Task | 1 | Indejeet
1.4.4.2 | Backend API | Task | 4 | Parth Jani
1.4.4.3 | Web Front End | Task | 3 | Indejeet
1.4.4.4 | Mobile | Task | 2 | Indejeet
1.4.5 | US-28: Generate Consignment Return Document PDF with Reconciliation Summary | User Story | 7
1.4.5.2 | Backend API | Task | 5 | Parth Jani
1.4.5.3 | Web Front End | Task | 2 | Indejeet
1.4.6 | US-29: Auto-Derive Consignment Status Across the Lifecycle | User Story | 5 | Indejeet
1.4.6.2 | Backend API | Task | 3 | Parth Jani
1.4.6.3 | Web Front End | Task | 1 | Indejeet
1.4.6.4 | Mobile | Task | 1 | Indejeet
1.4.7 | US-30: Flag Client Supplied Balances Nearing Project End | User Story | 5
1.4.7.2 | Backend API | Task | 2 | Parth Jani
1.4.7.3 | Web Front End | Task | 2 | Indejeet
1.4.7.4 | Mobile | Task | 1 | Indejeet
1.4.8 | US-31: Consignment List with Owner-Type and Status Filters | User Story | 7
1.4.8.2 | Backend API | Task | 2 | Parth Jani
1.4.8.3 | Web Front End | Task | 3 | Indejeet
1.4.8.4 | Mobile | Task | 2 | Indejeet
1.4.9 | US-32: Maintain Vendor Sample Register with No Stock Impact | User Story | 10
1.4.9.1 | Database | Task | 1 | Indejeet
1.4.9.2 | Backend API | Task | 3 | Parth Jani
1.4.9.3 | Web Front End | Task | 4 | Indejeet
1.4.9.4 | Mobile | Task | 2 | Indejeet
1.5 | Epic 5: MRIS — Requisition, Approval & Issue | Epic | 0
1.5.1 | US-33: Raise General Store MRIS with Mandatory Activity Allocation | User Story | 0
1.5.1.1 | Database | Task | 0 | Indejeet
1.5.1.2 | Backend API | Task | 0 | Parth Jani
1.5.1.3 | Web Front End | Task | 0 | Soumy
1.5.1.4 | Mobile | Task | 0 | Hardik
1.5.2 | US-34: Raise SR-Linked Spare Parts MRIS from Within SR | User Story | 0
1.5.2.1 | Database | Task | 0 | Indejeet
1.5.2.2 | Backend API | Task | 0 | Parth Jani
1.5.2.3 | Web Front End | Task | 0 | Soumy
1.5.2.4 | Mobile | Task | 0 | Hardik
1.5.3 | US-35: Raise Fuel MRIS with 4-Party Anti-Theft Workflow | User Story | 0
1.5.3.1 | Database | Task | 0 | Indejeet
1.5.3.2 | Backend API | Task | 0 | Parth Jani
1.5.3.3 | Web Front End | Task | 0 | Soumy
1.5.3.4 | Mobile | Task | 0 | Hardik
1.5.4 | US-36: Flag Fuel Discrepancy Immutably and Notify Management | User Story | 0
1.5.4.2 | Backend API | Task | 0 | Parth Jani
1.5.4.3 | Web Front End | Task | 0 | Soumy
1.5.4.4 | Mobile | Task | 0 | Hardik
1.5.5 | US-37: Approve or Reject MRIS per Entry-Point Approver Configuration | User Story | 0
1.5.5.2 | Backend API | Task | 0 | Parth Jani
1.5.5.3 | Web Front End | Task | 0 | Soumy
1.5.5.4 | Mobile | Task | 0 | Hardik
1.5.6 | US-38: Store Issues MRIS with Real-Time Availability Re-Validation | User Story | 0
1.5.6.2 | Backend API | Task | 0 | Parth Jani
1.5.6.3 | Web Front End | Task | 0 | Soumy
1.5.6.4 | Mobile | Task | 0 | Hardik
1.5.7 | US-39: Partial Fulfilment with Auto-Created Back-Order MRIS | User Story | 0
1.5.7.2 | Backend API | Task | 0 | Parth Jani
1.5.7.3 | Web Front End | Task | 0 | Soumy
1.5.7.4 | Mobile | Task | 0 | Hardik
1.5.8 | US-40: D365 Write-Back on Issue with Silent-Failure Retry Policy | User Story | 0
1.5.8.1 | Database | Task | 0 | Indejeet
1.5.8.2 | Backend API | Task | 0 | Parth Jani
1.5.8.3 | Web Front End | Task | 0 | Soumy
1.5.9 | US-41: Daily D365 Reconciliation Report | User Story | 0
1.5.9.2 | Backend API | Task | 0 | Parth Jani
1.5.9.3 | Web Front End | Task | 0 | Soumy
1.5.10 | US-42: Auto-Cancel Open MRIS on Equipment Transfer (ECR) Completion | User Story | 0
1.5.10.2 | Backend API | Task | 0 | Parth Jani
1.5.10.3 | Web Front End | Task | 0 | Soumy
1.5.11 | US-43: Auto-Generate PPE MRIS from Safety Module Issuance | User Story | 0
1.5.11.2 | Backend API | Task | 0 | Parth Jani
1.5.11.3 | Web Front End | Task | 0 | Soumy
1.5.12 | US-44: MRIS Queue with Entry-Point, Status and Project Filters | User Story | 0
1.5.12.2 | Backend API | Task | 0 | Parth Jani
1.5.12.3 | Web Front End | Task | 0 | Soumy
1.5.12.4 | Mobile | Task | 0 | Hardik
1.6 | Epic 6: Store Dashboard & Reports | Epic | 42
1.6.1 | US-45: Store Dashboard KPI Cards Across All Features | User Story | 14
1.6.1.1 | Database | Task | 1 | Indejeet
1.6.1.2 | Backend API | Task | 5 | Parth Jani
1.6.1.3 | Web Front End | Task | 5 | Indejeet
1.6.1.4 | Mobile | Task | 3 | Hardik
1.6.2 | US-46: Dashboard Active Queues (MRIS, Gate Pass, Overdue, Consignment) | User Story | 9
1.6.2.2 | Backend API | Task | 3 | Parth Jani
1.6.2.3 | Web Front End | Task | 4 | Indejeet
1.6.2.4 | Mobile | Task | 2 | Hardik
1.6.3 | US-47: Dashboard Summary Panels (Gate Activity, MRIS Mix, D365 Status) | User Story | 4
1.6.3.2 | Backend API | Task | 2 | Parth Jani
1.6.3.3 | Web Front End | Task | 2 | Indejeet
1.6.4 | US-48: Management Summary View for PM and P&M HOD | User Story | 7
1.6.4.2 | Backend API | Task | 3 | Parth Jani
1.6.4.3 | Web Front End | Task | 4 | Indejeet
1.6.5 | US-49: Gate Pass Reports & Analytics with Export | User Story | 8
1.6.5.2 | Backend API | Task | 4 | Parth Jani
1.6.5.3 | Web Front End | Task | 4 | Indejeet
1.7 | Epic 7: Roles, Notifications, Integrations & NFRs | Epic | 21
1.7.1 | US-50: Enforce Store vs P&M Role Boundaries and Project Scope | User Story | 0
1.7.1.1 | Database | Task | 0 | Indejeet
1.7.1.2 | Backend API | Task | 0 | Parth Jani
1.7.1.3 | Web Front End | Task | 0 | Indejeet
1.7.1.4 | Mobile | Task | 0 | Hardik
1.7.2 | US-51: Deliver Store Notification Matrix N-01 to N-13 Across Channels | User Story | 8
1.7.2.1 | Database | Task | 1 | Indejeet
1.7.2.2 | Backend API | Task | 5 | Parth Jani
1.7.2.3 | Web Front End | Task | 1 | Indejeet
1.7.2.4 | Mobile | Task | 1 | Hardik
1.7.3 | US-52: Immutable Records, No Hard Deletes, and Complete Audit Trail | User Story | 6
1.7.3.1 | Database | Task | 1 | Indejeet
1.7.3.2 | Backend API | Task | 4 | Parth Jani
1.7.3.3 | Web Front End | Task | 1 | Indejeet
1.7.4 | US-53: Meet Store Module Performance and Responsiveness Targets | User Story | 7
1.7.4.2 | Backend API | Task | 3 | Parth Jani
1.7.4.3 | Web Front End | Task | 2 | Indejeet
1.7.4.4 | Mobile | Task | 2 | Hardik

## Epic Timeline
HIMAPP 2.0 STORE MODULE — EPIC-LEVEL TIMELINE
WBS ID | Epic | Estimated Hours | Days
1.1 | Epic 1: Store Master Data & Configuration | 21 | 3 | Row Labels | Estimated Hours | Days
1.2 | Epic 2: Gate Pass — Creation & Approval | 53 | 7.5714 | Hardik | 45 | 6.4286
1.3 | Epic 3: Gate Pass — Movement, Returns & Closure | 75 | 10.7143 | Indejeet | 68 | 9.7143
1.4 | Epic 4: Consignment Material Tracking | 77 | 11 | Soumy | 56 | 8
1.5 | Epic 5: MRIS — Requisition, Approval & Issue | 0 | 0 | Ronak | 64 | 9.1429
1.6 | Epic 6: Store Dashboard & Reports | 42 | 6 | Parth Jani | 53 | 7.5714
1.7 | Epic 7: Roles, Notifications, Integrations & NFRs | 21 | 3 | Grand Total | 286 | 40.8571
| PROJECT TOTAL | 289 | 41.2857